## CAB ALL (hidden)
Date | Change Requestor | Jeeves DB | Description | Justification | Prio | BC Resp | Person adding request | Decision | STATUS | Comment (Feature) | Cust notified | LINKS
| Bella TU - RFC 24/11/2015 | Current ? China | Change of Vendor of 236 Items from 5039 - 7017 | None given | 4 | EL ( CS ) |  | Propsed NO = less then 300 rows Piotr to educate in GIFT ! | REJECTED |  | Preliminary that it might b no , final deceison = 9/12
| Stephan C -RFC 27/11/2015 | Current FRA | Upfate of MOQ amd SQ from Gliwici 649 Items | Save Time of Update | 5 | EL ( CS ) |  | YES | IMPLEMENTED | 4940 | YES sprint 97
| Ida Modigh RFC 1/12/2015 | Current jeeves SDL | Change of existing Report se "excel" REPO ! | Better Follow UP | 4 | CS |  | YES | IMPLEMENTED | 4941 | YES not planned yet
| Annica B RFC 1/12 2015 | Current jeeves SDL | Skip Print preview on MO prined in SDL | Time consuming to have preview | 5 | CS |  | YES | IMPLEMENTED | 4902 | YES Sprint 96 CANNOT TEST !!!
| Sarah Keller RFC 31/11 2015 | One Jeeves | Uploading of price list details from Excel file | time consuming/feature for all 1J users | 5 | MP |  | Yes | IMPLEMENTED | 4897 | First step is just to create basic functionality and get feedback from users | https://docs.google.com/document/d/15_Sl2NFqbSaSn5m8qVoHmC1CIUBeHMGQ3U3Txnl_ufQ/edit
| Lukasz Niezgodka | One Jeeves | “Column “Item per package” is OK, but in col. “Nr of packages” if we have less than in “outerbox” at least we would like to round up and show 1 box as in attach file items 219639 and 309932 | The report is showing o nr of packages if the qty is less than 1 full box | 3 | EL ( CS ) |  | YES | OPEN | 4942 | Yes - not planned yet | https://docs.google.com/document/d/1Tv8uqXyzjK10jVbMNPtpq9VOgxPXBQCmP88cJEH11pw/edit
| Alina Garbacz RFC 15/12 | One Jeeves | For Purchase Orders above 20 000 PLN (over treshold) - we need system message before blocking PO if it,s correct and if we don't want to change anything there | It help us to avoid any mistakes on PO, waiting for unblocking it and again change it. Espicially in cases when we ar not aware of value on PO | 4 | EL (CS) |  |  | OPEN
| Nordic & West users - directly to BC | One Jeeves | BOM information for KIT/packages is visible only on picking list. It should be visible also on OA/OC, delivery note and invoice | Improve customer satisfaction. Reduce user's manual work | 4 | MP |  | YES | IMPLEMENTED | 4916 |  | https://docs.google.com/document/d/1gITPYMDx4NpqhglygOk807RntX-yZS2zfOLFF7ataCY/edit
| Anna Welin Sundsvall RFC 16/12 | current Jeeves | Change in query used for controller follow up, ataly weigt etc | To have a better follow up used for improvemets | 5 | CS |  | YES ( Andreas A) | IMPLEMENTED | 4945
| Anna Welin Sundsvall RFC 17/12 | current Jeeves | UPDATE of new cacl budget Prices du to change from AB | Need to be done ! | 5 | CS |  | YES | IMPLEMENTED | 4944
| Dorota P and Tina B PR Trading 17/12 | ONE JEEVES | EDI betweeen GLI and PR Trading was set up to Falun and SDL now we moved to GLI | Customer an Internal request | 4 | CS |  |  | OPEN | Asked for more facts and not approved by Xavier will be a project | Pls update SD and user with Feature number if OK
| Alexander Herou | One JEEVES | Problem with consolidated invoice for Norway - basic data seems wrong and we have sometimes very strange values - We would like to develop a report that collects all the included rows in order to see which items that is causing the problem and be able to correct | Basic data quality | 4 | AH |  | YES | REJECTED | 4972 | Sprint 107 | https://docs.google.com/spreadsheets/d/1y0e1k_ZULQao2EJ6aESW9m1L3eltbKL1aiHxXtOyR9k/edit#gid=1776109920
| CS Anette, Jannicke and Emilia | One JEEVES | Decision of part delivery for package items on order level, instead of settings in xxz program. | It is locking the system if a package non-delivery item is partly delivered | 4 | AH |  | YES | REJECTED | 4973 | Sprint 105
| Caroline Xu | One Jeeves | Need to add Item status in program: al | This function could show sellable items clearly under one supplier. | 3 | AH/ERLA |  | YES | IMPLEMENTED | 5021 | Sprint 113
| Caroline Xu | ONE Jeeves | Add Po Print link to G-mail by button: release PO | The default link is to Outlook and we are no longer using outlook any more. | 4 | ERLA/ALHE |  | NO - no further dev for Google connections | REJECTED | Check with Ann when we will be in the new Office 365 - Starting q1 - Ann will come back with more info until next meeting. Whitin a quarter of a year the roll-out should be ongoing. Suggestion is then to reject/Alex |  | https://docs.google.com/document/d/1NHVClGzJxXRjkKFK4_zvek4Zq7BBi7fu27ihT0LKqUQ/edit
| Caroline Xu | ONE Jeeves | Add PO entry date in row level. Program: “bp” | We could compare the confirm date with entry date to measure the KPI in row level. | 4 | ERLA/ALHE |  | YES | IN PROGRESS | 5017 |  | https://docs.google.com/document/d/1D67wzXAdkFt2AYpOF95qJxd6pTIqwoCBPJXTVnLV6XI/edit
| Caroline Xu | ONE Jeeves | Add new button to export excel report in OJ which contains attached information | We could easily get such report to run Order point list & forecast list by monthly / Quaterly. | 4 | ERLA/ALHE |  | NO - we will use QV SIOP report | REJECTED | Education for SIOP |  | https://docs.google.com/document/d/16SxYAHdU4XBBxLM10k93OTRdVMjbgvSINTOG1HATTfg/edit https://docs.google.com/spreadsheets/d/1vZ4Ez7oZHEzSyDwjQhn-k0M2p_Ww_pjbn-vVsPVxxLE/edit#gid=1701927432
| Aleksandra Pawlińska | One Jeeves |  |  | 4 | pigl |  | YES | IMPLEMENTED | 5032 | 27/1 Sprint 101 | https://docs.google.com/document/d/1_-qvaiYHyq5amwNs_vk-PC-ht8h0gcsO2lesiYSDMTs/edit
| Anna Reiter | One Jeeves | Correct planning manager for complementary MO |  | 3 | pigl |  | YES | IMPLEMENTED | 5028 Development accepted ! | 27/1 Sprint 101
| Maja Ostrowska | One Jeeves | Set proper product account in 1J Master Data for SVL items when item is created. Now by default we have HL PROD but for purchase items should be TRADED and each time user need to go to 1J and edit it. | Provide proper replication between sdl and 1j to save time for unnecessary changes. | 3 | ALHE/ERLA/CHSA |  | YES | REJECTED | 5068 | Sprint 105
| Caroline Xu | One Jeeves | Add creating time in row level in program: orp_q | We cannot define the time frame in orp_q without this field. | 3 | MP |  | YES | IMPLEMENTED | Marcin: We should add creation date to programs: orp, orp_q and orp_all - feature 5184
| Caroline Xu | One Jeeves | Need to add purchasing prices for Main supplier in article search list. Program: artikel | This function could help to save time when we want to get the price list for all sellable items for monthly report.We wanna show Gross purch price in the list view | 3 | Alhe/Erla |  | YES | IMPLEMENTED | 5174 | Sprint 107
| Valentina Semenova | CJ RU | New invoice template needed (with field "argumentation" in right upper corner) | Customer's request | 5 | MP |  | YES | IMPLEMENTED | 5058
| Alina Garbacz | One Jeeves | There is needed to block for all users beside of: Alina Garbacz, Pawel Baran, Beata Kepska, Lukasz Niezgodka possibility to make moves on item 369788 – bins: externalpet and externalpet2. It is required because it is material located outside of factory and there is no possibility to use it to production. As far as now it’s happen that it is taken to production and it cause of many confusions. | Transparency and simplification of work. | 5 | CS |  | NO | REJECTED |  | YES
| Alina Garbacz | One Jeeves | Please create windows / columns / message window – anything, that told us what amount ultimately is taken when we make goods receiving to the warehouse. | The point is, that accepting delivery where is hidden the start-up cost price we can see only the price of the unit, without double klick in the various items we do not know finally what value do the adoption. This is problematic, and as experience shows this is the cause of many problems with deviations. The problem gets even bigger when we get partial deliveries | 4 | EL |  | YES | IMPLEMENTED | 5137
| Lena Persson | Current Jeeves SDL | Add PC 5 start and Unit cost so it is visible in Order ONE program | Easier to check that Price is correct calculated when selling Factory to FActory | 3 | CS |  | YES | IMPLEMENTED | Feature 5170 4 hrs. | YES Internal test status
| Ida Modigh | Current Jeeves SDL | Add DATA in Country in Country of origin field SDL | Not on Jeeves today needed for sure ! | 5 | CS |  | YES | IMPLEMENTED | 5232 | YES Business Test Passed
| Malin Nordstrom | One Jeeves | Is it possible to change format in BM% column in Sales report/Custom report to be the same as in Overview tab? | Current solution is not clear | 5 | MP |  | Yes - it will be handle within BP process | IMPLEMENTED | 5179
| Anna Reiter | One Jeeves | Planning manager should be visible on order row and in the table on order header | It will save a time - at this moment planning manager is visible on planning list | 3 | MP |  | YES | IMPLEMENTED | It should be added during order creation process, no updates // feature: 5189
| Monica Yi | One Jeeves | In programs orp, orp_q and orp_all dispatch method is shown as a symbol (not description) and it is taken from order header instead row | Wron information is visible | 3 | MP |  | YES | IMPLEMENTED | 5184
| Kinga Leśniewska | One Jeeves | Company created using finction on PoD level have field "trading area" empty. It shjould be filled automatically based on choosen country. | VAT matrix don't work correctly with company created using this way | 5 | MP |  | YES | IMPLEMENTED | 5226
| Bella Tu | Current Jeeves (Shuzou & Sundsvall factory) | We need a warning message if the order QTY is not up to the MOQ QTY when create CO from EDI to order1 | We need this function to force the order QTY not up to the MOQ but release to production | 4 | EL |  |  | OPEN
| Sarah Keller | One Jeeves | Adjust invoice templates to HL envelopes | It will improve customer satisfaction and make address visible only. | 4 | MP |  | YES | IMPLEMENTED | 5230
| Steve Mepsted | One Jeeves | Modification of picking list template UK |  | 4 | EL |  |  | OPEN
| Lekstutis Mariusz / Birgitta Möllerskog | One Jeeves | Replace the description in Ariba” so that items in a basket are more readable for Statoil users. | ? Mariuz to tell more !! | 4 | EL |  | YES | OPEN
| Magda Kruk (Czerwińska) | One Jeeves | Change and standardization of invoices printing templates due to large number of templates in 1810 | Better control, less numbers of mistakes and saving a time of users | 4 | MP |  |  | IMPLEMENTED | 5457, 5456
| Joanna Rosol | One Jeeves | Article Serach Gliwici = change of Gliwici and Harlow serach engine to show leadtime for each product with exact dispatch date as is used for Sundsvall article search. | Customer and Area Manager like same function for all FActories | 4 | CS |  |  | OPEN | NO Approval from Xavier , many hours to do in reality ! Placed ONHOLD !
| Tomasz Mikulski | One Jeeves | Create new field "Tool owner" in vy (Tool program) |  | 3 |  |  | YES | OPEN
| Lucie Bakowa | One Jeeves | Czech templates have to be updated to using Czech signs | To increase customer satisfaction | 4 | MP |  | YES | IMPLEMENTED | 5364
| Rakuca D. (Romania), Rafał L. (Poland) and many others | One Jeeves | Create program/report to extract info about customer and contacts | At this momemt we have a lots of such requests and all of them have to be covered by our support (SQL query to database) | 4 | MP |  | NO | REJECTED | Feature 5400 - BP development, QV report
| Bela Tu (Souzhou) | Souzhou | Warning during SO registration or Order converted from EDI if the Order Qty is below the MOQ defined for the item |  | 4 | EL |  | YES | IMPLEMENTED | 5374 | For now waiting hours in Maintenance
| Stéphane Carrivain | French Jeeves + Current Jeeves | Purpose is to get : - On the requisition list a new field with the value Average Cost Price * requested Qty - Display this new field on the Requisition template | This will allow to highlight high values of requisitions | 4 | EL |  | NO | REJECTED
| Magda Kruk (Czerwińska) | One Jeeves | Due day for advance payment missing | There is no such field in advance node, hard to search for orders with payment term in the past. | 3 | MP |  | Yes | REJECTED | 5404 - Go through FBG transition project 8020 Kinga test old fuctionality and come back to Marcin 06/22 Rejected - this functionality is not needed
| Marcin Pianka | One Jeeves | Remove invoice templates (original/prints only, standard and collective) and OC templates (both print and reprint) from program order1 For LT and LV | Save maintenance time in the future | 4 | MP |  | Yes | IMPLEMENTED | 5415 - DO this through GPI project 6257
| Magda Kruk (Czerwińska) | One Jeeves | Wen we have advance payment, on final invoice on order row with item 900005 information aboout advance payment invoice number should appear | To increase whole flow of advance apayment | 4 | MP |  | ON HOLD - wait for another feature for creation on new field on order header with info about advanced inovice nr | REJECTED | 5419 - Rejected after discusion with Kinga - too low business value
| Mikael Agustsson | Current jeeves sdl | Add Full Item desription to Prod Report | We want this change to: - Improve the quality of the speed follow-up report - Strengthen the motivation of Production Leaders and operators by showing the real good results that they deliver - Carefully monitor our ability to keep DBR speeds as it is a crucial cost component that (based on the large volume) has a significant impact on the factory’s profitability The analysis will help us to - Show correct results - Make better decisions | 5 | CS |  |  | Implemented | 5438 | About Zero hrs YES NOT planned in sprint
| Rob Smith | One Jeeves | in PO row program, "Promised dispatch Date" (bp.bestlovlevdat) is empty. Would be usefull to use it as it was the case in old Jeeves to measure what was the original promise date from the factory | usefull to measure deviations between original promise and current | 4 | EL |  |  | OPEN | More investigation needed
| Andreas Lindqvist | One Jevees | Bartender Update - Problem with frames | Need of each label needs to be adjusted Impact of Falkenberg | 5 | AEK |  | Yes | REJECTED | Approx 40h Feature 5446 | Andreas E responisble
| Stephanie Roinard | FraJvs001 | Upload of datas into kus program (update of Sales rep and Sales assistant for 1000 customers) | Save time while registering sales order and avoid mistake | 5 | EL | EL | Yes | IMPLEMENTED | 5484
| Aleksandra Pawlińska | One Jeeves | Button for attach several files ( different types ) in UK | To improve efficiency, and due to new flow in Harlow FActory ( AW's to be attached to MO's ) | 4 | ? | Christer | Isn't the same what in line 67??? | REJECTED | copy of action from line 67
| Anna Selmi | One Jeeves | bar code for Bioderma | Important customer, HVP for Bioderma | 5 | MP | Kamil | YES | IMPLEMENTED | 5498

## ARCHIVE CAB ALL (hidden)
Date | Change Requestor | Jeeves DB | Description | Justification | Prio | BC Resp | Person adding request | Decision | STATUS | Comment (Feature) | Cust notified | LINKS
| Valentina Semenova Rem = 414856 date 17/11/2015 | Current Russia | In Jeeves Prod Rus need to check debts. There should be Invoice No(RU) and Invoice No., go together. | We want to have a list of the unpaid invoices with invoice no.(ru) | 5 | KIPA |  | NO | REJECTED |  | 19/11 work around shown - retrive data from fh program 25/11 waiting for feedbak if work around is ok 01/12 still not respons from Russia 01/12 data can be retrive from fh to excel - no need of new report - confirmed by Valentina
| Jessica Ljunggren - RFC directly to BC | One Jeeves | We would like to use the xakon function but since this is set as a global program today we cannot use this. We will save time and have a more effective way of work if we can use xakon locally. | save time - be able to create auto postings and allocaltion rules licaly | 4 | KIPA |  | YES | IMPLEMENTED | 4887 | 1/12 feature in sprint 96 | https://docs.google.com/document/d/1-2EG3q3bRukXyc0psjXYY8glHFzhReAgJ7IOTsKFOXY/edit# https://docs.google.com/document/d/1Avte4pyddVnBHLGC3E7xCNeQFeI1HgrffcVim64TW3U/edit
| Katarzyna Klopotowska - RFC directly to BC | One Jeeves | Activete job moving EDi invoices from EDFH to supplivcs for 1810 | Reducing the time of registered invoices, reducing possible mistakes | 5 | KIPA |  | Yes (this job is active in all compamnies in1J which are using EDI) | IMPLEMENTED | 4918 | 09/12/2015 feature in sprint 97 | https://drive.google.com/a/hl-display.com/file/d/0B6hrQ4ninuBTT0VuRnZjMWpEbVk/view?usp=sharing
| Jessica Ljunggren - RFC directly to BC | One Jeeves | We´d like to add field Pipe in form, program xkvr | Pipe is standard dimention that need to be visible | 4 | KIPA |  | YES | IMPLEMENTED | 4924 | 11/12/2015 feature in sprint 97 | https://drive.google.com/open?id=0B6hrQ4ninuBTdGVtU1I0VDJ5OGc
| One Jeeves Support/BC | One Jeeves | missing fields in VALT program | To ba able to chceck which journal was not posted user needs to see all journals in standard tab | 4 | KIPA |  | YES | IMPLEMENTED | 4958 | 2016/01/07 feature in sprint 99 | https://drive.google.com/a/hl-display.com/file/d/0B6hrQ4ninuBTTXhENV9ZRVhWaFE/view?usp=sharing
| Baris Rasinski | Curret Jeeves | Change of Query | Need to create a report, change will make it nuch easier and quicker | 5 | CS(Kinga) |  | YES | REJECTED | 5001 | YES IN Business TEST
| IT dev/BC | ONE Jeeves | missing fields in program BANK | In program BANk part of the standard fields is not visible - due to that users can not insert data corectly. Data from this program are used for EDi cominucation that is why request coming from IT/BC | 5 | KIPA |  | YES | IMPLEMENTED | 5029 | 2016/01/27 feature in sprint 100 | https://drive.google.com/open?id=0B6hrQ4ninuBTY3RYc2xRRFdDMjQ
| Caroline Xu | ONE Jeeves | inventory location in vfaktst | possiblity to easy differentiate sales doen by HUB and sales unit. Can also be helpfull for other countries to differentiate different sales flows such as customer own goods, traded ect | 4 | KIPA |  | YES | IMPLEMENTED | 5030 | 2016/01/27 feature in sprint 101 2016/03/02 CFT | https://drive.google.com/a/hl-display.com/file/d/0B6hrQ4ninuBTUFBwMnBOemZ0TEE/view?usp=sharing
| Bella TU - RFC 24/11/2015 | Current ? China | Change of Vendor of 236 Items from 5039 - 7017 | None given | 4 | EL ( CS ) |  | Propsed NO = less then 300 rows Piotr to educate in GIFT ! | REJECTED |  | Preliminary that it might b no , final deceison = 9/12
| Stephan C -RFC 27/11/2015 | Current FRA | Upfate of MOQ amd SQ from Gliwici 649 Items | Save Time of Update | 5 | EL ( CS ) |  | YES | IMPLEMENTED | 4940 | YES sprint 97
| Ida Modigh RFC 1/12/2015 | Current jeeves SDL | Change of existing Report se "excel" REPO ! | Better Follow UP | 4 | CS |  | YES | IMPLEMENTED | 4941 | YES not planned yet
| Annica B RFC 1/12 2015 | Current jeeves SDL | Skip Print preview on MO prined in SDL | Time consuming to have preview | 5 | CS |  | YES | IMPLEMENTED | 4902 | YES Sprint 96 CANNOT TEST !!!
| Sarah Keller RFC 31/11 2015 | One Jeeves | Uploading of price list details from Excel file | time consuming/feature for all 1J users | 5 | MP |  | Yes | IMPLEMENTED | 4897 | First step is just to create basic functionality and get feedback from users | https://docs.google.com/document/d/15_Sl2NFqbSaSn5m8qVoHmC1CIUBeHMGQ3U3Txnl_ufQ/edit
| Lukasz Niezgodka | One Jeeves | “Column “Item per package” is OK, but in col. “Nr of packages” if we have less than in “outerbox” at least we would like to round up and show 1 box as in attach file items 219639 and 309932 | The report is showing o nr of packages if the qty is less than 1 full box | 3 | EL ( CS ) |  | YES | OPEN | 4942 | Yes - not planned yet | https://docs.google.com/document/d/1Tv8uqXyzjK10jVbMNPtpq9VOgxPXBQCmP88cJEH11pw/edit
| Alina Garbacz RFC 15/12 | One Jeeves | For Purchase Orders above 20 000 PLN (over treshold) - we need system message before blocking PO if it,s correct and if we don't want to change anything there | It help us to avoid any mistakes on PO, waiting for unblocking it and again change it. Espicially in cases when we ar not aware of value on PO | 4 | EL (CS) |  |  | OPEN
| Nordic & West users - directly to BC | One Jeeves | BOM information for KIT/packages is visible only on picking list. It should be visible also on OA/OC, delivery note and invoice | Improve customer satisfaction. Reduce user's manual work | 4 | MP |  | YES | IMPLEMENTED | 4916 |  | https://docs.google.com/document/d/1gITPYMDx4NpqhglygOk807RntX-yZS2zfOLFF7ataCY/edit
| Anna Welin Sundsvall RFC 16/12 | current Jeeves | Change in query used for controller follow up, ataly weigt etc | To have a better follow up used for improvemets | 5 | CS |  | YES ( Andreas A) | IMPLEMENTED | 4945
| Anna Welin Sundsvall RFC 17/12 | current Jeeves | UPDATE of new cacl budget Prices du to change from AB | Need to be done ! | 5 | CS |  | YES | IMPLEMENTED | 4944
| Dorota P and Tina B PR Trading 17/12 | ONE JEEVES | EDI betweeen GLI and PR Trading was set up to Falun and SDL now we moved to GLI | Customer an Internal request | 4 | CS |  |  | OPEN | Asked for more facts and not approved by Xavier will be a project | Pls update SD and user with Feature number if OK
| Alexander Herou | One JEEVES | Problem with consolidated invoice for Norway - basic data seems wrong and we have sometimes very strange values - We would like to develop a report that collects all the included rows in order to see which items that is causing the problem and be able to correct | Basic data quality | 4 | AH |  | YES | REJECTED | 4972 | Sprint 107 | https://docs.google.com/spreadsheets/d/1y0e1k_ZULQao2EJ6aESW9m1L3eltbKL1aiHxXtOyR9k/edit#gid=1776109920
| CS Anette, Jannicke and Emilia | One JEEVES | Decision of part delivery for package items on order level, instead of settings in xxz program. | It is locking the system if a package non-delivery item is partly delivered | 4 | AH |  | YES | REJECTED | 4973 | Sprint 105
| Caroline Xu | One Jeeves | Need to add Item status in program: al | This function could show sellable items clearly under one supplier. | 3 | AH/ERLA |  | YES | IN PROGRESS | 5021 | Sprint 113
| Caroline xu | One Jeeves | We need a warning message when doing receiving in program: benilev without PO acknowledge. | We need this function to force BSO/CSO to confirm the order before receiving so every PO would be followed timely. | 5 | ALHE/ERLA |  | YES | IN PROGRESS | 5022 | Sprint 109
| Caroline Xu | ONE Jeeves | Add Po Print link to G-mail by button: release PO | The default link is to Outlook and we are no longer using outlook any more. | 4 | ERLA/ALHE |  | NO - no further dev for Google connections | REJECTED | Check with Ann when we will be in the new Office 365 - Starting q1 - Ann will come back with more info until next meeting. Whitin a quarter of a year the roll-out should be ongoing. Suggestion is then to reject/Alex |  | https://docs.google.com/document/d/1NHVClGzJxXRjkKFK4_zvek4Zq7BBi7fu27ihT0LKqUQ/edit
| Caroline Xu | ONE Jeeves | Add PO entry date in row level. Program: “bp” | We could compare the confirm date with entry date to measure the KPI in row level. | 4 | ERLA/ALHE |  | YES | IN PROGRESS | 5017 |  | https://docs.google.com/document/d/1D67wzXAdkFt2AYpOF95qJxd6pTIqwoCBPJXTVnLV6XI/edit
| Caroline Xu | ONE Jeeves | Add new button to export excel report in OJ which contains attached information | We could easily get such report to run Order point list & forecast list by monthly / Quaterly. | 4 | ERLA/ALHE |  | NO - we will use QV SIOP report | REJECTED | Education for SIOP |  | https://docs.google.com/document/d/16SxYAHdU4XBBxLM10k93OTRdVMjbgvSINTOG1HATTfg/edit https://docs.google.com/spreadsheets/d/1vZ4Ez7oZHEzSyDwjQhn-k0M2p_Ww_pjbn-vVsPVxxLE/edit#gid=1701927432
| Aleksandra Pawlińska | One Jeeves |  |  | 4 | pigl |  | YES | IMPLEMENTED | 5032 | 27/1 Sprint 101 | https://docs.google.com/document/d/1_-qvaiYHyq5amwNs_vk-PC-ht8h0gcsO2lesiYSDMTs/edit
| Anna Reiter | One Jeeves | Correct planning manager for complementary MO |  | 3 | pigl |  | YES | IMPLEMENTED | 5028 Development accepted ! | 27/1 Sprint 101
| Maja Ostrowska | One Jeeves | Set proper product account in 1J Master Data for SVL items when item is created. Now by default we have HL PROD but for purchase items should be TRADED and each time user need to go to 1J and edit it. | Provide proper replication between sdl and 1j to save time for unnecessary changes. | 3 | ALHE/ERLA/CHSA |  | YES | REJECTED | 5068 | Sprint 105
| Aleksandra Pawlińska | One Jeeves | After processing button "Adjust order for deliveries" system overwite existing information in field "External text" with info about PoD. There should be question if system should overwite ot add new text below | Avoiding errors | 3 | MP |  | YES | OPEN | 5034
| Caroline Xu | One Jeeves | Add creating time in row level in program: orp_q | We cannot define the time frame in orp_q without this field. | 3 | MP |  | YES | IMPLEMENTED | Marcin: We should add creation date to programs: orp, orp_q and orp_all - feature 5184
| Caroline Xu | One Jeeves | Need to add purchasing prices for Main supplier in article search list. Program: artikel | This function could help to save time when we want to get the price list for all sellable items for monthly report.We wanna show Gross purch price in the list view | 3 | Alhe/Erla |  | YES | IMPLEMENTED | 5174 | Sprint 107
| Valentina Semenova | CJ RU | New invoice template needed (with field "argumentation" in right upper corner) | Customer's request | 5 | MP |  | YES | IMPLEMENTED | 5058
| Alina Garbacz | One Jeeves | There is needed to block for all users beside of: Alina Garbacz, Pawel Baran, Beata Kepska, Lukasz Niezgodka possibility to make moves on item 369788 – bins: externalpet and externalpet2. It is required because it is material located outside of factory and there is no possibility to use it to production. As far as now it’s happen that it is taken to production and it cause of many confusions. | Transparency and simplification of work. | 5 | CS |  | NO | REJECTED |  | YES
| Alina Garbacz | One Jeeves | Please create windows / columns / message window – anything, that told us what amount ultimately is taken when we make goods receiving to the warehouse. | The point is, that accepting delivery where is hidden the start-up cost price we can see only the price of the unit, without double klick in the various items we do not know finally what value do the adoption. This is problematic, and as experience shows this is the cause of many problems with deviations. The problem gets even bigger when we get partial deliveries | 4 | EL |  | YES | IMPLEMENTED | 5137
| Lena Persson | Current Jeeves SDL | Add PC 5 start and Unit cost so it is visible in Order ONE program | Easier to check that Price is correct calculated when selling Factory to FActory | 3 | CS |  | YES | IMPLEMENTED | Feature 5170 4 hrs. | YES Internal test status
| Ida Modigh | Current Jeeves SDL | Add DATA in Country in Country of origin field SDL | Not on Jeeves today needed for sure ! | 5 | CS |  | YES | IMPLEMENTED | 5232 | YES Business Test Passed
| Malin Nordstrom | One Jeeves | Is it possible to change format in BM% column in Sales report/Custom report to be the same as in Overview tab? | Current solution is not clear | 5 | MP |  | Yes - it will be handle within BP process | IMPLEMENTED | 5179
| Anna Reiter | One Jeeves | Planning manager should be visible on order row and in the table on order header | It will save a time - at this moment planning manager is visible on planning list | 3 | MP |  | YES | IMPLEMENTED | It should be added during order creation process, no updates // feature: 5189
| Monica Yi | One Jeeves | In programs orp, orp_q and orp_all dispatch method is shown as a symbol (not description) and it is taken from order header instead row | Wron information is visible | 3 | MP |  | YES | IMPLEMENTED | 5184
| Kinga Leśniewska | One Jeeves | Company created using finction on PoD level have field "trading area" empty. It shjould be filled automatically based on choosen country. | VAT matrix don't work correctly with company created using this way | 5 | MP |  | YES | IMPLEMENTED | 5226
| Bella Tu | Current Jeeves (Shuzou & Sundsvall factory) | We need a warning message if the order QTY is not up to the MOQ QTY when create CO from EDI to order1 | We need this function to force the order QTY not up to the MOQ but release to production | 4 | EL |  |  | OPEN
| Sarah Keller | One Jeeves | Adjust invoice templates to HL envelopes | It will improve customer satisfaction and make address visible only. | 4 | MP |  | YES | IMPLEMENTED | 5230
| Steve Mepsted | One Jeeves | Modification of picking list template UK |  | 4 | EL |  |  | OPEN
| Lekstutis Mariusz / Birgitta Möllerskog | One Jeeves | Replace the description in Ariba” so that items in a basket are more readable for Statoil users. | ? Mariuz to tell more !! | 4 | EL |  | YES | OPEN
| Magda Kruk (Czerwińska) | One Jeeves | Change and standardization of invoices printing templates due to large number of templates in 1810 | Better control, less numbers of mistakes and saving a time of users | 4 | MP |  |  | IMPLEMENTED | 5457, 5456
| Joanna Rosol | One Jeeves | Article Serach Gliwici = change of Gliwici and Harlow serach engine to show leadtime for each product with exact dispatch date as is used for Sundsvall article search. | Customer and Area Manager like same function for all FActories | 4 | CS |  |  | OPEN | NO Approval from Xavier , many hours to do in reality ! Placed ONHOLD !
| Sandra Malczyk/ Magda Kruk | One Jeeves | Adding local account to program Nobi iin tabs : customer invoices and suppier invoices to bea bale to poste bank statement more efficienlty | to be able to poste bank statement more efficiently | 5 | KL |  | YES (project 8020) | IMPLEMENTED | 5359
| Tomasz Mikulski | One Jeeves | Create new field "Tool owner" in vy (Tool program) |  | 3 |  |  | YES | OPEN
| Magda Kruk (Czerwińska) | One Jeeves | Picture of printed invoice safed in fh | Legal demand to show exacly the same copy of the invoice as orginal sent to customer if tax office will required data. additionaly control function for fiance - to be able to follow if corect templaets are used for printout of corective invoices comind from credit order and price adjustment | 5 | KL |  | YES ( project 8020) | IMPLEMENTED | 5353 | sprint 109 | https://docs.google.com/document/d/1Dc-jABl6Y0Iq4mFDNNr11c6_XICv3ltzXgChcUTZGFw/edit
| Lucie Bakowa | One Jeeves | Czech templates have to be updated to using Czech signs | To increase customer satisfaction | 4 | MP |  | YES | IMPLEMENTED | 5364
| Rakuca D. (Romania), Rafał L. (Poland) and many others | One Jeeves | Create program/report to extract info about customer and contacts | At this momemt we have a lots of such requests and all of them have to be covered by our support (SQL query to database) | 4 | MP |  | NO | REJECTED | Feature 5400 - BP development, QV report
| Bela Tu (Souzhou) | Souzhou | Warning during SO registration or Order converted from EDI if the Order Qty is below the MOQ defined for the item |  | 4 | EL |  | YES | IMPLEMENTED | 5374 | For now waiting hours in Maintenance
| Stéphane Carrivain | French Jeeves + Current Jeeves | Purpose is to get : - On the requisition list a new field with the value Average Cost Price * requested Qty - Display this new field on the Requisition template | This will allow to highlight high values of requisitions | 4 | EL |  | NO | REJECTED
| Magda Kruk (Czerwińska) | One Jeeves | Due day for advance payment missing | There is no such field in advance node, hard to search for orders with payment term in the past. | 3 | MP |  | Yes | REJECTED | 5404 - Go through FBG transition project 8020 Kinga test old fuctionality and come back to Marcin 06/22 Rejected - this functionality is not needed
| Marcin Pianka | One Jeeves | Remove invoice templates (original/prints only, standard and collective) and OC templates (both print and reprint) from program order1 For LT and LV | Save maintenance time in the future | 4 | MP |  | Yes | IMPLEMENTED | 5415 - DO this through GPI project 6257
| Magda Kruk (Czerwińska) | One Jeeves | Wen we have advance payment, on final invoice on order row with item 900005 information aboout advance payment invoice number should appear | To increase whole flow of advance apayment | 4 | MP |  | ON HOLD - wait for another feature for creation on new field on order header with info about advanced inovice nr | REJECTED | 5419 - Rejected after discusion with Kinga - too low business value
| Mikael Agustsson | Current jeeves sdl | Add Full Item desription to Prod Report | We want this change to: - Improve the quality of the speed follow-up report - Strengthen the motivation of Production Leaders and operators by showing the real good results that they deliver - Carefully monitor our ability to keep DBR speeds as it is a crucial cost component that (based on the large volume) has a significant impact on the factory’s profitability The analysis will help us to - Show correct results - Make better decisions | 5 | CS |  |  | Implemented | 5438 | About Zero hrs YES NOT planned in sprint
| Rob Smith | One Jeeves | in PO row program, "Promised dispatch Date" (bp.bestlovlevdat) is empty. Would be usefull to use it as it was the case in old Jeeves to measure what was the original promise date from the factory | usefull to measure deviations between original promise and current | 4 | EL |  |  | OPEN | More investigation needed
| Jessica Ljunggren | Curent Jeeves Hong Kong | update of alternative suppliers in Hong Kong - nessesery for implementation for new BC solution |  | 5 | KL |  | Yes | IMPLEMENTED | 5474 | sprint 111
| Imee Santos | One Jeeves | bank charges in in currency in INB - field need to be moved from all fields to HL Standard | for accounts restricted just for currency standard field avaliable at the moment can not be used - user need to see fileds for currency - at the moment only manula posting of bank charges can be used as workaround - additional workload | 5 | KL |  | Yes (project 6263) | IMPLEMENTED | 5471 | 5471 sprint 111 | https://docs.google.com/document/d/1Sniuv-ue98sXYhWTaj40WSKvCtmaHcCyd6kJpam-6Mw/edit#
| Kinga Leśniewska | One Jeeves | exchange rate in vfaktst - the wrong exchange rate is shown at the moment - it is order rate insted of invoice rate |  | 4 | KL | KL | Yes | IMPLEMENTED | 5473 | sprint 111
| Jenny Hedberg | Current Jeeves HFS | macro updating OCR number for HFS - nessesery for finalyng implementation of sepa functionality |  | 5 | KL | KL | Yes (Sepa project) | IMPLEMENTED | Go through SEPA project - plan time for release 112? Rough est 16-24 h 5497 sprint 112 | 5497 sprint 112
| Andreas Lindqvist | One Jevees | Bartender Update - Problem with frames | Need of each label needs to be adjusted Impact of Falkenberg | 5 | AEK |  | Yes | REJECTED | Approx 40h Feature 5446 | Andreas E responisble
| Kinga Leśniewska | One Jeeves | VAt rate on the item - should be local filed as all Vat releated fields - now is global | no possiblity to use Vat on item level due to fact that field is global | 4 | KL | KL | Yes | IMPLEMENTED | 5477
| Aleksandra Pawlińska | One Jeeves | "Get multi file" button should work in order1 and xti https://drive.google.com/open?id=0B76Z_xXyAkTsV29SeTFEUWt5bU0 | To save a time | 3 | MP | MP | Yes | OPEN | 4049
| Stephanie Roinard | FraJvs001 | Upload of datas into kus program (update of Sales rep and Sales assistant for 1000 customers) | Save time while registering sales order and avoid mistake | 5 | EL | EL | Yes | IMPLEMENTED | 5484
| Aleksandra Pawlińska | One Jeeves | Button for attach several files ( different types ) in UK | To improve efficiency, and due to new flow in Harlow FActory ( AW's to be attached to MO's ) | 4 | ? | Christer | Isn't the same what in line 67??? | REJECTED | copy of action from line 67
| Anna Selmi | One Jeeves | bar code for Bioderma | Important customer, HVP for Bioderma | 5 | MP | Kamil | YES | IMPLEMENTED | 5498
| Leszek Kwiatkowski | One Jeeves | change invetory fields design to 5 decimal places | it is possible to pick material for more than 2 decimal places but it is not possible to see how much is left in stock and to do the stocktaking | 5 | AEL | Julia | YES but need to be disscus with Christer | IN PROGRESS | 5546
| Rob Smith | One Jeeves | Capture original confirmed date by factory | Save time | 4 | EL | EL | Yes | OPEN | 5494
| Maelle Fauconnier | FraJvs001 | Upload item description language from XL file | Save time | 5 | EL | EL | yes | IMPLEMENTED | 5493
| Marcin PIanka | One Jeeves | Use functionality of 5439 for standard purchase orders (not only DD) | Save time, better communication, less | 4 | EL | MP | NO | REJECTED | 07/09/2016 EL : for stad PO, the procurement dpt job is to check the order response
| Stephen Mepsted | One Jeeves | New inventory location needed - called "Lightwood " | "We have another outside storage company who stores our bulk stock. If we don’t locate it there sales can sell the stock thinking its onsite and ready available also it’s for the auditors when they come to check our inventory." | 4 | EL | MP | NO | REJECTED | 5534 | YES
| Ida Modigh | Current Jv sdl ( ONE Jeeves 9 | We still have problems with "article description 2" in ONE Jeeves. We first noticed this when we received printed pos from ex Harlow, when they place one of our items alla of articles description2 comes through on the PO. This is not good, especially as the information is only for Sundsvall. Maja O has confirmed that a Feature was processed to stop this from happening with new items, so at least that is done. but for old items that text is already there. ( I presume she stopped the art descr 2 being tranfered from Sundsvall to ONE Jeeves ). I do not know how to solve this, I presume you will have to go in to each local jeeves to remove what has been transferred in asrt description 2 for the Sundsvall Items. | The text is only internal and not for the salescompanies, as well as it really does not look good on gthe orders. I have attached an example | 4 | JH | CS |  | IMPLEMENTED | 5587
| Leszek Kwiatkowski | One Jeeves | Block possibility of: 1) setting items to status: - Sellable or - Component not for sale or - Approved for production Where CurrentCostPrice = 0 and Product Account = HLPROD. 2) creating Manufacturing Order where current cost price of item is equal to 0 and itemStatus = Approved for production | This is to ensure correct value of goods on stock and correct bookings of COGS in ERP system while it is being invoiced. | 5 | AEL | JH |  | IN PROGRESS | 5547Completed , 5549 remain
| Aleksandra Pawlińska | One Jeeves | Feature for Button 'Update sales price' to update price on PO | inccorret BC values on the invoices | 5 | JH | JH |  | IMPLEMENTED | 5536
| Leszek Kwiatkowski | One Jeeves | Block item calculation if there is an atempt to calculate on quantity = 1. | This is to ensure correct value of goods on stock and correct bookings of COGS in ERP system while it is being invoiced. | 5 | JH | JH |  | IMPLEMENTED | 5548
| Sarah Keller | One Jeeves | To improve process please: a) add pop-up message when user wants to change quantity on sales order row level when connection CO-PO-CO is already established but it is not confirmed yet. b) when user wants to change quantity in sales order and po is already confirmed by factory then system should change quantity only in sales order. | Possibility to change quantity on SO without effecting PO | 4 | EL/MP | MP | YES | OPEN | 5487
| Katarzyna Zelwor | One Jeeves | During copying order rows within one quotation system should copy also field: "Inquiry date" | - save user's time - make proces easier - be sure this field is filled - these values are taken into KPI | 4 | MP | MP | yes | IMPLEMENTED | 5593
| Paulina Wróblewska | One Jeeves | Add time signature on MO ROW after Item recalculation. | Statistical purposes. Now we write each row individually to calculate preparation LT. To have control whether we meet our deadlines and KPIs. | 4 | JH | JH | yes | IMPLEMENTED | 5697
| Paulina Wróblewska | One Jeeves | Possibility to add date in „deadline column” on MO ROW that would be manually fullfiled by business service | Possibility to prioritize work. To have control whether we meet our deadlines and KPIs. | 4 | JH | JH | yes | IMPLEMENTED | 5828
| Kinga Lesniewska | One Jeeves | all account segment visible in ANLG program | All used account segments should be visible for users in all used programs for anailzes and possility to modify | 3 | KL | KL | yes | IMPLEMENTED | 5609 |  | https://docs.google.com/document/d/17r0fgxLMmOJ43EKqjW_VyRNKZW7H5MRDcN8A13WDnfs/edit
| Katarzyna Kłopotkowska/ Marcin Dutkiewicz | One Jeeves | 3 different templates needed for Romania (RON, EUR, HUF) // Request's update - there will be 3 different footers - 1 for RON, 1 for HUF and 1 for EUR which is ok | Legal demand - different account for different currency | 5 | MP | MP | Y | IMPLEMENTED | 5655
| Stephane Carrivain | FraJvs001 | Upload of new Production Lead time for Gliwice items | Provide relevant informations to process requisitions and availablity of items in stock | 5 | EL | EL | yes | IMPLEMENTED | 5621
| Marcin Dutkiewicz / Anna Czudaj | One Jeeves | Create readable version of polish tax file for VAT | As legal demand polish entities need to send data to tax office in html file form. Files should be checked before sending but it is not possible with html structure. On the base of request report should be created in which data from the file will be visible in readable form | 5 | KL | KL | yes (project 6257) | IMPLEMENTED | 5650
| Katarzyna Klopotowska | One Jeeves | ICT and EDI invoices posted in supplinvcs once a day | to have all invoices coming by ICT and EDI posted with vouchrse nubers one by one - easier to keep control |  | KL | KL | NO - rejected by KL | REJECTED |  | Hej Kasiu Sorry for switching to English but I will be off soon and Beki will take part of my duties - so we already now agreed that I will include her in most of the issues which I’m running now So – there is no option to do the setup as you would like to have: ICT invoices posted once a day one by one instead of appearing in supplier invoices program the same time as they are issued by factory How it works: When Hub and factory are in One Jeeves invoices and orders are send by ICT– this way of communication causes that if transaction is made in one company it appears the same time in another – no matter if we talking about sending invoice from factory to HUB or sending order from Hub to factory. Everything is happening the same time. There is no option to change that – general rules for all When factory is outside one Jeeves as 1140 then we have Edi communication – this is a little bit different – here to send info you need to do something: print report or something like that – depending on the transaction. When it comes to supplier invoices send from 1140 to 1810. When 1140 is issuing invoice Edi message is send and invoice appear in edfh in 1810. From edfh invoices are send to supplier invoices program during the night So this is working as you would like to have – once a day and you will have sequence of vouchers for those invoices But there is no option to change that for ICT communication
| Marcin Dutkiewicz | One Jeeves | Change in EDI logic - way how VAt info is sent | To be able to send corect Vat data from invoice row level (project 8020) - only for Tieto | 5 | KL | KL | yes (project 8020) | IMPLEMENTED | 5648
| Magda Kruk/ Sandra Malczyk | One Jeeves | Local account on postings in UOH and SUPPLINVCS | To be able to save time and to avoid corection diuring manual taping of local accounts | 5 | KL | KL | yes | IMPLEMENTED | 5658
| Magda Kruk/ Anna Czudaj | One Jeeves | tax declaration for VAt UE - xml file from Jeeves | There is a legal obligation in UE to report all EU transaction on special VAT declaration. Usually this is done manually but due to large number of transaction for Gliwice entities is become to be not possible to manage. Due to that fact decision was taken that process should be automatized - to avoid errors, to save time ( 2 days a month) - in the scope of project 6257 - cvhange just for 1810 and 1190 | 5 | KL | KL | yes | IMPLEMENTED | 5665
| Ida Modigh / Håkan T | Current Jeeves SDL | To be able to give a correct price to the customer and track the hit rate of quotationswe would like to do the following change in the Sundsvall Jeeves. Add a 4 digit field for the OFF number in customer order program xxx that is searchable and possible to use in queries. The field should be on the order row as it will be matched to specific articles. | Messure perfomance and give feedback | 4 |  | CS | yes | OPEN
| Tiina Holma | One Jeeves | Tick box to programs Invoising (orderhf) and also for Customer (kus) For invoicing; to help take only e-invoices out, so we can handle better our outgoing invoices. We do not need to double check every invoice whether it has been gone by IT or should we send paper invoice to customer. And for kus; to mark customer with correct information so it can be checked easily. We can check from this program if their invoices are normally send via IT or by post. | Two of our biggest customers has waited e-invoicing for a year now. This will help us CSO here in the office with easier way to print invoices and we save money and resource’s when we don’t print unnecessary paper invoices. | 4 |  | CS | Go back and look at process. | OPEN
| Maelle Fauconnier | FraJvs001 | Import of Item description language from XL in arb table |  | 4 |  | EL |  | IMPLEMENTED | 5664
| Olivier Pedroncini | FraJvs001 | Disable possibility to use the "X" to delete orders on order rows | Wrong figures in QV Same solution as OneJeeves requested | 4 |  | EL |  | IMPLEMENTED | 5654
| Emilia H | ONE Jeeves | Freight charge are missed due to missing info when Disptaching we like som fields to be Mandontary | We send goods for free | 5 |  | CS | Yes | Closed | We have made achange by setting rules so that right Disptach method are choosen lets see outcome of that ! Erwan and CS to discus next step later
| Marcin Dutkiewicz | One Jeeves | E-mail confirmation if exchange rates have been uploaded correctly | Save time and give info to Customer service if fiance team is not avaliable - background - legal demand to issue invoice with daily rate; Request was rised diuring 8020 by Nordic countries | 4 | KL | KL | Yes | IMPLEMENTED | 5680
| Kinga Lesniewska | One Jeeves | Design in xpvlr | To addjust e-approval programs to polish requirements some fields need to ne moved from all fields tab to Hl Standard tab - e-approval - part of project 6257 | 4 | KL | KL | Yes | IMPLEMENTED | 5681 Gliwici Imprv.
| Susann Radestrom | One Jeeves | Design in le - remove checkbox payment befor finall app from tabs visible for users | To unable users to pay invoices without finall approval | 4 | KL | KL | Yes | IMPLEMENTED | 5728
| Susann Radestrom | One Jeeves | to block possiblity of unblock bloked customers and orders only for fiancial users | Only fiance should be able to unblock orders and customers bloked after retriving credit limit | 5 | KL | KL | yes | OPEN | Use Security Mgr ?
| Pascal Aubert | FraJvs001 | Remove from arb.artbeskr2 all return chariot caracters when the item description is ending with this caracter (this caracter can appear several times) | field arb.artbeskr2 contains from time to time char(10) (return chariot). As a consequence some templates are wrongly printed (footer missing with sum amount, vat,etc... Apprx 1800 records affected in FraJvs001. Tomek Sarniak knows about the issue in the support dpt | 4 | EL | EL |  | OPEN
| Kinga Lesniewska | One Jeeves | adjustments for functionality implemented with 5353 - performacje issue with printing invoices from order 1 | to make proces stable | 5 | KL | KL | Yes | REJECTED | 5684 project 6257
| Magda Kruk / Anna Czudaj | One Jeeves | adjustments to functionality implemented with 5599 and 5653 - polisk control files | to secure functionlity | 5 | KL | KL | Yes | IMPLEMENTED | 5683 project 6257
| Gosia Stasierska | One Jeeves | Pb with picking list in following case : 1/ Order with Part delivery allowed 2/ Booking done against few order rows (the one available in stock) 3/ Picking list printed for part of the order 4/ Receive delivery done while the picking is in progress making new order rows fully booked but not on the picking list Issue : When the warehouse staff is dispatching the goods, risk to dispatch in the system more goods that originally on the picking list | Secure the dispatch flow and avoid customer claims | 5 | EL | EL | Investigate more EL | OPEN
| Maelle Fauconnier | FraJvs001 | New import of item description language Fr | Customer demand to get clear descriptions of items | 5 | EL | EL | Yes | IMPLEMENTED | 5694
| Xavier V | All ( GLI HUB ) | I guess that we need to look into “linking” order rows once they have been created in the system in order to have only one invoice. Let me know how this can be done. | Customer in Sweden receiving 8 cm of invoices .. | 5 |  | CS | Investigate MORE ! Anders LAutmann will call me for discusion how customer see on it. | Closed | Need to discus exatly need what is needed in more of a detail // Christer After Discussions with Anders Lautmann and Anette Karlssom we decided to CLOSE
| Emilia Hermio | One Jeeves | Please add status of claim and customer info to list mode in program ork. | Make program more user friendly and useful. Also it will save a time. | 4 | MP | MP | Yes | IMPLEMENTED | 5742
| Mikael Agustsson - 161114 | Current Jeeves SDL(Systid) | Create an overview screen in the tool room to enable the changeover personnel to synchronize and plan their activities in an optimal way. | According to a master's thesis performed in the spring 2016 one of the losses in production was from bad timing of the tool changeovers. No system support exists today to optimize changeovers. | ? | ? | AEL | On hold | OPEN | 5784
| Katarzyna Zelwor | One Jeeves | When field "Inquiry date" (ofh.q_cusreqquoteday) on quotation's header is filled then during creation new quotation row this date should be copied automatically to field "Inquiry date" (ofp.q_cusreqquoteday). | To save time and have more realistic lead times | 4 | MP | MP | yes | IMPLEMENTED | 5762
| Maja Ostrowska | One Jeeves | Improve Po layout | Still not efficient layout, loosing to much space, wasting to many sheets | 4 | Erwan? | Maja Ostrowska |  | OPEN | 5758
| 1J Support + Jackie Kilbridge | One Jeeves | More detailed information about email status needed | At this moment we have information that email with invoice has been moved out of Jeeves but without veryfiaction in smtp server. For example email with wrong address has status "sent ok" but email was no send. | 4 | MP | MP | yes | IMPLEMENTED | 5774
| Valentina Siemionowa | Russian CJ | Small adjustment for RU CJ invoices are needed - new stamp. | Legal demand. | 5 | MP | MP | yes | IMPLEMENTED | 5775
| Lena Persson | Current Jeeses SDL | Add Country of Origin and Stat CODE on Invoice, Order conf and Delivery note ( note CR ) | Customer demand ! | 5 |  | CS | yes | IMPLEMENTED | 6112
| Barbara Misiaczek | One Jeeves | We need to have additional 4 days included into LT which is calculated in estimator. Those days are need for administration, preparation, planning. Moreover if LT is f.e. 1.2 it should be round up to 2. MP: Value 4 should be set as a parameter | Offering Team is obliged to give an information about production LT on the offer. For this moment, system gives only MFG LT+BOM LT without extra days for preparation. | 5 | MP | MP | yes | REJECTED | 5785 / Factory does not need this functionality any more
| Marcin Pianka | One Jeeves/DW | We have to create tabkle to keep information about deleted orders and order rows. | Right now user can delete orders and order rows the same day like there were created. Tghe issue is with order rows delerted after uploading and processing of DW. Such order rows are still in DW/QV but not in 1J. | 4 | MP | MP | yes | IMPLEMENTED | 5796
| Anna Reiter | One Jeeves | Number of points to be adjusted in template "pallet spec" | Better customer satisfaction, lower number of errors | 4 | MP | MP | yes | REJECTED | 5799 / Rejected - customer will not pay to external supplier
| Erwan Lardic | One Jeeves / DW | Year End routine 2016-2017 |  | 5 | EL | EL | Yes | IMPLEMENTED | 5787
| Pascal Aubert | FraJvs001 | Update of Terms in Conditions for all customers that have been ordering during 2016 | Align with financial decisions (reduce payment delays, imporve cash flow) | 5 | EL | EL | yes | IMPLEMENTED | 5789
| Olivier Pedroncini | All Asian companies current Jeeves | Block the possibility to remove order rows by using the "X" on order row level for all Asian Jeeves db | Wrong Backlog in Qlikview which doesn't give proper figures to management | 3 | EL/MP | EL |  | OPEN | First : investigations regarding the number of implicated order rows No development for this single feature but instead cleaning feature one per quarter in the datawarehouse
| Olivier Pedroncini | All Asian companies current Jeeves | On the Asian country, with current Jeeves,the cristal report 1401 is not working properly on program BP. I would like to implement the 1401 report from the database FRAJVS001 called 1401 Test which is working well. Priority : 1/ Thailand 2/ Indonesia 3/ Other asian countries | We need to have a working report to be able to justify this account on all current Jeeves database. | 5 | EL/MP | EL | Yes | IMPLEMENTED | 5805 Marcin: Łukasz Sokół checked Jeeves in Asia - there is no deleted order rows in CJ sales offices. Only about 2100 rows in 2950 (1J, Shanghai)
| Szygula Kinga (KTW) | OneJeeves | As client INEX Partners reuqests new type of labelling, we need adjustable tempalte for outer package on few items dedicated for that client, as well as labels for pallets. Pallet label must consist of information about items and how many packets are on that one pallet. If pallet is filled with one item, then that pallet label must consist that information. If pallet has several items, label must have information how many package pallet has totally. All different items must be marked to label. What customer highlighted was this SSCC marking. So that every logistic unit must be recognized with this kind serial number. Warehouse must be able to adjust the label for each different order. Outer package labels will always be the same for each item. Please take a look on sample labels attached. Biggest issue is incorporating EAN codes on labels. | Inex Partners are building new logistic center that will be filled with automation. They try to automate most of their receiving goods, that’s why they need our labels to be updated. We need adjustable template for both types of labels, outer package and pallet, to fulfill those requirements. | 4 |  | EL | Yes | IMPLEMENTED | 5804
| Jannicke Holdorf | OneJeeves | There is possibility to change requested Requested Dispatch Date only once (program: order1). Please add possibility to change Requested Dispatch Date without any limitation. It should be control by JVSP parameter. | Sometimes there is necessary to change this date second time and system blocks it. | 3 | MP | MP | Yes | IMPLEMENTED | 5820
| Anders Lautmann | ONE Jeeves | Add UNILEVER to ARIBA (orders) | Just do it :-) | 5 | CS | CS | YES | ON HOLD | 5834 Investigation regarding turnover and number of orders | YES , we are waiting for Unilever.
| Ida Modigh | Current Jeeves | We have decided to reduce the quantity of acquisition methods in Sundsvalls jeeves as a preparation for going over to One Jeeves.To do this we will have to change the acquisition method on some items. I have created a list with 2900 items where this needs to be changed.To do this we will have to change the acquisition method on some items. I have created a list with 2900 items where this needs to be changed.On the list you can see the metod that is current and the one it should be changed into. I have marked the column in yellow that it should be changed to. | It will help us clean up the system in preparation for one jeeves. | 3 | CS | CS | Discus at Pree Study SDL | OPEN | Is it really needed before the Migration to OneJeeves or can this be done while we prepare mapping files for OneJeeves
| Adrian Różański | OneJeeves | Add checkboxes to the list on MO | For reporting purposes employee has to check status on each MO line, 1 to 6 checkboxes. | 4 | JH | JH | Yes | IMPLEMENTED | 5836
| Pascal Aubert | FraJvs001 | Change of Terms and Conditions for all french customers that have been ordering since 01/01/2017 | Apply new french legislation | 5 | EL | EL | Yes | IMPLEMENTED | 5789
| Maelle Fauconnier | FraJvs001 | Import of french Item description Language | Customer satisfaction when reading HL external documents (Order ACK, Del Note, Invoice) | 4 | EL | EL | Yes | IMPLEMENTED | 5801
| Barbara Misiaczek | OneJeeves | Add item number to factory when item is created from the estimator in HUB |  | 5 | JH | JH | Yes | IMPLEMENTED | 5838
| Adrian Różański | OneJeeves | Report for capacity in preparation | To calculate workload on daily basis, data must be gathered from the system which currently is only available to one jeeves support. | 4 | JH | JH |  | REJECTED | Investigation if real time datas are needed (then QV could be used if datas from Day-1 are OK)
| Łukasz Niezgódka | OneJeeves | Create in picking list document in header or in last page information tha will be contained estimated number of pallets and weight on the basis of data product packaging in cardboard and further translated into the pallet | It will help to estimate how big the dispatch will be, how many trucks is needed and so on | 4 |  | JH | YES | IMPLEMENTED | 5920
|  |  | On the list you can see the metod that is current and the one it should be changed into. I have marked the column in yellow that it should be changed to. | [5 empty] | OPEN
| Murzina Evgeniya | Current Jeeves RUS | In Jeeves Prod Rus need tochange Inventory Transaction Report (add column with incoming invoice number) according to correspondence below. We plan to put incoming invoice number in the line for comment: | Information needed for export to excel at later stage | 5 | CS | CS | YES | IMPLEMENTED | OT Feature 5875 16 hrs | YES and asked for status 22/3 !
| Linda Yang(Monica Yi | Current Jeeves (2940,2970,2960) | - Upload bin location list with items in 2960,2970,2940 - Show bin NO. on the picking list in 2960,2970,2940 | No current Bin locations generating ineffecient warehouse handling. Decrease personal mistake. |  |  | AEL |  | OPEN
| Paulina Wróblewska | OneJeeves | Calculate 'Deadline' column based on the creation date and item category like: Standard + 2 days, Modified Standard+ 3 days, Bespoke +5 days | Possibility to prioritize work. To have control whether we meet our deadlines and KPIs. | 4 | JH | JH | YES | IMPLEMENTED | 5828, 5934
| Christer Sahlen | OneJeeves | Default value of Incoterm (Halmstad) for all Swedish customers / Wait for discussion with Gosia and Christer | Part of Receiver pays flow | 4 | MP | MP |  | REJECTED | Gosia put this point on hold
| Basia Misiaczek | OneJeeves | Right-click arrow for Taric Code in Estimator | connected to new replication - feature 5777 from MIO project | 4 | JH | JH | YES | IMPLEMENTED | 5897
| Gemma Watson | OneJeeves | Please add possibility to add sub-brands to assign them to orders. There should be drop down list in order1, tab HL Finance and it should be visible in QV reports. | To keep control and to have more details regarding international brands, for example Coca-Cola | 4 | MP | MP | YES | IMPLEMENTED | 5877
| Indri Lestari | CJ (JKT) | User wants to have big text field in order1, the same way like for example in po | To increase visibility of these notes | 3 | MP | MP | NO | REJECTED
20-02-2017 | Katarzyna Zelwor | OneJeeves | Add EOQ calculation to Estimator | To make possible to prepare IM items in Estimator program | 4 | JH | JH | YES | IMPLEMENTED | 5894
20-02-2017 | Joanna Skiba | OneJeeves | Additional copy of corrective invoice is needed (print and reprint) | Legal demand | 5 | MP | MP | YES | IMPLEMENTED | 5890
2017-02-22 | Tymoteusz Glajcar | One Jeeves | Add operation start and end to MO report |  | 4 | JH | JH |  | OPEN | Betr: (report? MO combined? Julia confirm)
2017-02-22 | Vantina Semenova | Current Jeeves RUS | Change requiested 1 year ago - cannot have incorrect bank name | Bank/Legal requirements (incorrect bank name showing) | 5 | BT | BT | YES | OPEN | OTF 5930, est 4 hours (Kamil estimate) - Betr
2017-02-22 | Adrian Róźański | OneJeeves | Add Prototype frame to XTI | To calculate department workload/capacity I need to have specific data. This checkbox will allow to filter data for prototype workload. | 4 | JH | JH | YES | IMPLEMENTED | 5932
2017-02-24 | Małgorzata Stasierska | OneJeeves | Incoterms for Norway |  | 5 | MP | MP | YES | IMPLEMENTED | 5937
2017-02-28 | Rob Smith | One Jeeves | Improve Kanban flow, multiple instead of single PO row | Save 4 hours weekly in HUB alone | 4 | CS | BT | Investigate more | OPEN | Christer to investigate, PO can not be updated asked UK if we can change flow so that SO update // C
2017-03-03 | Stephen Mepsted | One Jeeves | Delivery date issue on picklist and order. Promised delivery date is taken from order header and not order row | See actual promised delivery date on order row level |  | AEL | SM |  | OPEN | SRX12148: Andreas to investigate with HUB Managers.
03-03-2017 | Magdalena Kruk | OneJeeves | GPI Polish control file | We should have the same structure for all control files. GPI Polish control files has to be adjusted | 5 | KS | KS | YES | IMPLEMENTED | 6001
2017-03-14 | Stephen Mepsted | One Jeeves | Original promised ack date on PO and also able to set manual Date and who confirmed | Dates changes happens a lot, hard to follow up what was original promised | 4 |  | CS |  | OPEN | Christer to talk to Erwan asap. Meeting booked 23/3 !
2017-03-22 | Bartosz Wowra | One Jeeves | Orginal Blueprint field | to keep track if the drawning is changed | 5 | JH | JH |  | OPEN | Check Version handling
2017-03-22 | Bartosz Wowra | One Jeeves | Copy field Blueprint from estimator to item | to keep track if the drawning is changed | 4 | JH | JH | YES | OPEN
2017-03-22 | Adrian Róźański | OneJeeves | Add field Blueprint to Subcotnract PO | to be sure that supplier knows how the final product should look like | 5 | JH | JH | YES | IMPLEMENTED | 6009
2017-03-22 | Bartosz Wowra | One Jeeves | Show document with name and not ID | today the list of documents is not clear, when there is several PDF files on only ID number then user is not sure which document is for which drawning | 4 | JH | JH | YES | OPEN
2017-04-12 | Reto Hunziker | One Jeeves | general ledger report modifications | report is not clear, does not show the figures so he needs te report to be able to monthly close | 4 | BT | Jessica |  | OPEN | OTF
5-5-2017 | Emilia Hermio | OneJeeves | Please to add to “credit note" template fields: - Who created claim - Claim reason And new field (drop down list) to ork program - Internal/External | 1) This document (credit note request) will be more clear 2) Internal correction/credit note to customer is needed | 4 | MP | MP |  | IMPLEMENTED | Done within 6177
17-05-2017 | Adrian Róźański | One Jeeves | Make M.O. checkboxes from HL Orderunique (xti:aa:wxti) possible to mass change on multiple items in “MO to prepare” list. | For reporting purposes employee has to check status on each MO line, 1 to 6 checkboxes. | 4 | AEL | JH | Yes | OPEN
17-05-2017 | Adrian Róźański | One Jeeves | On list M.O. to prepare distinguish for example by bold font, duplicate jeeves codes. | Customer is able to order same jeeves code twice at the same time. If it happens before preparation occurs, double preparation is made. | 3 | AEL | JH | Yes | OPEN
17-05-2017 | Adrian Róźański | OneJeeves | On list M.O. to prepare correct checkbox timestamp to be always filled with Gliwice Factory time zone. Applies to all checkboxes on m.o. to prepare. | Need for time reporting. Currently wrong time -2 hours | 4 | JH | JH | Yes | IMPLEMENTED | 6162
17-05-2017 | Adrian Róźański | One Jeeves | Business service officer has to double check “prototype” checkbox on oder1 and xti M.O.– requirement is to replicate value from oh.q_hl_prototype to ti.q_hl_prototype when creating M.O. | Need for time reporting. Currently we have problems reporting preparation capacity in production preparation | 4 | JH | JH | Yes | IMPLEMENTED | 6316
17-05-2017 | Adrian Róźański | OneJeeves | Create a possibility to copy (similar to copy table) selected rows/entire table in table format for mail/word documents + 1st top row.Currently there is only a string of spaces, tabs and letters/digits which changes appearance when mail is wider/more narrow in browser – makes it unreadable. | Business service sends hundreds of mails daily, informing departments and clients about m.o./item status which needs to copy essential info from system. To keep visual appearance business service makes screen shot which denies ability to copy data quickly from mail. | 2 | JH | JH | NO | REJECTED | Not possible
25-05-2017 | Rosol Joanna | One Jeeves | Update article search of inventory location sample (ars.lagstalle ) at the moment we have only main warehouse. | Samples availability is crucial in the offering process.In case of injection molded technology samples production on request is not profitable due to high base cost start. The factory needs to stock as many samples as possible to enable KAMs to build prototypes, test them with customer’s products and give the customer touch and feel of the solution, which is offered. Another very crucial success factor in offering process is speed to market. Quick information about samples availability could improve our offering process significantly. Main benefits of introducing the possibility to filter “samples inventory” on HL Net:Sales units would get quick information about what samples are available and can decide by themselves what items suit customer needs bestSales units could place the order immediately and get samples asapGLI factory would not waste time on ping pong emails informing about samples availability and could concentrate on other tasksGLI factory would not waste time on ping pong emails informing about samples availability and could concentrate on other tasks | 4 |  | CS |  | OPEN | ASK XLENT for offer if XAvier agree // CS
29-05-2017 | Malgorzata Stasierska | One Jeeves | Pick list restrictions with advanced payment - Add warning when using advanced payment and exclude orders without paid invoices on picking list | A lot of orders gets prepared today without invoice payed. To avoid operators to place uneccassary work and have goods batched up without being able to be dispatched we want to have a warning displayed when printing pricking list for unpaid invoice if printing for 1 order. If batch printing "picklist to date" we want the report to exclude unpaid orders | 4 | Andreas/Jessica | AEL | YES | IN PROGRESS | OTF:6202 |  | https://hldisplay.sharepoint.com/sites/itdocumentationrepository/_layouts/15/WopiFrame.aspx?sourcedoc=%7B84DF8D2B-99EF-4BFE-90F5-B8E633CD53C6%7D&file=XXXX%20-%20Pick%20list%20restrictions%20with%20advanced%20payment.docx&action=default
29-05-2017 | Jeeves Support | One Jeeves | Shortage report in Xarla now shows shortage based on full order quantity instead of remaining order quantity. | Shortage report should display actual shortage. With larger orders or any part-delivery shortage is incorrect because parts of the order have been dispatched and invoiced. | 3 | Andreas | AEL |  | REJECTED | Andreas to investigate more. Agreed with Jolanta that the current report is not sufficient for warehouse use. A bigger discussion should be taken with key HUB users. Could eWMS or EazyStock provide be used for this or should we change the current logic of the reports? |  | https://hldisplay.sharepoint.com/sites/itdocumentationrepository/_layouts/15/WopiFrame.aspx?sourcedoc=%7BDF4C6541-1B79-48B6-9BD5-E771193865AE%7D&file=XXXX%20-%20Shortage%20report%20remaining%20quantity%20comparison.docx&action=default
24-05-2017 | Bożena Paszkowska | One Jeeves | files in GDPDU_EXPORT. The file is mandatory element of reporting to the Tax Office about VAT. Right now it’s impossible to generate a file in correction version. | legal purposes | 4 | Beki / Jessica | BETR |  | OPEN
5-6-2017 | Marcin Pianka | OneJeeves | Price unit factor (orp.fsgprisper) should be visible in the invoice (1190) | Some items have price for 100 pices and there are errors in rounding | 5 | MP | MP | Yes | IMPLEMENTED | More investigation needed
5-6-2017 | Marcin Pianka | One Jeeves | Button "print credit note request" should be local. | Currently in 1190 and 2400 we have old values from Nordic | 4 | MP | MP | YES | OPEN | 6171
8-6-2017 | Marcin Pianka | OneJeeves | Additional texst field is missing on estimator's row - it should be similar to text between order rows in order1 | External text on quotation row is very narrow | 4 | MP | MP |  | REJECTED | Rejected, 6187 will extend existing field instead adding a new one
12-06-2017 | Julia Homik | OneJeeves | Possibility to sell KIT item from the facotry to hub, and ito 'unpack' in hub into several items. | It take a lot of time to prepare all the items and them process them in production process, JGP and so on | 4 | JH | JH | NO | REJECTED
13-6-2017 | Marcin Pianka | Current Jeeves | Please create collective invoice (copy of EN COLL INV from 2950) | User's efficiency, save costs | 5 | MP | MP | YES | IMPLEMENTED | 6197
16-6-2017 | Krzysztof Mizielski | One Jeeves | Optimize packing report in OLHUCORL | Rationalizing, Improving competetivness? |  | AEL | AEL |  | OPEN | More investigation needed with Krzysztof
22-06-2017 | Ewa Stępińska | HLNet | Add Quotations to Article Search | My idea is to share quotes we make for one Sales Unit with other Sales Units. The aim is to give Sales Unit ability to find similar quote that has been done before and estimate to the customer. So generally, yes, I would like all valid quotes to be visible on hl net, but I think it would be good to have also an option not to show it (by specific status or field). | 4 | JH | JH |  | OPEN | Julia to make a more detailed invetigation.
05/07/2017 | Maja Ostrowska, Małgorzata Stasierska | OneJeeves | Additional parameter for mass calculation to keep previous qty | In order to use mass calculation in Hub. Today it is not possible to use it because the calculation in done based on the qty per pallet | 5 | JH | JH | YES | IMPLEMENTED | 6257
12/07/2017 | Bartosz Wowra | One Jeeves | Add Blueprint to PO template | to be sure that supplier knows how the final product should look like | 4 | JH | JH |  | OPEN | Wait for Erwan to discus
24/07/2017 | Paulina Motyl -> Tomasz Wieszyński | One Jeeves | Add checboxes 'Manual Setup time' and 'Manual Qty Per hour' to operation | Usually operations values are calculated according to excel file and rules in the facotry. Sometimes due to material that is used the operation time is not standard and was filled in manually by preparation engineers. Users wants to mark operation where the values are not standard to not overwrite. Today when the operations time is not correct then the price is not right and the delivery date to customer may be wrong. These checkobxes are to mark operations that may look strange but in fact values are correct and no one should ovewrite them. | 4 | AEL | JH |  | OPEN | Julia to ask Gliwici FActory for more info ..
25/07/2017 | Justyna Bagniewska | One Jeeves | Automatic booking of subcontracting MO |  | 4 | JH | JH |  | OPEN | MO not booked today ? Julia to check ..
26/07/2017 | Kinga Szyguła | One Jeeves | Adjustments to report 'MO Added Value' 1. For now there is only item spec. USers would like to see item desc too (as on the old report) 2. Add bin inventory balance to the report 3. Group rows for one item with several bins. | In Gliwice hub they stopped to use the report due to these three points. They use the old report because they have more information in there | 4 | AEL | JH |  | OPEN | WHY not using Aotodo Picking list. Another MO report change is made in OTF: 6809
01/08/2017 | Sarah Keller | One Jeeves | Planning List in ofhestimator | They would like to have the planning list in the offer. It is faster to have it there than to go to the item firstly. | 4 | JH | JH | YES | OPEN | 6361
08/08/2017 | Bożena Paszkowska | One Jeeves | It is necessary to include in Order Confirmation to customers who have VAT tax/ type set as ”S-inside EC goods (except Poland)” following information: | There are tax requirement to use 0% VAT. These two functionalities will allow us to apply a 0% VAT rate and avoid paying 23% VAT rate to Tax Office. Both of these funcionalities have huge impact on the Group liquidity. | 5 | JH | JH | YES | IN PROGRESS | 6335
22/05/2017 | Boguslaw Kuczynski | OneJeeves | New tool for dispatch scanning process, Centiro | 1 FTE can be reduced if proper solution is implemented according to Boguslaw. | 5 | AEL | AEL | NO | REJECTED | Request not agreed from management, too costly. Excel based solution suggestion from Boguslaw. How is other HUB's working?
09/06/2017 | Boguslaw Kuczynski | One Jeeves | New pop up window or fee row on right site of order to eliminate not released fees Only for Polish Sales company ! | Lot of extra administrational work and less money to HL due to missed fee to customer | 3 | AEL | AEL |  | OPEN | Waiting for confirmation from Marcin P about what kind of indication that can be used to alert about fees in the system. We need more facts about what kind of fees we talk about for Polen Company.
20/06/2017 | Boguslaw Kuczynski | One Jeeves | Query for logistics analyze of open orders |  | 3 | AEL | AEL | YES | OPEN | Country of delivery missing, change needed to query. Responsible user back in W.34, waiting for his info. Bogus to update me FEATURE = 6203
05/04/2017 | Boguslaw Kuczynski | One Jeeves | Journal closing option | Not sending item with too large qty | 3 | AEL | AEL |  | OPEN | Waiting for Tomek's reply. Reject if no easy fix is possible since this sounds more process related. Check what has been prepared for Area West then look if more "DEV" Needed
10/05/2017 | Boguslaw Kuczynski | OneJeeves | Scanning for inbound delivery. No manual delivery should be possible. Only scanning and confirming bin location. | This would decrease risk of wrong inbound delivery. Automatic process with scanning, entering bin location and confirming. | 3 | AEL | AEL | NO | REJECTED | Barcodes needed on all bin locations. Reject for now
28/03/2017 | Boguslaw Kuczynski | One Jeeves | Already confirmed historic locations should be identified in the system | Currently they are double working by constantly confirming all historic locations. We should differentiate already confirmed historic locations from locations TO BE confirmed. | 3 | AEL | AEL |  | OPEN | More Investigation needed and AEL to aks for example.
15/03/2017 | Boguslaw Kuczynski | One Jeeves | Night put away and replenishment process - Replenish Pick location(low) from bulk location (high) based on current orders | Big potential cost savings | 5 | AEL | AEL |  | OPEN | eWMS? Bogus to send current replenishment functionality in jeeves which isn't enough. We should then schedule a meeting with logistics managers/WH managers
02/05/2017 | Boguslaw Kuczynski | One Jeeves | Comparison of newly added goods and picking list | Virtually sending goods but physically not. Problem is that inbound can work and put in goods while pickers don't see on picking list. 50 % of claims used to be because of not sending complete order | 4 | AEL | AEL |  | OPEN | Christer, Help? It happen because for example we are printing Picking for order with status- Part delivery allowed (11:00) and after that (11:10) our Inbound dep is booking item needed for this order, later Order picker while closing process is taking all rows and between them there is a ‘new line’- fully booked. I know that this we should to check but for ‘big’ orders it will take some time. 23/8: Take a meeting on arrival Entry and explain use of that and that you then can see that goods are in WH but not on bin./
20/06/2017 | Boguslaw Kuczynski | One Jeeves | Query x2 |  | 3 | AEL | AEL | YES but need to be disscus with Christer | IN PROGRESS | Wait for update from Responsible user back in W.34, waiting for his info. Bogus to update me. Same as open order request???
15/08/2017 | Boguslaw Kuczynski | OneJeeves | Is it possible to add new field on ORK where we can chose one of two options for each claim- Approved or NOT Approved. Is it possible to add new field on ORK where we can chose one of two options for each claim- Approved or NOT Approved (I can’t find this @ on my Outlook) |  | 3 | MP | AEL | YES | IMPLEMENTED | Done within 6177 project
| Boguslaw Kuczynski | OneJeeves | Picking route. Implement pick list sorting on bin locations based on picking route provided by Boguslaw | It would | 5 | AEL | AEL |  | REJECTED | Email with explenation and image exist from Bogus to be used in feature. Add logistics Managers to discussion. Could be benificial to add in other HUBs. eWMS?
21-8-2017 | Anette Karlson | One Jeeves | Button needed to cancel sending email with invoice | To have possibility to fix an error | 4 | MP | MP | YES | OPEN | 6310
22/08/2017 | Damian Glajcar | One Jeeves | XTI program: Delivdate SO – this is the button confirming that the order line is planned. However, there is no date showing WHEN it was done. It is crucial to develop a new field with date and time of order row planning. | Without this field we are not able to report any proper KPI planning time. | 4 | AEL | JH | YES | IMPLEMENTED | 6385
22/08/2017 | Jannicke Holdorf | One Jeeves | Already booked rows against incoming PO should be marked yellow in program order1. Currently users have to go to the planning list | To save user's time and increase overview. | 4 | MP | MP | Wait for MP | OPEN | 6363 / mail sent to Erwan if makes sense 01/03/2018: Marcin to check if the request is still valid
04/09/2017 | Boguslaw Kuczynski | One Jeeves | XLS file connected with a RF scanner to proceed with wireless dispatching of all parcels | Not Given | 5 | EL | CS |  | OPEN | project proposal? Waiting for management decision
8/09/2017 | Anette Karlsson | One Jeeves | We receive orders from circle K into Jeeves by Ariba system. These orders do not get the box "earlier dispatch allowed" ticked as default. We ant it to be ticked as def. | Misses at CS causes later problems in flow | 5 | MP | CS | YES | IMPLEMENTED | 6573
14/09/2017 | Ida Modigh | Current Jeeves | We have a Crystal Report in Sundsvall Jeeves. It's in program xarla = Future Disptaches. In the report we can bring up orders dispatching between specific dates. When we created the report we did not use the PO ststus "goods in transit", now we have strated using this status. The problem now is that orders set in this status does not show on the report. We would like that orders set in status "goods in transit" also shows on the report. | We use this report both to plan dispatches in (China) and also check delivery follow up of our orders. SO its very important statisrics and anylses. | 4 | CS | CS | NO | REJECTED | 01/03: soon SDL will join 1J, no new development should be implemented in CJ
10/04/2017 | Birgitta Möllerskog | ONE Jeeves | From Circle K we receive orders through their system Ariba System are connected to each other through our customer number and their station numbers. The problem that we know have appeared is when they need to have delievry to unemployed statios but to another dekiveryadress for example a local salesoffice. IN Ariba they write this information ( see enclosed ) which do not follow over to Jeeves. |  | 4 | CS | CS |  | OPEN | 01/03: review needed with EDI project. meeting on 8/03/18
20/10/2017 | Boguslaw Kuczynski | One Jeeves | Pop-up in Olhucorl if 'txt on picking list'. Should be displayed when entering SO | Information is not visible until picking list has been printed. Ineffective. | 4 | EL/AEL | AEL | ? | IN PROGRESS | 6584 – Popup window for picking list text
6/11/2017 | Emilia Harmio | One Jeeves | During processing order form Ariba system should automatoically fill field "sales type" using value "customer system". | To save time and to avoid mistakes. | 4 | MP | MP | YES | IMPLEMENTED | 6573
16/10/2017 | Katarzyna Kielar | One Jeeves | Add BC unit and BC start fields in BOM | Not given, reason rationalizaing | 4 | AEL | AEL | YES | IN PROGRESS | Values is already set in system if item is "Purchase to order point" 6879 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/WopiFrame.aspx?sourcedoc=%7BBA9F0E11-85A7-4939-A419-2C6D692500A9%7D&file=HL%20IT%20Change%20Request%20Form%20-%20kaki%2016.10.17.docx&action=default
7/11/2017 | Sarah Keller | One Jeeves | Advance payment templates | Legal demand | 5 | MP | MP | YES | IMPLEMENTED | 6580
17/11/2017 | Jessica Steffen | One Jeeves | possiblity of corect base cost - new fileds in vfaktst | corect margin in QV | 5 | KL | KL | YES | IMPLEMENTED | 6601 |  | https://hldisplay.sharepoint.com/sites/itdocumentationrepository/Delade%20dokument/Development%20Documentation/6601%20-%20Base%20cost%20correction%20field%20in%20vfaktst.docx?d=wbb683d2d90d54e4ba5bd32587a620062&csf=1&e=7b302ff3b26a4b1d8bd8c74bbee21d19
05/12/2017 | Imee Santos | One Jeeves | manual invoice template with VAT | legal demans | 5 | KL | KL | YES | IMPLEMENTED | 6629 |  | https://hldisplay.sharepoint.com/sites/itdocumentationrepository/Delade%20dokument/Development%20Documentation/6629%20-%20Manual%20invoice%20template%20with%20VAT%20for%203901.docx?d=we4c7d16e69fb4d61939b42cceb1bd72b&csf=1&e=329fb7d52cc14a9888e93179ea12b833
24/11/2017 | Alicja Mamińska | One Jeeves | changes in Polish control file for VAT | legal demand | 5 | KL | KL | YES | IMPLEMENTED | 6611 |  | https://hldisplay.sharepoint.com/sites/itdocumentationrepository/Delade%20dokument/Development%20Documentation/6611%20-%20Polish%20control%20file%20-%20VAT%20structure%20-%20changes%20from%2001.01.2018.docx?d=w6433d38c484145928da695848077c155&csf=1&e=dd93627b11b1472089656a0c41b3410a
05/12/2017 | Jessica Steffen | One Jeeves | auto import of files with suppier invoices into Jeeves- e-approval | unification and time saving | 4 | KL | KL | YES | IN PROGRESS | 6631 |  | https://hldisplay.sharepoint.com/sites/itdocumentationrepository/Delade%20dokument/Development%20Documentation/6631%20-%20e-approval%20-%20auto%20import%20of%20files%20for%201200,1300,1210.docx?d=w6a3bb5c4f17748b0b8155b21a98a61d5&csf=1&e=ad5baac5873e400a9496a4f1c4d10ac5
29/12/2017 | Katarzyna Zelwor | One Jeeves | LT calculation in Order1 |  |  | AEL | AEL |  | OPEN | Marcin sent email to Katarzyna Zelwor, we are waiting for the answer. Andreas should take a lead
09-01-2018 | Małgorzata Stasierska | One Jeeves | Email to procurement/added value department when sales order (or just row) is cancelled | To secure that proper actions in HUB are taken once the order/order row is cancel in aim to avoid over stock. | 5 | MP | MP | YES | IN PROGRESS | 6694 // Mail to Erwan nad Paweł Nowak if we can use this functionality also in the rest of companies
09-01-2018 | Christer Sahlen | Current Jeeves | additonal function to remove old records automatically from MUP and load new records | improve process on ulpoad new prices familiar for users | 4 | PANO | PANO | YES | IN PROGRESS | 6693
10-01-2018 | Małgorzata Stasierska | One Jeeves | Addtional label when Good lable row 2 is filled | safe time to not create separetly extra label | 5 | PANO | PANO | YES | IMPLEMENTED | 6709 Bartender resolution was chosen
12-1-2018 | Emilia Hermio | One Jeeves | Information about category should be moved to field "text between order rows" | To adjust functionality to ohre HUBs | 4 | MP | MP | YES | IMPLEMENTED | 6700
15-1-2018 | Pawel Nowak | One Jeeves | Investiagtion of flow Collective invoice and extend for bigger invoices | Secure flow invoices in portal Tieto, to avoid problem with stuck invoices or mismatch rows between invoices | 5 | PANO | PANO | Yes | IN PROGRESS | 6708
16-1-2018 | Andrea Sanda | One Jeeves | Import of data for Austrian customer | 4600 customers to be updated - to save users time | 5 | MP | MP | YES | IMPLEMENTED | 6702.
18-1-2018 | Stephen M | ONE Jeeves | Change of tick box when CR Picklist is just partly booked | Need to untick a lot when fully booked | 4 | CS | CS | YES | OPEN
17-01-2018 | Małgorzata Stasierska | One Jeeves | Add Guarant Descr, Earlier disp ok, FIxed deliverydate field on Picking list pl | Being able to inform WH of important orders which can be sent 1 day earlier, helps resource and transport planning in WH (saves costs). | 5 | PANO | PANO | YES | IMPLEMENTED | 6707
24-01-2018 | Tomi Yrjönen | One Jeeves | Trade Policy / Broken Box Fee and Std Handling Costs visible on e-invoice (should not appear on invoice) | Items which are not visible on invoice(trade policy flow) are showing in Tieto portal like normal itmes | 5 | PANO | PANO | YES | IMPLEMENTED | 6724
24-1-2018 | Ewa Moskal (Stępińska) | One Jeeves | 1) Need to block possibility to create item without logistic data 2) factory should have information about answer 3) Adding to main price list has to be improved | It is necessary to allow users to create items in HUB | 5 | MP | MP | YES | IN PROGRESS | 6713 - Mail sent to Xavier - waiting for response
29-1-2018 | Imee Santos | One Jeeves | Credit note template is needed in company 3901 | Legal demand | 5 | MP | MP | YES | IMPLEMENTED | 6735
02-02-2018 | Sarah Keller | One Jeeves | Reprint Delivery note from olhfu after invoice | Customer request after invoiced order,company 2400 doesnt have that posibility | 4 | PANO | PANO | YES | IMPLEMENTED | 6787 created
12-02-2018 | Jolanta Basiaga | One Jeeves | To convert supplier LT from calendar to working days replicating item from Factory to local companies | We need to convert calendar days to working days when we migrate new item from Master data to local company system. Conversion rate which should be applied is 5/7 i.e. LT in factory=18 should be converted to LT=18/7*5=12,8~13 in the hub | 5 | PANO | PANO | Investigate | OPEN
12-02-2018 | B. Kuczynski | One Jeeves | Additonal changes in stock taking journal | Need for audit request for 1810 | 5 | PANO | PANO | YES | IMPLEMENTED | F6788 created
15-2-2018 | Imee Santos | One Jeeves | Additional templates (sales without VAT) | Legal demand | 5 | MP | MP | YES | IMPLEMENTED | 6767
15.02.2018 | Kinga Lesniewska/ Julia Homik | One Jeeves | add log of cahnges on TF fileds | to make analises possible | 4 | KL | KL | YES | OPEN
15.02.2018 | Kinga Leśniewska | One Jeeves | design in programs conected with journals | a lot of fileds are missing in journals programs in HL standard tabs - due to that fact users are not able analise data by themselves | 4 | KL | KL | YES | IN PROGRESS | 6786
15.02.2018 | Susann Radestrom | Current Jeeves | auto update of currency rate from web to Jeeves | easier to operate and control | 4 | KL | KL | YES | IN PROGRESS | 6821
21.2.2018 | Danuta Bonior | One Jeeves | Additional information on PL and PL-EN footers regarding environmental rules. | Legal demand | 5 | MP | MP | YES | IMPLEMENTED | 6797
21.2.2018 | Marcin Pianka | One Jeeves | Proper margin calculation. Two fields in estimator were prepared only for proper calculation of added value items. Purpose is to have proper vlue also for estimated items | There should be proper margin for estimated items - lots of complains from users | 5 | MP | MP | YES | IN PROGRESS | 6798
22.2.2018 | Marcin Pianka | One Jeeves | Margin in order1 - to discuss | Currently maring in order1 is not correct. It is also impossible to have the same margin like in invoice due to our pricing model | 4 | MP | MP | NO | REJECTED | 01/03/18: this should be consider with the new BC model project
23.02.2018 | Pawel Nowak | One Jeeves | Improve Carrier code transfer from PoD on order | To avoid mistake in date on order and safe time during creation order to other countries | 5 | Pano | Pano | wait for Erwan | IN PROGRESS | 6802
10.01.2018 | Kinga Szygula | One Jeeves | MO report change | To avoid packing problems | 4 | AEL | KS | YES | OPEN | 6809
19.02.2018 | Boguslaw Kuczynski | One Jeeves | Proforma invoice in 1810 adjustment to brutto weight | Currently Brutto is count based on formula 1.2xqtyxweight, it should be taken form Specified Gross weight like CPI | 5 | PANO | PANO | YES | IN PROGRESS | 6822 created
15.02.2018 | Boguslaw Kuczynski | One Jeeves | Additonal field Picker name on close order freight | KPI for packing goods, productivity on packing | 4 | PANO | PANO | YES | IN PROGRESS | 6823
27.02.2018 | Boguslaw Kuczynski | One Jeeves | Create Proforma for Aland Islands in 1810 | Additional area for existed Proforma | 5 | PANO | PANO | YES | IN PROGRESS | 6824
28.2.2018 | Marcin Pianka | One Jeeves | Export from QR to Word | Layout of quotation report after export to Word format is not ok. We found way to fix it. Exporting to Word is kind of workarounf (estimator has not so many option of adjusting layout like CRM) | 4 | MP | MP | YES | IN PROGRESS | 6811
28.2.2018 | Anette Karlson | One Jeeves | Price list details | There should be information about sales quantity in list mode (all item details will be helpful during creation of price list - MP) and base costs | 4 | MP | MP | YES | IMPLEMENTED | 6813
28.2.2018 | Katarzyna Zelwor | One Jeeves | Sales assistant should appear on orders during drop shipment process | To improve customer cooperation (in factory we have persons responsible for key customers) | 4 | MP | MP | YES | IN PROGRESS | 6814
28.2.2018 | Sarah Keller | One Jeeves | Add logo "20 years of HL" | To build mark stronger | 4 | MP | MP | YES | IMPLEMENTED | 6812 Mail to Sarah 1-3-2018
28.02.2018 | Boguslaw Kuczynski | One Jeeves | Change mark on Pickig list for Early dispatch "E" instead Y | "Y" is already cover different field Fixed delivery date | 4 | PANO | PANO | ? | OPEN
2018-11-17 | Kinga Szygula | One Jeeves | Subcontracting color coding in planning list | Raised by Sales Units. To be a clearar of when it is subcontracting and who then to contact at the HUB. | 4 | AEL | AEL | ? | OPEN | Emilia, Gosia and Sarah keller raised this. Functionality should be similar to marked book MO. which is yellow.
2017-10-18 | Patrycja Slusarek | One Jeeves | Pro Forma invoice for Gliwice Factory | This is for customs purposes and they have previously created manual pro forma invoice. They are also requesting additional functionality in the OLHUCORL | 5 | PN | AEL | YES | IN PROGRESS | F6839
2017-10-16 | Katarzyna Kielar | One Jeeves | Base Cost Unit and Base cost start of compoenents visible in BOM ( it is just adding 2 columns to present view) | To avoid the need of clicking into the item program. | 4 | AEL | AEL | NO | REJECTED | 6857 2018-03-20:Rejected. Will not be valid if we do the modifications in ARPROD suggested in next RFQ.
2017-05-31 | Michal Los | One Jeeves | Create new tab in item program | They think they can rationalize their work by combining information from several views. HL Inventory, HL Properties, item balances. | 4 | AEL | AEL | ? | OPEN | Should we create a new tab? Second part of RFC is unclear, need to book meeting with requestor. If no new TAB. They would like to have a view with BOM and Operations. 15/03: meeting to discuss Ewa will show ARPROD to her team. Together with this a development should be done to add 3 columns in the BOM list, BCU, BCS and purchase price.
26 lipca 2017 | Katarzyna Zelwor | One Jeeves | Lead time in order row calculated for the proper quantity - request for change sent, discussed internally in IT. |  | 3 | AEL | AEL | to be discussed with factory | OPEN | 15/03: to be invesitgated
2-3-2018 | Jannicke Holdopf Emilia Hermio | One Jeeves | Field "Sales type" should be mandatory in ordofh | This is mandatory in order1, but not during creation orders based on offers. this is very important statistic information. It is just adding rule to program q_oblfieldh | 4 | MP | MP | YES | IN PROGRESS | 6841
2-3-2018 | Vivian Li | CJ Jakarta | "Sales person" in program fh | This is needed to have statistics to analyze invoices by KAMs | 4 | MP | MP | YES | IN PROGRESS | 6858
07/03/2018 | Kinga Lesniewska / Jessica Steffen | One Jeeves | block possiblity to add new records localy in posting templates programs | Posting templates are global and should not be modified localy | 5 | KL | KL | YES | OPEN
08-03-2018 | West SU | One Jeeves | Page break in quotation report. There should be checkbox to have possibility to put page break - to have next option/category on separate page | To improve control on report. Currently there is no such possibility | 4 | MP | MP | YES | IN PROGRESS | 6837
08-03-2018 | West SU | One Jeeves | There should be warning message "please choose proper localization" during drop shipment order creation | To increase control | 3 | MP | MP | On hold | ON HOLD
08-03-2018 | West SU | One Jeeves | Field "order specific text" needs to be created in estimator to have possibility to transfer information from offer to picking list row | Needed to have additional information for added value department or other information for warehouse which are connected only with special row | 4 | MP | MP | YES | IN PROGRESS | 6830
08-03-2018 | West SU | One Jeeves | Pop up message when user is trying to put non-working day in order1 as dispatch or delivery date | To increase control | 3 | MP | MP | NO | REJECTED
24-01-2018 | Kay Phillips | OneJeeves | Item description textbox should be increased in Item Program | Crucial part of the item description is not visible without moving the cursor inside the textbox. At least in the ITEM program the complete item description should be possible to be seen to reduce work and improve overview in the program | 4 | AEL | AEL | YES | OPEN | 6853
07-03-2018 | Katarzyna Zelwor | OneJeeves | They want to have Created by user automatically replicated to supervisor | To reduce manual work of adding field information | 3 | AEL | AEL | YES | OPEN | 9/3: Discussion on-going with Katarzyna about how they can work instead so we use field for what they are meant for. 12/3: Agreed that a created by column in Plan List would be enough
12-03-2018 | Antoine Raffin | One Jeeves | Currently, the field Notes in Factories contain technical information that can be usefull for Purchasign dpt. This field is right now local (factories info are not replicated) | Purpose is to get these technical informations to Sales company (possibility to replicate local field ar.edit from 1190/7110 to 1600 into an other field than ar.edit) | 3 | EL | EL | On hold | IN PROGRESS | 10/04 - Test from ErLa in Test5: 1/ Creation of item in Master 2/ Add comments to the field "Notes" in company 1190 3/ These notes informations from 1190 were not replicated to 1600 or 1810 MP: Field "Notes" should be filled in MD. Then it will be replicated into local companies. User in companies are allowed to adjust it if it is needed.
02/03/2018 | Malgorzta Stasierska | One Jeeves | Automtic change the Dispatch method in order1 program according to the number of rows in one order. | t the moment this needs to be done manually from customer service. This is a) bad as it is one point more they need to think about, b) takes some additional time in entering-process and c) causes troubles in HUB when customer service forget to change the dispatch method (which happens often). If we implement this feature Customer Service and Hub will be more efficient. | 4 | Pano | Pano | YES | OPEN | F6861
8/3/2018 | Tinne Adams | One Jeeves | Sorting quantity when we tiering in estimator | To have proper overview in quotation report. Currently it looks ok only when on row level we have lowest quantity. | 4 | MP | MP | YES | OPEN | 6868
13/03/2018 | Jolanda de Vis | One Jeeves | Possibility to overwrite datas from factory in case of Drop Shipment | Extend feature 6604 to allow user to change date on header, to safe time,not do this row by row | 4 | erla | pano | YES | OPEN | F6859 status Onhold
13/03/2018 | Boguslaw Kuczynski | One Jeeves | Additonal column in report BIN replanishemnt | To show booked qty per bin, to increase efficiency of stock tacking, flow of goods in daily work | 4 | pano | pano | YES | OPEN | F6862 created
14/03/2018 | Lukasz Niezgodka | One Jeeves | additional field with packer in “Close order freight etc.” node in ffhlevp program | The purpose of this feature is create new KPI’s for pickers and control performance. | 5 | pano | pano | YES | OPEN | F6860 created
07/03/2018 | Boguslaw Kuczynski | OneJeeves | WMS - Increase Scanner functionality | 2 imporvements : - Get a confirmation message when the user press the button "Confirm delivery" - Review sorting options while making the receive delivery (review the way that default location is displayed and the way existing bins is displayed) | 4 | ErLa | ErLa | to be investigated | OPEN | Erwan to discuss with other HUB using this functionality (1600)
15/03/2018 | Area West Sales(Tinne Adams) | OneJeeves | Connection between customer offer and added value quotation. They want to have an added value item to show the work and the cost. And the added value dpt. Should be able to easily find this in the estimator | Less navigation in Jeeves Easier connection added value quotation. No connetion exists today | 4 | MP | AEL |  | OPEN | Investigate exact requirement before creating feature. 2018-03-28: Laurence to investigate France needs. Business to decide on working flow that suits both. Then look if development/education is needed.
2017 | Olivier Pedroncini | OneJeeves | Possiblity to send payment teminders by mail directly from Jeeves | simplification of the proces, time saving, cost cutting ( no paper vertion) | 4 | KL | KL | YES - agreed in West project | IN PROGRESS | 6849 (easy Send)
16/03/2018 | Anna Gancarz/West fiance team | OneJeeves | possiblity to send invoice by mail directly from Jeeves | simplification of the proces, time saving, cost cutting ( no paper vertion) | 5 | Kl | KL | YES - disscused on CAB 15/03 | IN PROGRESS | 6851 ( Easy send)
20/03/2018 | Aurelie Picou | OneJeeves | Removal of required purchase in HL Planning list | This line wasn't used to be in their old jeeves and is giving them a bad overview. They currently manually remove these rows. | 4 | PN | AEL | YES | OPEN
19/03/2018 | William Elis | OneJeeves | Make visible field HLBuyer in xarla from supplier level | Currently the standard report provides all requisition and there is no option to sort this list by buyer, so each buyer receives a copy of the list and has to search through the list for the items that they need to order manually. | 4 | pano | pano | YES | OPEN | 6886 created
21/03/2018 | Maja Ostrowska | OneJeeves | Stock protection in 1810 | SUs provides forecasts each month per item. HUB respect forecasted quantity and order goods from suppliers. Total forecasyed quantity should be available beggining of each month. But stock/demands forecasted by each Su is not protected and SUs can always place the order for quantity which exceed forecasted by that SU quantity of particular item. And as well SU which does not provide forecasts can ”steal” qty forecasted by other SUs. Both SU and HUB need to have the solution which will protect stock per SU per items. | 5 | ERLA | PANO | Project Poposal | OPEN | 29/03: Pawel to talk to Maja regarding this
21/03/2018 | Maja Ostrowska | OneJeeves | Manual LT in HUB 1810 | LT has huge impact on stock level, is one of the most important/significant driver. LT define booking horizon for each items. There is group of items which stock management works differently than by standard requsition and we would like to have possibility to have shorter booking horizon what is possible only reducing LT in the system. | 5 | PANO | PANO | to be discussed during the meeting with Sales Units, Hub and Factory | OPEN
21/03/2018 | Maja Ostrowska | OneJeeves | Unblocking sales order only by warehouse team after Picing list was printed in 1810 | Request from 1810, at the moment sales support receive warnning or blocking order and warehouse just email. They wish decide if unlock order is avaible from their perspective not sales support | 4 | pano | pano | to be confirmed with Maja | OPEN
23/03/2018 | Jolanda de Vis | One Jeeves | Functionality connected with field "sales type" in order1 | There should be additional functionality depending on sales type, for example price should be = 0 when type = "factory replacement" | 4 | MP | MP | NO | REJECTED
23/03/2018 | Paweł Nowak | 1j-CDB-CJ | Correction of synchronization CDB with Jeeves | Improve of functionality and transfer items ,safe time and efficieny of IT, sales units and production | 5 | Pano | Pano | YES | IMPLEMENTED | F6885
27/3/2018 | Marcin Pianka | 1J | Discounts in tiering | Discounts from tiering (estimator) are not properly displayed and transfered into order. | 5 | MP | MP | YES | IMPLEMENTED | 6872
27/03/2018 | Markus Reiterer | 1J | reminder letters for PL market in 1810 | at the moment reminders to customers are handled manualy in excel/world - for time saving and bettre control it would be bettre to use Jeeves standard function for this | 4 | KL | KL | YES | OPEN
28/03/2018 | Marcin Nowicki | One Jeeves | Upload of new transport days on Schenker for Norway | Properly data and transport time to customer | 5 | PANO | PANO | YES | IMPLEMENTED | 6883 created
28/03/2018 | Marcin Nowicki | One Jeeves | Change rules during the place orders by Norway with two days delay | To save cost of transport by Schenker to Norway and increase quality of shipments - quite urgent | 5 | PANO | PANO | YES | IMPLEMENTED | 6884 created
28-3-2018 | 1600 Sales SU | 1J | Default text for DS is missing on row level | To save time - such text is on row level (when type of DS) but many time there are mix types and such text should be place on row level | 4 | MP | MP | YES | ON HOLD | Request put on hold due to back to Excel in Area West
29-03-2018
2-4-2018 | O. Pedroncini | 1J | Information about advance payment in the footer of invoice as summary, instead of row | To have proper information and make view clear for customers | 4 | MP | MP |  | IMPLEMENTED | 6901
5-4-2018 | Laurence Lakafa | 1J | Taric code and country of origin in advance payment template | Legal demand - necessary for sales outside EU | 5 | MP | MP | YES | OPEN | 6896
05-04-2018 | Laurence Lakafia Arnaud Pichonnière | 1J | Post closing sales field 1/ Not on correct Tab in order 1 (should be moved to HL Entry 2/ To be displayed on olhucorl + fr picking list template | Information needed to be transfered to Warehouse staff to avoid sending goods that should not suring end of month period | 4 | PN | EL | YES and On Hold ;) | OPEN | 6887 12/04: point 2 sounds resonable and can be implemented. Point 1 to be discussed with Marcin P during next CAB meeting
09/04/2018 | Barbro Johansson | 1J | Add Product Group field to Item program | to make it easier for users to work with new product structure and current classifaction | 4 |  | JH | YES | OPEN
09/04/2018 | Barbro Johansson | 1J | Change the name of Product Number to Product ID | to have the same name of fiedls in Jeeves and in PIM | 4 |  | JH | YES | OPEN
09/04/2018 | Barbro Johansson | CJ | Add fields Product Name to Russia and Asian SU | high workload to support current solution (40 dev hrs spent last month) | 5 |  | JH | YES | OPEN
11/04/2018 | Paweł Nowak | One Jeeves | Main key Projcode disconnect from inventory transaction | Issue since Jeeves upgrade 5, main key of project has impact on all transaction in Jeeves. Jeeves team will not fix it. | 5 | JH | PANO | YES | OPEN | F6919 created
12/04/2018 | Olivier Pedroncini | 1J | VAt and order specific text - fields to be moved from all fields tab | fields need to be visible for users | 4 | KL | KL | YES | OPEN
12/04/2018 | Julia Homik | 1J | Package calculation method field to be local field | each company can have different price calculation | 4 |  | JH |  | OPEN
12/04/2018 | Roseline Labrune | 1J | De-mounting items and put back in stock as components. | Cost saving to use components separately instead of not selling the top item at all | 4 | AEL | AEL | On Hold | OPEN
12/04/2018 | Elena Zhang | CJ | China facotry sales calculation to be done on PC5 and not BC asles | Calculation in SZV is not ok according to the BC model set by the Group | 5 | KL | JH | YES | OPEN
12/04/2018 | Laurence Lakafia | 1J | Sales support report imporvements 6 points were highlighted, discussed within It dpt 2 weeks ago. I explained that we are reaching the technical limits of crystal report It is a MUST to have these improvements (correction of bugs + imporvements). Not being able to export datas to Excel is OK IF a query providing exactly the same datas can be created. It is a MUST to have these datas not only in Paper but being able to rework in Excel | 1/ Being able to exclude from the report all rows for which the allocation is done against stock (they want to keep only rows for which the goods are not available)  This seems to me reasonable and a good improvement 2/ When the user wants to see only rows with negative difference  They also can see rows with difference = 0 They want to remove rows with difference = 0  This looks to me to be more a defect 3/ Laurence says she can’t export in a nice way to Excel and that has been already reported. To check together the status 4/ One more point to investigate : Order row booked against PO  as you know such rows appear in yellow in the planning list and in the edit field we can see the allocation with PO nr and PO row nr It seems that such rows (booked against open PO) are appearing as available in stock  Can we check that together ? 5/ Default values Stock Item Only Y/N (No by default) DS order rows = Ticked by default 6/ PO Booking (request from Emilia) What I mean is that in the Sales Support Report it doesn’t show any discrepancy on the EDD date compared to PO OA date since allocation is Fully Booked when the SO is booked against PO. CS should see the discrepancy in the report as “minus days” when EDD is not correctly set according to availability. 7/ Removing zeros (similar to 2?) | 5 | MP | EL |  | OPEN
12/04/2018 | Laurence Lakafia | 1J | Delayed orders management imporvement As soon as a PO is delayed : For ICT factories an automatic mail is alerting the procurement dpt (with po nr, item, delayed qty, new delivery date) This is not enough. This functionality must be extended : For ICT, EDI, External suppliers, such mails need to be generated as soon as the PO has status 25.Order Acknowledged Moreover, this mail must be sent to sales support impacted by this delay (not only the purchase dpt, but also sales) |  | 5 | PN | EL |  | OPEN
12/04/2018 | Laurence Lakafia | 1J | Unbooking of order rows moved from "Entered/Entry in Progress" to status "Preliminary" | As soon as a Sales Order is moved from Status “Entry in Progress / Entered” to “Preliminary”, an automatic unbooking of corresponding order rows must be done + a warning message should be displayed to the user informing him about this unbooking | 4 | PN | EL | YES | IMPLEMENTED | This can be a reason of overbooking in all companies in 1J F6912
12/04/2018 | Stéphane Carrivain | 1J | Overbooking after Stock take adjustment | Jeeves Node in xinvj + Query is existing to provide items affected by overbooking. This is not enough, the system should also : • Unbook automatically all overbooked items (first unbooking the most recent order rows till the most oldest order rows) • Alert through email the sales support concerned (picking list printed or not) + same mail to the warehouse manager (so that the picking list can be collected and destroyed) + remove the PL print date | 5 | PN | EL | YES | OPEN
12/04/2018 | Stéphane Carrivain | 1J | Change of Items status by the factory / hub | As soon as an item status is changed and is related to an active pricelist, an automatic email should be sent to sales dpt alerting about such items status changes | 4 | PN | EL |  | OPEN
12/04/2018 | Stéphane Carrivain | 1J | Booking horizon improvement | As we know, the automated booking is working fine according to current rules : Booking horizon according to Item Lead Time + Safety window Purpose of adjustment : Booking routine using as Booking horizon a fixed booking horizon (which would be setup in a JVSP and adjusted each month). Example : 01/04 : setup of the booking horizon till the 06/05 01/05 : setup of the booking horizon till the 06/06 01/06 : setup of the booking horizon till the 06/07 01/07 : setup of the booking horizon till the 06/08 Etc… But still keep as priority, the creation date of each order row. | 5 | PN | EL | to be discussed | OPEN
17-4-2018 | Laurence Lakafia | 1J | Create of POD based on Excel file | To save a time, no not needed to create every single POD manually | 4 | MP | MP | check how often it will be used | OPEN | 6922
17-4-2018 | Tinne Adams | 1J | When in estimator you do a tiering, please unmark by default the checkbox ‘display total’, there is no total when you have a tiering | It looks strange and unprofessional towards the client | 3 | MP | MP | NO | REJECTED
18-4-2018 | Joanna Skiba | 1J | Upload of ORDERS based on Excel file | To save time. Currently orders with 300 lines and different customers has to be entered manually | 5 | MP | MP | wait for ROI | OPEN | 6921
02-4-2018 | O. Pedroncini | 1J | Information about advance payment in the footer of invoice as summary, instead of row | To have proper information and make view clear for customers | 4 | MP | MP |  | IMPLEMENTED | 6901
24-4-2018 | S. Roinard | 1J | Move discount fields from "all fields" tab to "HL Entry" | Possibility to cancel dicount on rows with fees. | 4 | MP | MP | YES | OPEN | 6925
07-05-2018 | V. Auger | 1J | Claims - messages about existing invoices should appera during registering, not saving | To save time and to avoid doubled records | 3 | MP | MP |  | OPEN

## Production
Process Leader |  | Lennart Johansson
Business Coordinator |  | Christer Sahlen
Date | Requested By | Authorized By | Approved By | Business Consultant | HL Unit | HL Area | Release | Product | Description | Justification | Prio | Added By | Est Dev (hrs) | Est Cost (EUR) | Decision | Decision date | Est Deliv Date | Status | Feature ID | Comment | Cust notified | RFC Link
2018-04-25 | Stephane C | [6 empty] | OneJeeves | Booking JOB MO | To avoid manual labour of booking | 5 | Andreas |  | 0 | YES |  |  | IMPLEMENTED |  | 6934
2018-04-26 | Roseline Labrune | [6 empty] | OneJeeves | Negative MO for subcontracting | To correct subcontracting | 4 | Andreas |  | 0 | YES |  |  | IMPLEMENTED |  | Guide sent to Roseline
2018-05-14 | Patrycja Slusarek |  |  |  | HL Display Gliwice Sp z.o.o | Central | R5.14 Dec | One Jeeves | Copying/replicate of MO data when creeting MO for simprints | It could allow much more speed up work of department Sales Support, Preparation and Prepress. It also could let us to avoid mistakes, which may be make because of repeating a lot times the same things. Can have 20-30 lines. sometimes we have just 2-3 simprints with total 10 rows, but sometimes there are 8-10 simprints with 100rows, it depends.. | 4 | AEL | 24 | 1440 | OK |  |  | IMPLEMENTED |  | Discussion will be taken in the pre-cab 10/7: Kasia justify the change. It is a local change. 28/8: Andreas to create feature 7134 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B9BB4BB3F-3DB8-4CDA-8F4B-08B6DCAAE982%7D&file=RFC%20MO%20-%20Simprints.DOCX&action=default&mobileredirect=true https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B6C49C819-695F-4233-82C0-6468830E2DF2%7D&file=RFC%20MO%20attachment%20-%20Simprints.docx&action=default&mobileredirect=true
2017-11-17 | Kinga Szygula | [6 empty] | One Jeeves | Subcontracting color coding in planning list | Raised by Sales Units. To be a clearar of when it is subcontracting and who then to contact at the HUB. | 4 | AEL |  | 0 | YES |  |  | IMPLEMENTED |  | Emilia, Gosia and Sarah keller raised this. Functionality should be similar to marked book MO. which is yellow. 6968
07-05-2016 | Rob Smith | [6 empty] | One Jeeves | Capture original confirmed date by factory | Save time | 4 | EL |  | 0 | Yes |  |  | IMPLEMENTED |  | 5494
| Maelle Fauconnier | [6 empty] | FraJvs001 | Upload item description language from XL file | Save time | 5 | EL |  | 0 | yes |  |  | IMPLEMENTED |  | 5493
| Ida Modigh | [6 empty] | Current Jv sdl ( ONE Jeeves 9 | We still have problems with "article description 2" in ONE Jeeves. We first noticed this when we received printed pos from ex Harlow, when they place one of our items alla of articles description2 comes through on the PO. This is not good, especially as the information is only for Sundsvall. Maja O has confirmed that a Feature was processed to stop this from happening with new items, so at least that is done. but for old items that text is already there. ( I presume she stopped the art descr 2 being tranfered from Sundsvall to ONE Jeeves ). I do not know how to solve this, I presume you will have to go in to each local jeeves to remove what has been transferred in asrt description 2 for the Sundsvall Items. | The text is only internal and not for the salescompanies, as well as it really does not look good on gthe orders. I have attached an example | 4 | CS |  | 0 |  |  |  | IMPLEMENTED |  | 5587
10.01.2018 | Kinga Szygula | [6 empty] | One Jeeves | MO report change | To avoid packing problems | 4 | KS |  | 0 | YES |  |  | IMPLEMENTED |  | 6809
| Aleksandra Pawlińska | [6 empty] | One Jeeves | Feature for Button 'Update sales price' to update price on PO | inccorret BC values on the invoices | 5 | JH |  | 0 |  |  |  | IMPLEMENTED |  | 5536
| Leszek Kwiatkowski | [6 empty] | One Jeeves | Block item calculation if there is an atempt to calculate on quantity = 1. | This is to ensure correct value of goods on stock and correct bookings of COGS in ERP system while it is being invoiced. | 5 | JH |  | 0 |  |  |  | IMPLEMENTED |  | 5548
| Paulina Wróblewska | [6 empty] | One Jeeves | Add time signature on MO ROW after Item recalculation. | Statistical purposes. Now we write each row individually to calculate preparation LT. To have control whether we meet our deadlines and KPIs. | 4 | JH |  | 0 | yes |  |  | IMPLEMENTED |  | 5697
| Paulina Wróblewska | [6 empty] | One Jeeves | Possibility to add date in „deadline column” on MO ROW that would be manually fullfiled by business service | Possibility to prioritize work. To have control whether we meet our deadlines and KPIs. | 4 | JH |  | 0 | yes |  |  | IMPLEMENTED |  | 5828
| Katarzyna Kłopotkowska/ Marcin Dutkiewicz | [6 empty] | One Jeeves | 3 different templates needed for Romania (RON, EUR, HUF) // Request's update - there will be 3 different footers - 1 for RON, 1 for HUF and 1 for EUR which is ok | Legal demand - different account for different currency | 5 | MP |  | 0 | Y |  |  | IMPLEMENTED |  | 5655
| Stephane Carrivain | [6 empty] | FraJvs001 | Upload of new Production Lead time for Gliwice items | Provide relevant informations to process requisitions and availablity of items in stock | 5 | EL |  | 0 | yes |  |  | IMPLEMENTED |  | 5621
| Maelle Fauconnier | [6 empty] | FraJvs001 | Import of Item description language from XL in arb table |  | 4 | EL |  | 0 |  |  |  | IMPLEMENTED |  | 5664
| Olivier Pedroncini | [6 empty] | FraJvs001 | Disable possibility to use the "X" to delete orders on order rows | Wrong figures in QV Same solution as OneJeeves requested | 4 | EL |  | 0 |  |  |  | IMPLEMENTED |  | 5654
| Emilia H | [6 empty] | ONE Jeeves | Freight charge are missed due to missing info when Disptaching we like som fields to be Mandontary | We send goods for free | 5 | CS |  | 0 | Yes |  |  | IMPLEMENTED |  | We have made achange by setting rules so that right Disptach method are choosen lets see outcome of that ! Erwan and CS to discus next step later
| Maelle Fauconnier | [6 empty] | FraJvs001 | New import of item description language Fr | Customer demand to get clear descriptions of items | 5 | EL |  | 0 | Yes |  |  | IMPLEMENTED |  | 5694
| Xavier V | [6 empty] | All ( GLI HUB ) | I guess that we need to look into “linking” order rows once they have been created in the system in order to have only one invoice. Let me know how this can be done. | Customer in Sweden receiving 8 cm of invoices .. | 5 | CS |  | 0 | Investigate MORE ! Anders LAutmann will call me for discusion how customer see on it. |  |  | IMPLEMENTED |  | Need to discus exatly need what is needed in more of a detail // Christer After Discussions with Anders Lautmann and Anette Karlssom we decided to CLOSE
| Emilia Hermio | [6 empty] | One Jeeves | Please add status of claim and customer info to list mode in program ork. | Make program more user friendly and useful. Also it will save a time. | 4 | MP |  | 0 | Yes |  |  | IMPLEMENTED |  | 5742
| 1J Support + Jackie Kilbridge | [6 empty] | One Jeeves | More detailed information about email status needed | At this moment we have information that email with invoice has been moved out of Jeeves but without veryfiaction in smtp server. For example email with wrong address has status "sent ok" but email was no send. | 4 | MP |  | 0 | yes |  |  | IMPLEMENTED |  | 5774
| Valentina Siemionowa | [6 empty] | Russian CJ | Small adjustment for RU CJ invoices are needed - new stamp. | Legal demand. | 5 | MP |  | 0 | yes |  |  | IMPLEMENTED |  | 5775
| Lena Persson | [6 empty] | Current Jeeses SDL | Add Country of Origin and Stat CODE on Invoice, Order conf and Delivery note ( note CR ) | Customer demand ! | 5 | CS |  | 0 | yes |  |  | IMPLEMENTED |  | 6112
| Marcin Pianka | [6 empty] | One Jeeves/DW | We have to create tabkle to keep information about deleted orders and order rows. | Right now user can delete orders and order rows the same day like there were created. Tghe issue is with order rows delerted after uploading and processing of DW. Such order rows are still in DW/QV but not in 1J. | 4 | MP |  | 0 | yes |  |  | IMPLEMENTED |  | 5796
| Erwan Lardic | [6 empty] | One Jeeves / DW | Year End routine 2016-2017 |  | 5 | EL |  | 0 | Yes |  |  | IMPLEMENTED |  | 5787
| Pascal Aubert | [6 empty] | FraJvs001 | Update of Terms in Conditions for all customers that have been ordering during 2016 | Align with financial decisions (reduce payment delays, imporve cash flow) | 5 | EL |  | 0 | yes |  |  | IMPLEMENTED |  | 5789
| Olivier Pedroncini | [6 empty] | All Asian companies current Jeeves | On the Asian country, with current Jeeves,the cristal report 1401 is not working properly on program BP. I would like to implement the 1401 report from the database FRAJVS001 called 1401 Test which is working well. Priority : 1/ Thailand 2/ Indonesia 3/ Other asian countries | We need to have a working report to be able to justify this account on all current Jeeves database. | 5 | EL |  | 0 | Yes |  |  | IMPLEMENTED |  | 5805 Marcin: Łukasz Sokół checked Jeeves in Asia - there is no deleted order rows in CJ sales offices. Only about 2100 rows in 2950 (1J, Shanghai)
| Szygula Kinga (KTW) | [6 empty] | OneJeeves | As client INEX Partners reuqests new type of labelling, we need adjustable tempalte for outer package on few items dedicated for that client, as well as labels for pallets. Pallet label must consist of information about items and how many packets are on that one pallet. If pallet is filled with one item, then that pallet label must consist that information. If pallet has several items, label must have information how many package pallet has totally. All different items must be marked to label. What customer highlighted was this SSCC marking. So that every logistic unit must be recognized with this kind serial number. Warehouse must be able to adjust the label for each different order. Outer package labels will always be the same for each item. Please take a look on sample labels attached. Biggest issue is incorporating EAN codes on labels. | Inex Partners are building new logistic center that will be filled with automation. They try to automate most of their receiving goods, that’s why they need our labels to be updated. We need adjustable template for both types of labels, outer package and pallet, to fulfill those requirements. | 4 | EL |  | 0 | Yes |  |  | IMPLEMENTED |  | 5804
| Jannicke Holdorf | [6 empty] | OneJeeves | There is possibility to change requested Requested Dispatch Date only once (program: order1). Please add possibility to change Requested Dispatch Date without any limitation. It should be control by JVSP parameter. | Sometimes there is necessary to change this date second time and system blocks it. | 3 | MP |  | 0 | Yes |  |  | IMPLEMENTED |  | 5820
| Adrian Różański | [6 empty] | OneJeeves | Add checkboxes to the list on MO | For reporting purposes employee has to check status on each MO line, 1 to 6 checkboxes. | 4 | JH |  | 0 | Yes |  |  | IMPLEMENTED |  | 5836
| Pascal Aubert | [6 empty] | FraJvs001 | Change of Terms and Conditions for all french customers that have been ordering since 01/01/2017 | Apply new french legislation | 5 | EL |  | 0 | Yes |  |  | IMPLEMENTED |  | 5789
| Maelle Fauconnier | [6 empty] | FraJvs001 | Import of french Item description Language | Customer satisfaction when reading HL external documents (Order ACK, Del Note, Invoice) | 4 | EL |  | 0 | Yes |  |  | IMPLEMENTED |  | 5801
| Barbara Misiaczek | [6 empty] | OneJeeves | Add item number to factory when item is created from the estimator in HUB |  | 5 | JH |  | 0 | Yes |  |  | IMPLEMENTED |  | 5838
| Łukasz Niezgódka | [6 empty] | OneJeeves | Create in picking list document in header or in last page information tha will be contained estimated number of pallets and weight on the basis of data product packaging in cardboard and further translated into the pallet | It will help to estimate how big the dispatch will be, how many trucks is needed and so on | 4 | JH |  | 0 | YES |  |  | IMPLEMENTED |  | 5920
| Murzina Evgeniya | [6 empty] | Current Jeeves RUS | In Jeeves Prod Rus need tochange Inventory Transaction Report (add column with incoming invoice number) according to correspondence below. We plan to put incoming invoice number in the line for comment: | Information needed for export to excel at later stage | 5 | CS |  | 0 | YES |  |  | IMPLEMENTED |  | OT Feature 5875 16 hrs | YES and asked for status 22/3 !
| Paulina Wróblewska | [6 empty] | OneJeeves | Calculate 'Deadline' column based on the creation date and item category like: Standard + 2 days, Modified Standard+ 3 days, Bespoke +5 days | Possibility to prioritize work. To have control whether we meet our deadlines and KPIs. | 4 | JH |  | 0 | YES |  |  | IMPLEMENTED |  | 5828, 5934
| Basia Misiaczek | [6 empty] | OneJeeves | Right-click arrow for Taric Code in Estimator | connected to new replication - feature 5777 from MIO project | 4 | JH |  | 0 | YES |  |  | IMPLEMENTED |  | 5897
| Gemma Watson | [6 empty] | OneJeeves | Please add possibility to add sub-brands to assign them to orders. There should be drop down list in order1, tab HL Finance and it should be visible in QV reports. | To keep control and to have more details regarding international brands, for example Coca-Cola | 4 | MP |  | 0 | YES |  |  | IMPLEMENTED |  | 5877
20-02-2017 | Joanna Skiba | [6 empty] | OneJeeves | Additional copy of corrective invoice is needed (print and reprint) | Legal demand | 5 | MP |  | 0 | YES |  |  | IMPLEMENTED |  | 5890
2017-02-22 | Adrian Róźański | [6 empty] | OneJeeves | Add Prototype frame to XTI | To calculate department workload/capacity I need to have specific data. This checkbox will allow to filter data for prototype workload. | 4 | JH |  | 0 | YES |  |  | IMPLEMENTED |  | 5932
2017-02-24 | Małgorzata Stasierska | [6 empty] | OneJeeves | Incoterms for Norway |  | 5 | MP |  | 0 | YES |  |  | IMPLEMENTED |  | 5937
03-03-2017 | Magdalena Kruk | [6 empty] | OneJeeves | GPI Polish control file | We should have the same structure for all control files. GPI Polish control files has to be adjusted | 5 | KS |  | 0 | YES |  |  | IMPLEMENTED |  | 6001
2017-03-22 | Adrian Róźański | [6 empty] | OneJeeves | Add field Blueprint to Subcotnract PO | to be sure that supplier knows how the final product should look like | 5 | JH |  | 0 | YES |  |  | IMPLEMENTED |  | 6009
2017-03-22 | Bartosz Wowra | [6 empty] | One Jeeves | Show document with name and not ID | today the list of documents is not clear, when there is several PDF files on only ID number then user is not sure which document is for which drawning | 4 | JH |  | 0 |  |  |  | IMPLEMENTED |  | pano will contact Bartosz with suggestion solution Decided by Kamil, PAwel and Christer that std is enough. | Pawel to inform BArtoz.
5-5-2017 | Emilia Hermio | [6 empty] | OneJeeves | Please to add to “credit note" template fields: - Who created claim - Claim reason And new field (drop down list) to ork program - Internal/External | 1) This document (credit note request) will be more clear 2) Internal correction/credit note to customer is needed | 4 | MP |  | 0 |  |  |  | IMPLEMENTED |  | Done within 6177
17-05-2017 | Adrian Róźański | [6 empty] | OneJeeves | On list M.O. to prepare correct checkbox timestamp to be always filled with Gliwice Factory time zone. Applies to all checkboxes on m.o. to prepare. | Need for time reporting. Currently wrong time -2 hours | 4 | JH |  | 0 | Yes |  |  | IMPLEMENTED |  | 6162
17-05-2017 | Adrian Róźański | [6 empty] | One Jeeves | Business service officer has to double check “prototype” checkbox on oder1 and xti M.O.– requirement is to replicate value from oh.q_hl_prototype to ti.q_hl_prototype when creating M.O. | Need for time reporting. Currently we have problems reporting preparation capacity in production preparation | 4 | JH |  | 0 | Yes |  |  | IMPLEMENTED |  | 6316
5-6-2017 | Marcin Pianka | [6 empty] | OneJeeves | Price unit factor (orp.fsgprisper) should be visible in the invoice (1190) | Some items have price for 100 pices and there are errors in rounding | 5 | MP |  | 0 | Yes |  |  | IMPLEMENTED |  | More investigation needed
13-6-2017 | Marcin Pianka | [6 empty] | Current Jeeves | Please create collective invoice (copy of EN COLL INV from 2950) | User's efficiency, save costs | 5 | MP |  | 0 | YES |  |  | IMPLEMENTED |  | 6197
2018-07-17 | Katarzyna Zelwor | [6 empty] | OneJeeves | Mo To Be Prepared column order | Only used by polish factory. Design would improve visibility and the same as in PO to be prepared | 4 | AEL | 4 | 240 | Yes |  |  | IMPLEMENTED |  | Kasia searching for old RFC Kasia to send RFC to Stephen /Andreas kaze: sent and OK if only for viewing: as discussed during pre-cab, I checked the case with Harlow (see below please) and send you the corrected RFC (attached). What is the status? Feature created 23/10 7205 Feature Completed but old view still is on Prod, pano will contact Support |  | https://hldisplay-my.sharepoint.com/:w:/g/personal/katarzyna_zelwor_hl-display_com/Eb0fs-hb_XFGt6fjvI94qHoB8ZO7okgF7ro7lVl50Mjthw
05/07/2017 | Maja Ostrowska, Małgorzata Stasierska | [6 empty] | OneJeeves | Additional parameter for mass calculation to keep previous qty | In order to use mass calculation in Hub. Today it is not possible to use it because the calculation in done based on the qty per pallet | 5 | JH |  | 0 | YES |  |  | IMPLEMENTED |  | 6257
2017-07-12 | Bartosz Wowra | [6 empty] | One Jeeves | Add Blueprint to PO template | to be sure that supplier knows how the final product should look like | 4 | JH |  | 0 |  |  |  | IMPLEMENTED |  | Wait for Erwan to discus We covered that request in Salmon project 7232 PO report adjustment in 1210
20/06/2017 | Boguslaw Kuczynski | [6 empty] | One Jeeves | Query x2 |  | 3 | AEL |  |  | YES but need to be disscus with Christer |  |  | IMPLEMENTED |  | Wait for update from Responsible user back in W.34, waiting for his info. Bogus to update me. Same as open order request
22/08/2017 | Damian Glajcar | [6 empty] | One Jeeves | XTI program: Delivdate SO – this is the button confirming that the order line is planned. However, there is no date showing WHEN it was done. It is crucial to develop a new field with date and time of order row planning. | Without this field we are not able to report any proper KPI planning time. | 4 | JH |  | 0 | YES |  |  | IMPLEMENTED |  | 6385
01/08/2017 | Sarah Keller | [6 empty] | One Jeeves | Planning List in ofhestimator | They would like to have the planning list in the offer. It is faster to have it there than to go to the item firstly. | 4 | JH |  |  | YES |  |  | IMPLEMENTED |  | 6361
20/06/2017 | Boguslaw Kuczynski | [6 empty] | One Jeeves | Query for logistics analyze of open orders |  | 3 | AEL |  |  | YES |  |  | IMPLEMENTED |  | Country of delivery missing, change needed to query. Responsible user back in W.34, waiting for his info. Bogus to update me FEATURE = 6203
24-01-2018 | Kay Phillips | [6 empty] | OneJeeves | Item description textbox should be increased in Item Program | Crucial part of the item description is not visible without moving the cursor inside the textbox. At least in the ITEM program the complete item description should be possible to be seen to reduce work and improve overview in the program | 4 | AEL |  |  | YES |  |  | IMPLEMENTED |  | 6853
07-03-2018 | Katarzyna Zelwor | [6 empty] | OneJeeves | They want to have Created by user automatically replicated to supervisor | To reduce manual work of adding field information | 3 | AEL |  | 0 | YES |  |  | IMPLEMENTED |  | 9/3: Discussion on-going with Katarzyna about how they can work instead so we use field for what they are meant for. 12/3: Agreed that a created by column in Plan List would be enough 6944
15/08/2017 | Boguslaw Kuczynski | [6 empty] | OneJeeves | Is it possible to add new field on ORK where we can chose one of two options for each claim- Approved or NOT Approved. Is it possible to add new field on ORK where we can chose one of two options for each claim- Approved or NOT Approved (I can’t find this @ on my Outlook) |  | 3 | AEL |  |  | YES |  |  | IMPLEMENTED |  | Done within 6177 project
| Katarzyna Zelwor | [6 empty] | One Jeeves | During copying order rows within one quotation system should copy also field: "Inquiry date" | - save user's time - make proces easier - be sure this field is filled - these values are taken into KPI | 4 | MP |  | 0 | yes |  |  | IMPLEMENTED |  | 5593
8/09/2017 | Anette Karlsson | [6 empty] | One Jeeves | We receive orders from circle K into Jeeves by Ariba system. These orders do not get the box "earlier dispatch allowed" ticked as default. We ant it to be ticked as def. | Misses at CS causes later problems in flow | 5 | CS |  |  | YES |  |  | IMPLEMENTED |  | 6573
6/11/2017 | Emilia Harmio | [6 empty] | One Jeeves | During processing order form Ariba system should automatoically fill field "sales type" using value "customer system". | To save time and to avoid mistakes. | 4 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6573
7/11/2017 | Sarah Keller | [6 empty] | One Jeeves | Advance payment templates | Legal demand | 5 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6580
| Leszek Kwiatkowski | [6 empty] | One Jeeves | Block possibility of: 1) setting items to status: - Sellable or - Component not for sale or - Approved for production Where CurrentCostPrice = 0 and Product Account = HLPROD. 2) creating Manufacturing Order where current cost price of item is equal to 0 and itemStatus = Approved for production | This is to ensure correct value of goods on stock and correct bookings of COGS in ERP system while it is being invoiced. | 5 | JH | [5 empty] | IMPLEMENTED |  | 5547Completed , 5549 remain
2018-02-02 | Darren Webb | [6 empty] | One jeeves | Changing of MO report |  | 5 | AEL | 8 | 480 | YES |  |  | IMPLEMENTED |  | 7017. Prioritize for next sprint due to upcoming ISO Audit /AEL 2018-06-17
2018-02-28 | Tymoteusz Glajcar | [6 empty] | One jeeves | Golem Implementation | We need to transfer data from Jeeves to Golem | 5 | Julia |  | 0 | YES |  |  | IMPLEMENTED |  | 6810
28/05/2018 | Sandra Öhman | [6 empty] | Current jeeves | Change of Item Category to "standard" remove "LM Standard from table. | Have correct Basic Data on Item Level | 4 | CS |  | 0 |  |  |  | IMPLEMENTED |  | 6980. Excel file exist of 20 000 Items
2018-06-07 | Emilia Hermiö | [6 empty] | OneJeeves | Sales unit BOM and stock balance visiblity | More efficient workflow to reduce LT and faster response time. Also to ensure correct production. | 5 | AEL |  | 0 | Yes |  |  | IMPLEMENTED |  | 7011. Confirmed release date 20/7 with Emilia. To be estimated. /AEL 2018-06-17 Check if there is a report in QV to see the BOM. DIscussed in the sales pre-cab /Andreas 7011
| Katarzyna Zelwor | [6 empty] | One Jeeves | When field "Inquiry date" (ofh.q_cusreqquoteday) on quotation's header is filled then during creation new quotation row this date should be copied automatically to field "Inquiry date" (ofp.q_cusreqquoteday). | To save time and have more realistic lead times | 4 | MP |  | 0 | yes |  |  | IMPLEMENTED |  | 5762
2018-08-08 | Anna Welin | [6 empty] | Current Jeeves | Identify Prod items including ABS Material SDL JVS - To identify all active items consisting of raw material item no 362785 and 369457(in Jeeves Sdl) | Indespensable change. Items including raw material items above to have new calculated prices from October 1st 2018. | 5 | AEL |  | 0 |  |  |  | IMPLEMENTED |  | 13/8: Active items : ar.itemoktouse = ticked 28/8: Anna is being supported on how to search. |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B207FBE2A-1053-4130-82F6-4734C44C81A6%7D&file=RFC%20-%20identify%20prod%20items%20including%20ABS-material%20SDL%20Jvs%20-%20Anna%20Welin.docx&action=default&mobileredirect=true
2018-08-08 | Anna Welin | [6 empty] | Current Jeeves | Items including ABS Material on single calc id JVS - To place all active items including raw material item no 362785 and 369457 on own calculation id (in Jeeves Sdl) | Indespensable change. Items including raw material items above to have new calculated prices from October 1st 2018. | 5 | AEL |  | 0 |  |  |  | IMPLEMENTED |  | 13/8: Active items : ar.itemoktouse = ticked 28/8: Anna is being supported on how to search. |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B44501FA5-8ADB-4099-8AB9-2BDAB42D801E%7D&file=RFC%20-%20items%20including%20ABS%20material%20on%20single%20calculation%20id%20SDL%20Jvs%20-%20Anna%20Welin.docx&action=default&mobileredirect=true
2018-08-23 | Ida Modigh |  |  |  | HL Display Sundsvall AB | North East |  | Current Jeeves | Text to appear on picking list. To be set on article level and inicate on RPT-Print report. "Item consist of 2 boxes" | Additional clarification is needed when 17 new warehouse operators are employed. | 5 | AEL | 10 | 600 | YES |  | 2018-10-22 2016-11-16 | IMPLEMENTED |  | 28/8: Andreas to update Ida 23/10: See possibility of releasing sooner 7206 |  | https://hldisplay-my.sharepoint.com/personal/andreas_ekmanlindqvist_hl-display_com/_layouts/15/onedrive.aspx?listurl=https%3A%2F%2Fhldisplay%2Esharepoint%2Ecom%2Fsites%2Fitdocumentationrepository%2FDelade%20dokument&id=%2Fsites%2Fitdocumentationrepository%2FDelade%20dokument%2FCAB%2FRFC%2FOpen%2FChange%20Request-%20Note%20on%20pickinglist%20to%20be%20added%202018-08-23%2Epdf&parent=%2Fsites%2Fitdocumentationrepository%2FDelade%20dokument%2FCAB%2FRFC%2FOpen
2018-10-17 | Ida Modigh | [6 empty] | CJ | Add country of origin to labels | Needed for goods shipped into Dubai | 5 | AEL | 2 | 120 | YES | 17/10/2018 | Novemeber | IMPLEMENTED | 7193 | 17/10: Urgent CAB request. 7193. Released on 16/11/2018
2018-10-08 | Jessica Steffen / Anna Welin | [6 empty] | CJ | Update Invoice Statistics | Incorrect margin and base cost | 5 | AEL |  | 0 |  |  |  | IMPLEMENTED
20-02-2017 | Katarzyna Zelwor |  |  |  | HL Display Gliwice Sp z.o.o | Factories |  | OneJeeves | Add EOQ calculation to Estimator | To make possible to prepare IM items in Estimator program | 4 | JH |  | 0 | YES |  |  | IMPLEMENTED |  | 5894
28/08/2018 | Katarzyna Zelwor / Leszek Kwiatkowski | Magda Oczko | [5 empty] | One Jeeves | Production stock of components decimal places increase. The same request in row 113: change invetory fields design to 5 decimal places | KAZE: We need real value of components stock with at least 3 decimals, this is important in case of components like tapes where the components unit is meter. We have wrong components stock. LEKW: it is possible to pick material for more than 2 decimal places but it is not possible to see how much is left in stock and to do the stocktaking | 5 | PANO | 32 | 1920 | investigation | 05/11/2019 |  | REJECTED |  | 29/08 continue discusion on Production CAB 06/09: Moved to production feature: 5546 (Julia) - rejected 23/10: PRIO 5. Meeting to be with, Pawel N, Christer, Andreas, Katarzyna, Kinga L More Invetigation from Gliwici controlling Dimitrios. 24/09 wait for Dimitrios and end of calculation 05/11: no issue now, we can close it |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVFxlMSUrXVGpf1pYfPU75gBfwCzGrqDq1Ep0ogR6-fd7g?e=HeZpsm
2018-08-08 | Kinga Szyguła |  |  |  | Costs info in comment |  |  | OneJeeves | Picking MO - 1. Add "picked by" field in MRU2 and MRU3 2. Create report funct. in MRU3 that 1 picker picked all components. 3. Create reporting funct. in MRU2 who picked each row. | Decision Supporting. WH will be able to trace picking productivity of employees. Operators are today being tracked based on the production productivity but not MO pickers. | 4 | AEL | 40 | 2400 | onhold | 16/12/2019 |  | ON HOLD |  | 10/8: MRU3:aad:aor1h MRU2:aab:mrmru1 Better justification /Andreas 28/8 check if QV possible,involve other unit in disscusion on PreCab 04/09 cost will be taken by FRA and GLiwice HUB 24/09 Kinga S will check points with Stephane |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BCBDA8E27-ED19-4516-AF70-3AD684F42D66%7D&file=RFC%20-%20picking%20MO%20-%20Kinga%20Szygula.docx&action=default&mobileredirect=true
2018-08-27 | Stephane Carrivain | Stephane Carrivain | [5 empty] | OneJeeves | (CUBE) Performance indicator MO- We need these fields, Mo number, jeeves number, description, qty, item group, flow group, manufacturing group, mo/works orders status, created date, start date, ready date, inbound date, gross purch price curr, unit time. Per week or per week statistics when necessary. | With the new ISO version that we want to get it – it will be necessary for each processus described to get a performance indicator. This should already exist | 4 | AEL | 16 | 960 | onhold | 16/12/2019 |  | ON HOLD |  | Plan meeting with other managers so they optimize the Cube for other entities /Andreas /28/8 Update from Stephane? check if we can see that in QV 24/09 wait for Stephane C. and then close 14/10 FRA still interested, querry which used now not show lineked SO; Cube indeed better data visualization |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BF7EA0680-D518-421B-ACB0-A5D97A69F606%7D&file=RFC%20-%20Performance%20indicator%20MO%20-%20Stephane%20Carrivain.docx&action=default&mobileredirect=true
2019-01-25 | Patrycja Slusarek | Magda Oczko |  |  | HL Display Gliwice Sp z.o.o |  |  | 1J | Improvement of Feature 7134 Replicating Data when creating MO for Shipment | It could allow much more speed up work of department Sales Support, Preparation and Prepress. It also could let us to avoid mistakes, which may be make because of repeating a lot times the same things | 4 | AEL | 20 | 1200 | onhold | 24/09/2019 |  | REJECTED |  | 20/2 RFC added investiagtion of dev time: point1 around 16 hrs, point 2 around 4 hrs 27/08 Katarzyna Z. will check with Magda O. if she approve the cost 24/09 put onhold and check solution q_hl_upload |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BD584CB24-5DA6-4599-85A6-6788D3EB1186%7D&file=RFC%20-%20improvement%20of%207134%20-%20Replicating%20data%20when%20creating%20MO%20for%20simprints.docx&action=default&mobileredirect=true
| Ida Modigh | [6 empty] | Current Jeeves | We have decided to reduce the quantity of acquisition methods in Sundsvalls jeeves as a preparation for going over to One Jeeves.To do this we will have to change the acquisition method on some items. I have created a list with 2900 items where this needs to be changed.To do this we will have to change the acquisition method on some items. I have created a list with 2900 items where this needs to be changed.On the list you can see the metod that is current and the one it should be changed into. I have marked the column in yellow that it should be changed to. | It will help us clean up the system in preparation for one jeeves. | 3 | CS | 4 | 240 | Discus at Pree Study SDL |  |  | ON HOLD |  | Is it really needed before the Migration to OneJeeves or can this be done while we prepare mapping files for OneJeeves 04/07 mapping file was done and ACQ method map with current ACQ exist in 1J
2017-08-22 | Jannicke Holdorf | [6 empty] | One Jeeves | Already booked rows against incoming PO should be marked yellow in program order1. Currently users have to go to the planning list | To save user's time and increase overview. | 4 | MP | 16 | 960 | Wait for MP 14/5 MP Suggest that its Rejected ! |  |  | REJECTED |  | 6363 / mail sent to Erwan if makes sense 01/03/2018: Marcin to check if the request is still valid 10/7: Andreas to check 23/08/2019: New sales support report show that orders | Agreed with Jannicke and Anette that we will put this onhold as no use as is today // C
2018-07-10 | Agnieszka Dudek | [6 empty] | OneJeeves | Automatic information about the change of the planning of the MO to the customer officer of the linked order / if any change is made after the order had been confirmed to the customer Change of e.g ready date. | Improvement of communication with the customers and between departments. | 4 | AEL | 24 | 1440 | onhold |  |  | ON HOLD |  | 10/7: Not defined in the process how to work with changes. On hold and discussed outside of Pre-CAB. /Andreas 22/08/2019 pano: we agreed with Agnieszka and Kasia to check solution with workflow tool (wait for guide from Jeeves)
2017-10-16 | Katarzyna Kielar |  |  |  | HL Display Gliwice Sp z.o.o | Factories |  | One Jeeves | Add BC unit and BC start fields in BOM | Not given, reason rationalizaing. KAZE: we need to see the price of the component in BOM. | 4 | AEL | 4 | 240 | yes |  | May 2018 | IMPLEMENTED |  | Values is already set in system if item is "Purchase to order point" 6879 08/08/2019 email send to user to confirm if request is already implemented |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/WopiFrame.aspx?sourcedoc=%7BBA9F0E11-85A7-4939-A419-2C6D692500A9%7D&file=HL%20IT%20Change%20Request%20Form%20-%20kaki%2016.10.17.docx&action=default
2018-04-25 | Stephen Mepsted | Stephen Mepsted | Christer Sahlén |  | HL Display Harlow Ltd |  | R19.10 Oct | 1J | Add field PLANNING MANAGER to AOTODO program | Planning manager is used to categories items for different reasons one is for searching purposes. This function would allow us to be selective on which MOs to pick due to different internal LT. | 3 | PANO | 4 | 240 | YES | 22/05/2018 | Oct/Nov | IMPLEMENTED | 7612 | 10/7: Andreas to check about this 08/08/2019 email send to Steven if request is still valid 13/08 request valid and RFC found :) cost will be taken by Harlow Factory |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ETQrXfMafVBHokor7PNOyRoBfM9HUyscRy5ngH2Dmwlq8A?e=qnzKtt
2018-08-27 | Stephane Carrivain | Stephane Carrivain | Christer Sahlén |  | Costs info in comment | West | R19.11 Nov | OneJeeves | PO nr on del.note - Delivery note for MO linked to a PO - in order supplier to be able to find the corresponding PO among all pces received from us, we would like the PO nr to be automatically mentioned on the delivery note when goods are send | Indespensible | 4 | AEL | 8 | 480 | YES | 22/05/2019 | September/ October | IMPLEMENTED | 7603 | Add to english template /Andreas check if all HL to use on preCab 19/08 pano: only HUB 1600,1810 are interested, specifcation adjusted |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BD02EBFCC-DA97-4CB3-A1A9-D6C8EB9650BB%7D&file=RFC%20-%20PO%20nr%20on%20Del.%20note%20-%20Stephane%20carrivain.docx&action=default&mobileredirect=true
2018-08-27 | Stephane Carrivain | Stephane Carrivain | Christer Sahlén |  | Costs info in comment | West | R19.11 Nov | OneJeeves | Pop up component not sellable - MO | It has had of course consequences for the customer's deadlines. KAZE 07/09: We also need the warning in 1190 - or a change in the system: if a component is "DISCONTINUED" and there is no replacement => item status should be changed to: "TO BE discontinued". Is this something acceptable for other units? | 5 | AEL | 8 | 480 | YES | 08/08/2019 | Oct/Nov | IMPLEMENTED | 7620 | Kamil to find the feature that was made /Andreas 28/8 Investigate replacement for not sellable items existing as component Feature only exist for CCP =0 and not for use./AEL 29/8 08/08/2019 email sent to users and check proposition of development 22/08 pano:approved solution during meeting, feature will be created soon, cost will be taken by French HUB, Gliwice and Harlow Factory |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdmVtrhAXsdBj92ce0pWrsAB4A7y-B0AqxX00__tZLXm-A?e=UHetgg
2018-09-05 | Ida Modigh |  |  |  | HL Display Sundsvall AB | Factories |  | Current Jeeves SDL | Sign-in operators - They want to be able to get names of pickers and inbound personnel | To be able to keep control with newly recruited operators working in 2 entities / 2 systems | 5 | AEL |  | 0 | onhold |  |  | REJECTED |  | Chirster to check license to Jeeves. License according to Tomas O = 600 sek per user and Month. | Ida informed about cost | https://hldisplay.sharepoint.com/sites/itdocumentationrepository/Delade%20dokument/Forms/AllItems.aspx?id=%2Fsites%2Fitdocumentationrepository%2FDelade%20dokument%2FCAB%2FRFC%2FNew%2FRFC%20-%20Signing%20operator%20-%20Ida%20Modigh%20%281%29%2Epdf&parent=%2Fsites%2Fitdocumentationrepository%2FDelade%20dokument%2FCAB%2FRFC%2FNew
12/04/2018 | Elena Zhang | Jessica Steffen | Benno Eliasson |  | HL Display AB - Finance | Costs info in comment |  | CJ | China factory sales calculation to be done on PC5 and not BC sales | Calculation in SZV is not ok according to the BC model set by the Group | 5 | kipa | 24 | 1440 | YES | 27/08/2019 | 2020-11-20 | IN PROGRESS | 7625 | KIPA: should be handled by Andreas as a part of production area 7/9: Moved to Production Christer will check status Asked about more info, waiting for reply 27/08 confirmed by Jessica and King L to start developement in SZV, Kinga L will check if AB take the cost 29/08 cost will be taken by AB 14/01 waiting for final decision from business regarding count prices |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUxc74rT5ylJrYzSSvRlvYkBMkNIRspYl4ehJklxP-cf7w?e=7E5biU
2018-10-17 | Stephen Mepsted | Stephen Mepsted | Lennart Johansson |  | HL Display Harlow Ltd | Factories |  | 1J | Kanban hybrid |  | 4 | AEL | 54 | 3240 | yes | 23/09/2020 | nov/dec | IN PROGRESS |  | 22/10: Waiting for RFC 1/11: RFC and flow proposals in the repository. 27/08 flow need to be investigate and review with Christer 24/09 meeting this week 05/11: setup meeting and discuss whole flow Chister, Stephen, Pawel 9/12 raw estimatation around 80hrs 13/01 meeting regarding full flow, raw estimation changed :) 23/09 cost will be cover by.. |  | 3 LINKS BELOW https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BEAF0FD61-BAD9-43B3-ADE3-7D2D93F8C4B7%7D&file=RFC%20-%20Kanban%20Hybrid%20-%20Stephen%20Mepsted.docx&action=default&mobileredirect=true https://hldisplay.sharepoint.com/:x:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B26F9E351-679B-4FFE-850D-AF48E3FAFAF3%7D&file=RFC%20-%20Kanban%20Hybrid%20-%20Stephen%20Mepsted%20(attachment%202).xlsx&action=default&mobileredirect=true https://hldisplay.sharepoint.com/:x:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B26f9e351-679b-4ffe-850d-af48e3fafaf3%7D&action=default&uid=%7B26F9E351-679B-4FFE-850D-AF48E3FAFAF3%7D&ListItemId=12005&ListId=%7B61E1BBBF-F99F-4B52-83FD-E4342D62EA17%7D&odsp=1&env=prod
2018-10-15 | Stephen Mepsted | Stephen Mepsted |  |  | HL Display Harlow Ltd | Factories |  | 1J | MO Change Log | MO tracability, KPI Reporting, requirement for ISO 9001 | 5 | AEL |  | 0 | investigation | 27/08/2019 |  | INVESTIGATION |  | 2/11: Waiting for RFC 13/11: RFC added could be combine with request from Kinga row.123 ? 04/09 interested UK, Gliwice HUB/Factory 16/12 wait for feedback and maybe we can use existed CUBE 16/07/20 Paweł prepared logs in Jeeves and made query - waiting for vefirication |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B18ED40A6-319B-4578-9C2E-6E0AF16E23F2%7D&file=RFC%20-%20MO%20Change%20Log%20-%20Stephen%20Mepsted.docx&action=default&mobileredirect=true
2019-04-15 | Viktoria Kazieva |  | Christer Sahlén |  | HL Display Nordic | North East | R19.7 Jul | 1J | In order to plan AV and factory assembly works performed by the same team, the person planning it needs overview of AV’s Manufacturing Order details. When extracting data from xti for all MOs, the table only contains time, dates, item and economic date. We’d need the following columns added to the extraction: | Better control of operator’s time and overview of what is planned/expected/ongoing. Current view gives no details which means poor control and as a result inefficient planning of MOs and time distribution for Operators | 4 | CS | 4 | 240 | YES | 22/05/2019 | July | IMPLEMENTED | 7524 | Operation could NOT be added ! | YES | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQi0-SNnR0pKsMq3fEU21jgBtsTIhpvS3Sl77DKErZwSiQ?e=j5yrtW
2019-01-10 | Stephen Mepsted | Stephen Mepsted | Christer Sahlén |  | HL Display Harlow Ltd | Factories | R19.10 Oct | 1J | Put the artwork Field ar.q_hl_artwork on the Print MO Barcode Crystal Report located in program xti | Traceability FACTORY ! | 3 | CS | 5.25 | 315 | YES | 22/05/2019 | Oct/Nov | IMPLEMENTED | 7602 | RFC added CS cost taken by Harlow factory |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B7E0A5EA6-ADDA-4961-B88E-D615D9AD46BD%7D&file=Request%20for%20Change%20-%20Artwork%20on%20MO%20-%20HL%20Display%20(1)%20-%20Copy.docx&action=default&mobileredirect=true
2019-02-22 | Stephen Mepsted | Stephen Mepsted | Christer Sahlén |  | HL Display Harlow Ltd | Factories | R19.8 Aug | 1J | Please can we add the Artwork number filed and Blueprint to the upload spreadsheet so it can update automatically | Impove quality and will improve the communication flow | 4 | CS | 4 | 240 € | YES | 22/05/2019 | August | IMPLEMENTED | 7546 | RFC added CS 11/06 feature created by pano |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbutgcEthJJFt7DIj0d54rsBoVjdfJVeGjlxnaT7KZgwbQ?e=A5kFlt
2019-05-09 | Mikael Johansson | Håkan Tjernberg | Christer Sahlén |  | HL Display Sundsvall AB | Factories |  | CJ | We need to add cuSL on all CGC and CGS articles to have a good quality in production. Add cuSL in article description and add 728334 Smältlim – Prod in BOM. Its 2845articles we need to make this change on. | We can´t reach the quality requested if not assemble this glue(cuSL) on above articles. | 4 | CS | 8 | 480 | YES | 22/05/2019 |  | IMPLEMENTED | 7519 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BD7AF5472-344A-4380-8C08-F417C83D3022%7D&file=Request%20for%20change%20update%20Sm%C3%A4ltlim%20SDL.docx&action=default&mobileredirect=true | https://hldisplay.sharepoint.com/:x:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7Bad99812a-bf64-4216-9ff8-19c36e3d407e%7D&action=default&uid=%7BAD99812A-BF64-4216-9FF8-19C36E3D407E%7D&ListItemId=12787&ListId=%7B61E1BBBF-F99F-4B52-83FD-E4342D62EA17%7D&odsp=1&env=prod
2019-05-13 | Bartosz Wowra | Lars Ämtenmyr | Christer Sahlén |  | HL Display Nordic | Costs info in comment | R19.9 Sep | 1J | Add item descritpion and specifaction MO Added value report | LACK OF INFORMATION EXTENDS THE TIME FOR PRODUCTION MO AND DECREASE EFFICIENCY OF WORK | 4 | PANO | 7 | 420 | YES | 22/05/2019 | September | IMPLEMENTED | 7601 | 08/08 feature 7601 created 04/09 cost will be share within FRA, Nordic HUB |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERYnBCiR-RhIs6IfjwfJ9J0BhEkFCXRblNttjqYUTpTF6w?e=TH8jDk
2019-05-13 | Daniel Jania | Magda Oczko | Christer Sahlén |  | HL Display Gliwice Sp z.o.o | Factories | R19.9 Sep | 1J | When planner want to create MO for production and print documentation for it print all documentation from Item. We want to print data only from MO and operations. Not all data from ITEM only data from MO | Money saving ~5k PLN per year + ecological aspect | 4 | pano | 24 | 1440 | YES | 22/05/2019 | August/September | IMPLEMENTED | 7567 | pano will contact daniel 21/05 waiting for feedback 04/07 users chose two option of printing solution, one with PDM sorting and second with general list with optional marking |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EW_LqhdkuIZDkRb0XD2JUl4BZA7bG-l9iTLi9QQmmfHq_g?e=ldf9em
2019-02-04 | Stephen Mepsted | Stephen Mepsted | Christer Sahlén |  | HL Display Harlow Ltd | Costs info in comment | R19.10 Oct | 1J | Printing Multiple MO:s from xti program. FACTORY | Time SAVING, instead of printing 1 MO at a time you set your criteria and print in bulk. | 4 | CS | 24 | 1440 | YES | 22/05/2019 | Oct/Nov | IMPLEMENTED | 7606 7649 | I like to investigate "leaving" Crystal and design in Jeeves std report lets talk on Pre CAB. // Christer 08/08/2019 email send to all users concern this process 13/08 proposal solution created, cost it will be share wiithin - Harlow factory and FRA HUB |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BE85CC4C9-C199-40ED-A4F4-C1347B7F4D1A%7D&file=Request%20for%20Change%20-%20Multiple%20MOs.docx&action=default&mobileredirect=true
2019-05-13 | Aleksandra Kurzak | Magda Oczko | Christer Sahlén |  | HL Display Gliwice Sp z.o.o | Factories | R19.9 Sep | 1J | On planning list there are rows which are marked in blue color (MOs with subcontracting) but this functionality is pointless (only HUB use it ). Instead, it would be helpful to mark rows which are still on Preparation list --> Procurement department will be able to differentiate for which orders components should be ordered (the right moment/quantity/material for placing Purchase Order) | Currently all items generate requisition for components included in BOM (no matter if item is already set or not). The most time-consuming task (daily) for Procurement Department is to differentiate which component should be ordered and which has to wait for final calculation. Preparation team can implement a lot of changes while setting the final item. This is the main reason why Procurement should be very careful with placing orders (not to buy unnecessary components and increase stock value). Visible change (color) on planning list will be a major improvement in Procurement’s work, because it is highly probable to make a mistake in the way it is processed now. | 4 | PANO | 4 | 240 | YES | 22/05/2019 | September | IMPLEMENTED | 7545 | 20/05: add one checkbox on Planning list and use standard Jeeves colors, MO subco should be coloured in Hub not in factory, 11/06 feature created by pano, cost will be taken by Gliwice factory |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbrKM4vkG15EqRm-i6Q7bpkBF_r3nTNBGbXCYs_Dy5bqOw?e=cCvDxV https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeWJ70ND5nNAv4OxMibgQ58Bv0fx3CZ4ZwMuuvORO9Z7Hg?e=LXNdho
2016-06-09 | Torbjörn Schedin | [6 empty] | Sundsvall CJ | Actual machine time | To be able to plan maintenance, decrease breakdowns and manage the machines better they are extended the sensors on several machines and need to have actual run time from machines. This is not possible through Jeeves | 5 | Andreas |  | 0 | PAUSED IT |  |  | REJECTED |  | Discussed with Christer and agreeed. They will do a first test themselves.
2017-05-31 | Michal Los | [6 empty] | One Jeeves | Create new tab in item program | They think they can rationalize their work by combining information from several views. HL Inventory, HL Properties, item balances. | 4 | AEL |  | 0 | Rejected |  |  | REJECTED |  | Should we create a new tab? Second part of RFC is unclear, need to book meeting with requestor. If no new TAB. They would like to have a view with BOM and Operations. 15/03: meeting to discuss Ewa will show ARPROD to her team. Together with this a development should be done to add 3 columns in the BOM list, BCU, BCS and purchase price.
2018-04-20 | Alejandro Aquino | [6 empty] | Sundsvall CJ | Replacement of old force gauge equipment (Software and hardware) | Incorrect results. Operational impact | 5 | Andreas |  | 0 | Moved to Infra |  |  | REJECTED |  | Directed to infrastructure and Marika Westrin
2017-05-25 | Katarzyna Zelwor | [6 empty] | One Jeeves | Update article search of inventory location sample (ars.lagstalle ) at the moment we have only main warehouse. | Samples availability is crucial in the offering process.In case of injection molded technology samples production on request is not profitable due to high base cost start. The factory needs to stock as many samples as possible to enable KAMs to build prototypes, test them with customer’s products and give the customer touch and feel of the solution, which is offered. Another very crucial success factor in offering process is speed to market. Quick information about samples availability could improve our offering process significantly. Main benefits of introducing the possibility to filter “samples inventory” on HL Net:Sales units would get quick information about what samples are available and can decide by themselves what items suit customer needs bestSales units could place the order immediately and get samples asapGLI factory would not waste time on ping pong emails informing about samples availability and could concentrate on other tasksGLI factory would not waste time on ping pong emails informing about samples availability and could concentrate on other tasks | 4 | CS | 24 | 1440 | OK |  |  | REJECTED |  | ASK XLENT for offer if XAvier agree // CS NO RESPONS and Xavier left evaluate respond External development needed 10/7: No external dev needed /Kamil 07/09: kaze / what is the status?
| Marcin PIanka | [6 empty] | One Jeeves | Use functionality of 5439 for standard purchase orders (not only DD) | Save time, better communication, less | 4 | MP |  | 0 | NO |  |  | REJECTED |  | 07/09/2016 EL : for stad PO, the procurement dpt job is to check the order response
| Stephen Mepsted | [6 empty] | One Jeeves | New inventory location needed - called "Lightwood " | "We have another outside storage company who stores our bulk stock. If we don’t locate it there sales can sell the stock thinking its onsite and ready available also it’s for the auditors when they come to check our inventory." | 4 | MP |  | 0 | NO |  |  | REJECTED |  | 5534 | YES
17-05-2017 | Katarzyna Zelwor | [6 empty] | One Jeeves | Make M.O. checkboxes from HL Orderunique (xti:aa:wxti) possible to mass change on multiple items in “MO to prepare” list. | For reporting purposes employee has to check status on each MO line, 1 to 6 checkboxes. | 4 | JH | 20 | 1200 | Rejected |  |  | REJECTED
| Ida Modigh / Håkan T | [6 empty] | Current Jeeves SDL | To be able to give a correct price to the customer and track the hit rate of quotationswe would like to do the following change in the Sundsvall Jeeves. Add a 4 digit field for the OFF number in customer order program xxx that is searchable and possible to use in queries. The field should be on the order row as it will be matched to specific articles. | Messure perfomance and give feedback | 4 | CS |  | 0 |  |  |  | REJECTED |  | Rejected with other solution /AEL 28/6
| Tiina Holma | [6 empty] | One Jeeves | Tick box to programs Invoicing (orderhf) and also for Customer (kus) For invoicing; to help take only e-invoices out, so we can handle better our outgoing invoices. We do not need to double check every invoice whether it has been gone by IT or should we send paper invoice to customer. And for kus; to mark customer with correct information so it can be checked easily. We can check from this program if their invoices are normally send via IT or by post. | Two of our biggest customers has waited e-invoicing for a year now. This will help us CSO here in the office with easier way to print invoices and we save money and resource’s when we don’t print unnecessary paper invoices. | 4 | CS |  | 0 | Go back and look at process. |  |  | REJECTED |  | e-invoicing implemented
| Mikael Agustsson - 161114 | [6 empty] | Current Jeeves SDL(Systid) | Create an overview screen in the tool room to enable the changeover personnel to synchronize and plan their activities in an optimal way. | According to a master's thesis performed in the spring 2016 one of the losses in production was from bad timing of the tool changeovers. No system support exists today to optimize changeovers. | ? | AEL |  | 0 | On hold |  |  | REJECTED |  | 5784
17-05-2017 | Katarzyna Zelwor | [6 empty] | One Jeeves | On list M.O. to prepare distinguish for example by bold font, duplicate jeeves codes. | Customer is able to order same jeeves code twice at the same time. If it happens before preparation occurs, double preparation is made. | 3 | JH | 16 | 960 |  |  |  | REJECTED
| Barbara Misiaczek | [6 empty] | One Jeeves | We need to have additional 4 days included into LT which is calculated in estimator. Those days are need for administration, preparation, planning. Moreover if LT is f.e. 1.2 it should be round up to 2. MP: Value 4 should be set as a parameter | Offering Team is obliged to give an information about production LT on the offer. For this moment, system gives only MFG LT+BOM LT without extra days for preparation. | 5 | MP |  | 0 | yes |  |  | REJECTED |  | 5785 / Factory does not need this functionality any more
| Anna Reiter | [6 empty] | One Jeeves | Number of points to be adjusted in template "pallet spec" | Better customer satisfaction, lower number of errors | 4 | MP |  | 0 | yes |  |  | REJECTED |  | 5799 / Rejected - customer will not pay to external supplier
| Olivier Pedroncini | [6 empty] | All Asian companies current Jeeves | Block the possibility to remove order rows by using the "X" on order row level for all Asian Jeeves db | Wrong Backlog in Qlikview which doesn't give proper figures to management | 3 | EL | 24 | 1440 |  |  |  | REJECTED |  | First : investigations regarding the number of implicated order rows No development for this single feature but instead cleaning feature one per quarter in the datawarehouse
| Anders Lautmann | [6 empty] | ONE Jeeves | Add UNILEVER to ARIBA (orders) | Just do it :-) | 5 | CS |  | 0 | YES |  |  | REJECTED |  | 5834 Investigation regarding turnover and number of orders | YES , we are waiting for Unilever.
| Adrian Różański | [6 empty] | OneJeeves | Report for capacity in preparation | To calculate workload on daily basis, data must be gathered from the system which currently is only available to one jeeves support. | 4 | JH |  | 0 |  |  |  | REJECTED |  | Investigation if real time datas are needed (then QV could be used if datas from Day-1 are OK)
[9 empty] | On the list you can see the metod that is current and the one it should be changed into. I have marked the column in yellow that it should be changed to. |  |  |  |  | 0 |  |  |  | REJECTED |  | Closed by CS cannot see what is needed.
| Christer Sahlen | [6 empty] | OneJeeves | Default value of Incoterm (Halmstad) for all Swedish customers / Wait for discussion with Gosia and Christer | Part of Receiver pays flow | 4 | MP |  | 0 |  |  |  | REJECTED |  | Gosia put this point on hold
| Indri Lestari | [6 empty] | CJ (JKT) | User wants to have big text field in order1, the same way like for example in po | To increase visibility of these notes | 3 | MP |  | 0 | NO |  |  | REJECTED
22-06-2017 | Katarzyna Zelwor | [6 empty] | HLNet | Add Quotations to Article Search | My idea is to share quotes we make for one Sales Unit with other Sales Units. The aim is to give Sales Unit ability to find similar quote that has been done before and estimate to the customer. So generally, yes, I would like all valid quotes to be visible on hl net, but I think it would be good to have also an option not to show it (by specific status or field). | 4 | JH | 60 | 3600 | Move to Sales and ask for better justification. |  |  | REJECTED |  | 10/7: Use the offer report in QV instead /Kasia
2017-02-22 | Tymoteusz Glajcar | [6 empty] | One Jeeves | Add operation start and end to MO report |  | 4 | JH | 16 | 960 | YES |  |  | REJECTED |  | Betr: (report? MO combined? Julia confirm) Rejected by requester.
2017-02-28 | Rob Smith | [6 empty] | One Jeeves | Improve Kanban flow, multiple instead of single PO row | Save 4 hours weekly in HUB alone | 4 | BT |  | 0 | Investigate more |  |  | REJECTED |  | Christer to investigate, PO can not be updated asked UK if we can change flow so that SO update // C 15/5 Mail sent that just "this" request cannot be done BUT that we shall meet and se what other can be done as its a good saving // Christer | Partly YES
2017-03-22 | Bartosz Wowra | [6 empty] | One Jeeves | Orginal Blueprint field | to keep track if the drawning is changed | 5 | JH |  | 0 |  |  |  | REJECTED |  | Check Version handling 15/05 not useful anymore
2017-03-22 | Bartosz Wowra | [6 empty] | One Jeeves | Copy field Blueprint from estimator to item | to keep track if the drawning is changed | 4 | JH |  | 0 |  |  |  | REJECTED |  | 15/05 not useful anymore
17-05-2017 | Adrian Róźański | [6 empty] | OneJeeves | Create a possibility to copy (similar to copy table) selected rows/entire table in table format for mail/word documents + 1st top row.Currently there is only a string of spaces, tabs and letters/digits which changes appearance when mail is wider/more narrow in browser – makes it unreadable. | Business service sends hundreds of mails daily, informing departments and clients about m.o./item status which needs to copy essential info from system. To keep visual appearance business service makes screen shot which denies ability to copy data quickly from mail. | 2 | JH |  | 0 | NO |  |  | REJECTED |  | Not possible
29/12/2017 | Katarzyna Zelwor | [6 empty] | One Jeeves | LT calculation in Order1 |  |  | AEL |  | 0 | Rejected |  |  | REJECTED |  | Duplicate
2017-07-26 | Katarzyna Zelwor | [6 empty] | One Jeeves | Lead time in order row calculated for the proper quantity - request for change sent, discussed internally in IT. | LT depends on quantity of the standard items. We do not have any functionality to calculate it. This solution would save 80% of time of the planners who are checking it manually now. | 3 | PANO/AEL | 80 | 4800 |  |  |  | REJECTED |  | 15/03: to be invesitgated 10/7: Move functionality from estimator to order1 Can be another program? DW? Review another solution /Andreas and Solution architects. 07/09 kaze: yes, it can be another program. What is the decision? 23/10: need to be taken
8-6-2017 | Marcin Pianka | [6 empty] | OneJeeves | Additional texst field is missing on estimator's row - it should be similar to text between order rows in order1 | External text on quotation row is very narrow | 4 | MP |  | 0 |  |  |  | REJECTED |  | Rejected, 6187 will extend existing field instead adding a new one
12-06-2017 | Julia Homik | [6 empty] | OneJeeves | Possibility to sell KIT item from the facotry to hub, and ito 'unpack' in hub into several items. | It take a lot of time to prepare all the items and them process them in production process, JGP and so on | 4 | JH |  | 0 | NO |  |  | REJECTED
2017-07-25 | Justyna Bagniewska | [6 empty] | One Jeeves | Automatic booking of subcontracting MO |  | 4 | JH |  | 0 |  |  |  | REJECTED |  | MO not booked today ? Julia to check ..I talked to Hub team, the girl who reported it is no longer working. Other people don’t recognize it. You can reject it 😊 check with Kinga SZ JUlia respond
08/08/2017 | Bożena Paszkowska | [6 empty] | One Jeeves | It is necessary to include in Order Confirmation to customers who have VAT tax/ type set as ”S-inside EC goods (except Poland)” following information: | There are tax requirement to use 0% VAT. These two functionalities will allow us to apply a 0% VAT rate and avoid paying 23% VAT rate to Tax Office. Both of these funcionalities have huge impact on the Group liquidity. | 5 | JH |  |  | YES |  |  | REJECTED |  | 6335
22/05/2017 | Boguslaw Kuczynski | [6 empty] | OneJeeves | New tool for dispatch scanning process, Centiro | 1 FTE can be reduced if proper solution is implemented according to Boguslaw. | 5 | AEL |  |  | NO |  |  | REJECTED |  | Request not agreed from management, too costly. Excel based solution suggestion from Boguslaw. How is other HUB's working?
24/07/2017 | Tomasz Wieszyński | [6 empty] | One Jeeves | Add checboxes 'Manual Setup time' and 'Manual Qty Per hour' to operation | Usually operations values are calculated according to excel file and rules in the facotry. Sometimes due to material that is used the operation time is not standard and was filled in manually by preparation engineers. Users wants to mark operation where the values are not standard to not overwrite. Today when the operations time is not correct then the price is not right and the delivery date to customer may be wrong. These checkobxes are to mark operations that may look strange but in fact values are correct and no one should ovewrite them. | 4 | JH |  | 0 | Rejected |  |  | REJECTED |  | Not valid anymore
10/05/2017 | Boguslaw Kuczynski | [6 empty] | OneJeeves | Scanning for inbound delivery. No manual delivery should be possible. Only scanning and confirming bin location. | This would decrease risk of wrong inbound delivery. Automatic process with scanning, entering bin location and confirming. | 3 | AEL |  |  | NO |  |  | REJECTED |  | Barcodes needed on all bin locations. Reject for now
2017-07-26 | Kinga Szyguła | [6 empty] | One Jeeves | Adjustments to report 'MO Added Value' 1. For now there is only item spec. USers would like to see item desc too (as on the old report) 2. Add bin inventory balance to the report 3. Group rows for one item with several bins. | In Gliwice hub they stopped to use the report due to these three points. They use the old report because they have more information in there | 4 | JH |  | 0 |  |  |  | REJECTED |  | WHY not using Aotodo Picking list. Another MO report change is made in OTF: 6809 pano will check with Kinga Sz 15/05 reuqest not valid anymore
| Boguslaw Kuczynski | [6 empty] | OneJeeves | Picking route. Implement pick list sorting on bin locations based on picking route provided by Boguslaw | It would | 5 | AEL | [5 empty] | REJECTED |  | Email with explenation and image exist from Bogus to be used in feature. Add logistics Managers to discussion. Could be benificial to add in other HUBs. eWMS?
14/09/2017 | Ida Modigh | [6 empty] | Current Jeeves | We have a Crystal Report in Sundsvall Jeeves. It's in program xarla = Future Disptaches. In the report we can bring up orders dispatching between specific dates. When we created the report we did not use the PO ststus "goods in transit", now we have strated using this status. The problem now is that orders set in this status does not show on the report. We would like that orders set in status "goods in transit" also shows on the report. | We use this report both to plan dispatches in (China) and also check delivery follow up of our orders. SO its very important statisrics and anylses. | 4 | CS |  |  | NO |  |  | REJECTED |  | 01/03: soon SDL will join 1J, no new development should be implemented in CJ
20/10/2017 | Boguslaw Kuczynski | [6 empty] | One Jeeves | Pop-up in Olhucorl if 'txt on picking list'. Should be displayed when entering SO | Information is not visible until picking list has been printed. Ineffective. | 4 | AEL |  |  | ? |  |  | REJECTED |  | 6584 – Popup window for picking list text
2018-01-01 | Leszek Kwiatkowski | [6 empty] | One Jeeves | change invetory fields design to 5 decimal places | it is possible to pick material for more than 2 decimal places but it is not possible to see how much is left in stock and to do the stocktaking | 5 | Julia |  | 0 | YES but need to be disscus with Christer |  |  | REJECTED |  | 5546 According to OT 14/4 CS
2018-06-16 | Sabina Kozlowska | [6 empty] | OneJeeves | Estimator Calculation Polish Factory |  |  | AEL |  | 0 |  |  |  | REJECTED |  | Waiting for RFC /Andreas
2018-06-19 | Rob Smith | [6 empty] | 1J | Copy master button to copy BOM and operation localy as well as pricing calculations. | being more responsive in the item preparation will lead to less delays getting orders onto the system and ultimately improve service to the customer whilst reducing the impact to lead times | 5 | Pano | 20 | 1200 | Yes (IN LOGISTICS) |  |  | REJECTED |  | estimate time is only for copy bom and operation extra time needed for calculation process, need to be discuss on preCab if really needed 04/07: to be sent to Andreas and inclluded in Production CAB |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESO_Osbiv2tBs5YSXN8jKisB9UGNSLB20qRRRDmuP8CEfQ?e=SQ2ifL
2018-07-09 | Seraphie Tulasne | [6 empty] | 1J | Blueprint field update in AR program |  | 4 | AEL | 8 | 480 |  |  |  | REJECTED |  | 10/7: Communicate to Seraphie about other solution. Customer /Andreas
2018-07-10 | Michał Los / Tomasz Wieszyński | [6 empty] | OneJeeves | Alternative routing - We will use button for routing creation and after that we will change just one operation manually. | It will save us a lot of time because we won’t create all operations and all BOM components manually. | 4 | AEL | 16 | 960 |  |  |  | REJECTED |  | 10/7: Proposal to use GIFT program. Stephen to take this with Kasia. 07/09 kaze: next steps: gift training, gift access to be given.
2018-11-01 | Olivier Pedroncini | [6 empty] | 1J | Report of MO Differences | Indespensible and rationalizing. Manufacturing in HUB's currently have huge impact on the HUB pipe. This would improve the P&L accuracy. | 5 | AEL |  | 0 |  |  |  | REJECTED |  | book a meeting with Kinga L 16/05 Rejected, it was redirected to Group for global discussion connected with Value added flow in HUB |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B97652F5D-1B83-4414-9D7C-C4E4D968AC4E%7D&file=RFC%20-%20Report%20for%20MO%20difference%20justification%20-%20Olivier%20Pedroncini.docx&action=default&mobileredirect=true
2019-03-12 | Kinga Szyguła | Julia Homik | Benno Eliasson |  | HL Display AB - Finance |  | R19.7 Jul | 1J | Add field in XTI program (page HL Entry) showing current quantity from valid calculation. | Avoiding of MO diffrences, better control on MO | 4 | KIPA | 8 | 480 | YES | 21/05/2019 | July/August | IMPLEMENTED | 7542 | 20/05/2019 KIPA: this RFC concerns production area but should be disscused on CAB finace due to global investigation done by Lars S and Jessica heading to improvments in VAle added flow in HUB's 28/05/2019 KIPA: RFC was approved on CAB finace 21/05/2019 but it is strictly connected with productiona rea so it was moved from finance to prod - agreed with Christer. Kinga L informed Kinga Sz about decision and way of handling 11/06 F7542 created by pano |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdAxG58DNp5Olwtc5xLFiW8BmecVA5jaJbbzEitBJdTBbg?e=p4PvSM
2019-05-30 | Kamil Saczka | [6 empty] | CJ | Pre-Study for Upgrade ERP System in China Factory in Suzhou | Current ERP system is obsolete and most of the modules are not supported. Global HL development is more expensive because of the old architecture, sometimes some installations are not possible to be deployed. | 4 | KaSc | 40 | 2400 | Closed | 24/09/2019 |  | REJECTED |  | This is not an implementation of the project. This is just a start (pre-study) in order to review the current setup, estimate and recommend different alternatives to management. 27/08 need to be check with Kamil and Lennart 24/09 nothing decided yet
05/04/2019 | Bartosz Wowra | Håkan Tjernberg | Christer Sahlén |  | HL Display Nordic | Costs info in comment |  | QV | Qlick View rapport is needed in order to get correct consumption data based on direct sales and sales connected to manufacturing items in hub. | Better accuracy in stock / sales data which helps to reduce stock value and improve on time delivery. | 5 | pano | 20 | 1200 | YES | 27/08/2019 | 2020-08-20 | IN PROGRESS | 7627 | 05/06/2019 impossible currently extract the data from Jeeves, ,manual work could take 1 day 23/08 Eazystock basic data improvement to help correct data, cost will be taken by Nordic HUB 17/07 ready to test 23/09 users still test and compare with IT query, but report is ready to release |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESDE9wnORwtCu_-DqsLmnKgBJZDOp-qqCTddo-1pR0YoZQ?e=zfKGGO
11/07/2019 | Katarzyna Zelwor | Magda Oczko |  |  | HL Display Gliwice Sp z.o.o |  | R19.8 Aug | 1J | MO report – print MO Combine The report „Manufacturing Order” should be translated to polish. | This is an issue for polish production team to understand English descriptions on the report. It would improve the efficiency if all production employees would understand a basic document they work daily with. | 5 | pano | 8 | 480 | Yes | 12/07/2019 | August | IMPLEMENTED | 7586 | 12/07/2019 feature created, waitng for translation |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUw_9TkrSftNmA3Lo950JiEB5X_k9GbW1R9y6afMZSAJHA?e=sSO42b
31/07/2019 | Jacek Szypulski/ Tomasz Wieszyński | Magda Oczko | Lennart Johansson |  | HL Display Gliwice Sp z.o.o | Costs info in comment | R19.10 Oct | 1J | “Extra1” field available in local Jeeves for modification. | It will save a lot of time because we will not have to enter the Master Jeeves. Save 5min daily per one department, it’s 25 min. Saving 105 hrs per year. | 4 | pano | 5.25 | 315 | yes | 27/08/2019 | Oct/Nov | IMPLEMENTED | 7626 | cost will be taken by Gliwice Factory |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUCD9fjXPRlEqTolzjEbqJ0B4qbJU3t-vXz3g04vcI6DyA?e=yE3p2Z
15/07/2019 | Agnieszka Irzykowska / Katarzyna Zelwor |  |  |  | HL Display Gliwice Sp z.o.o |  |  | 1J | Injection Molding quotation in the Estimator: - Estimator should calculate weight correctly - Estimator should calculate prices correctly when calculating by ”EOQ” (and ”Mixed calculation”) | Offers HB and offers IM would have the same format. Offers would be more clear and easier to understand by customers. Good archiving of offers. There would be no need to create few new Jeeves codes for few options of offer – offers would first be send in .pdf, then jeeves code would be created only for one option that customer would choose. | 4 | PANO | 24 | 1440 | investigation | 23/09/2020 |  | REJECTED |  | 27/08 involve in investiagtion UK, Gliwice 24/09 wait for Agnieszka I. and check mix calculation -next week and do test 16/12 finalize test till Friday; INC-11477 reported to ITHelpdesk 24/01: defect logged by Support 20/05: Pawel will check status of solution 01/07: INC-11477 + defect 2351 and estimate time of delivery Sept20 23/09 defect was installed, no need dev |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ef_sYzo3BwlIuHqPbxZEYU8BbnuZ17J3kJDzmsQ7k-7XNg?e=rQyefy
08/08/2019 | Dimitrios Wlachojorgos | Magda Oczko | Christer Sahlén |  | HL Display Gliwice Sp z.o.o | Costs info in comment | R19.10 Oct | 1J | Item calculation according new budget rate 2020 | Updated item valuation according to costs planned for 2020 | 5 | pano | 21.75 | 1305 | yes | 23/08/2019 | August/September | IMPLEMENTED | 7600 7638 | 19/08 cost will be taken by Gliwice factory |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWof8L5QanxPrOz22OZLT1oBSIeBxd7ur9ohmK9mpvIUag?e=EhLtg8
06/09/2019 | Katarzyna Zelwor | Magda Oczko |  |  | HL Display Gliwice Sp z.o.o |  |  | 1J | New value calculate in field MOQ | Costs and logistics process optimization. Due to change of items assembly and settings we need to change all the data in operations and logistics data. | 5 | pano | 16 | 960 | onhold | 16/12/2019 |  | ON HOLD |  | 24/09 wait for decision Magda O and Lennart 16/12 topic: decrease MOQ on items HB (order unique) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EStZVP7CGRxJjoql_TFMnxQBtyG18LmnQfv4-Q9LfB6Utw?e=OE5kjA
08/10/2019 | Agnieszka Dudek | Magda Oczko | Lennart Johansson |  | HL Display Gliwice Sp z.o.o | Costs info in comment | R20.01 Jan | 1J | Add field with item weight on MO | Possibility to verify the correct item weight at the production start | 4 | pano | 4 | 240 | YES | 05/11/2019 | 2020-01-01 | IMPLEMENTED | 7725 | cost will be taken by Factory Gliwice |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdyS7tEObzNKuV0IMD9qVR8BZcbCO71FOqJSWlLMt9wUQg?e=HSrkIZ
08/10/2019 | Agnieszka Dudek |  |  |  | HL Display Gliwice Sp z.o.o |  |  | 1J | Components created in Estimator for customer dummy (44619) should not be replicated / customer unique | Components should not be sellable items in other companies | 5 | pano | 16 | 960 | onhold | 14/01/2020 |  | REJECTED |  | 05/11/19 Kasia will check with Agnieszka 16/12 defect reported by Kasia, need to be check if have impact on current flow 02.01.2020 this is not a defect but standard function 14/01 potential issue, we could try find other solution without dev |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVrhHQhZ5EpMk9vUlQNgCeUBR3l9FEMOj_ZUVszAEHC8XA?e=99gg1l
02/10/2019 | Roseline Labrune | Stephane Carrivain | Lennart Johansson |  | HL Display France SAS (+ SASU DESIGN) | Costs info in comment | R20.01 Jan | 1J | Supplier Name indicated in MO document – External production To get the supplier name in all MO document printed when it’s an external production. | The preparation is different when the MO is printed at the added value dpt. The goods must be sent as soon as possible at the supplier. We win some time when it’s printed automatically on the document. | 4 | pano | 4 | 240 | YES | 05/11/2019 | 2020-01-01 | IMPLEMENTED | 7726 | 05/11/19 cost will be taken by French HUB |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ES99qqj-NaxCjmwPqR1flZgB0lMeJlxWChgN6t-AXYmI5g?e=f2qgae
03/12/2019 | Aleksandra Kurzak | Magda Oczko | Lennart Johansson |  | HL Display Gliwice Sp z.o.o |  | R19.2 Feb | 1J | We need situation when all components which are in MO on the preparation list will be light on red. Now we have situation when underlight components on MO are in status “MO to be prepared” and we need to develop this on status “partially to be prepared". | We will be more flexibility to plan new big project orders. We will be able to use possibility which gives us Jeeves with but now we can’t use them without this improvement. We will be more customer friendly. There is a risk that we ‘’’will order a material that we don’t need. | 4 | pano | 6 | 360 | yes | 14/01/2020 | 2020-02-20 | IMPLEMENTED | 7790 | 16/12 Kasia will check with Magda to accept cost and Pawel will check est DEV time |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdF657jDWn5EnqfHB-pxvZYBOZZ-_wwE5tyYUv3Tsp8gPQ?e=1APFhc
18/12/2019 | Dimitrios Wlachojorgos | Magda Oczko | Lennart Johansson |  | HL Display Gliwice Sp z.o.o |  | R20.04 Apr | 1J | Add in program XTI fields with the login of person who flag MO as completed with the date and time of this operation. | Currently each Team Leader can flag orders as completed (even from other department). When we try to solve problem with the MO/ MO differences after closing this MO we cannot check who flag this order and is responsible for this. We also can’t check how many MO’s each person flag/ on which shift etc. We don’t have basic field which give us info who make mistakes and who needs our help with better understanding the process and the result. | 4 | pano | 4 | 240 | yes | 14/01/2020 | 2020-04-20 | IMPLEMENTED | 7789 | cost will be on Gliwice factory |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWAm5qHdvDlFl3uqVwHyTQsBqgjYlbp0pUtAHhwlLjulgw?e=2zPBBW
22/01/2020 | Patryk Baczek | Magda Oczko | Lennart Johansson |  | HL Display Gliwice Sp z.o.o | HL Display Gliwice Sp z.o.o |  | 1J | Add to item calculation details on each operation to could compare eg. Calculation No. 191 with calculation 201 on basic level. | Currently we waste a lot of time when we want to investigate what changed between two calculations- if we see the difference is on material we see all needed information. But if it’s in operation we have a problem. It contains people in controlling, offering, preparation and also Factory Project Managers. | 4 | pano | 16 | 960 | YES | 20/05/2020 | 2020-11-20 | IN PROGRESS | 7999 | 10/02 Stephane will send query prepared by Lars, send details to Stephen M regarding this topic 12/05 Query not fit to historical data required by Gliwice |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ed9YGzdRkX9FuXp_BFPocYsBjZiAnY4Kr-S3-XsDcRcwhQ?e=aClAPL
0
23/01/2020 | Roseline Labrune | Stephane Carrivain |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | Update automatically MO in “fixed planned” status when the PO is put in ‘order acknowledgement’ status. (adjustment to existed function) | The query is used every day in order to update the status of the MO - If this new process is accepted, we will save time at the transport dpt and the sales assistant will see more quickly the delivery date confirmed in the planning list. | 4 | pano | 10 | 600 | investigation | 14/10/2020 |  | REJECTED |  | 10/02 send details to Stephen and Kasia 20/03 positive feedback from FRA and UK, wait for Gliwice 20/07 info sent to 1210/1810 also 21/09 reminder sent to 1210/1810 14/10 14/10 Stephane advised to reject this request |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXBVIrenbYBEqp8VNc9XeBMB1018c2y6QM4PE7qjnret2g?e=7djYTO
05/02/2020 | Stephen Mepsted | Stephen Mepsted | Lennart Johansson |  | HL Display Harlow Ltd | HL Display Harlow Ltd | R20.10 Oct | 1J | Kanban Flow on 1J needs to be the same as the normal PO flow |  | 4 | pano | 8 | 480 | YES | 10/02/2020 | 2020-10-20 | IN PROGRESS | 7851 | 10/02 check dev hrs and cost will be taken by Harlow, update Stephen M. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVjUs_efTU1KvlYiWIW0ayQB5jkTbjpf9O-pvq-9cg1IVw?e=0tOPxX
17/02/2020 | Mateusz Nicota | Magda Oczko |  |  | HL Display Gliwice Sp z.o.o |  |  | 1J | At present Gliwice factory use quality blocked inventory batch for products which are stored outside Gliwice factory. By blocking goods on separate batch system generate requisitions and orders as a goods needs to be produce or ordered. We need new status for example external warehouse thanks which system will be aware that new manufacture or purchase orders are not needed. | Thanks that feature we will improve time for manufacturing and purchasing orders cancellation, eliminate mistakes made by manual management. This functionality can be used within all factories and hubs . | 4 | pano | 16 | 960 | investigaation | 16/03/2020 |  | INVESTIGATION |  | 16/03/20 schedule meeting with full explenation of flow in Gliwice 12/05 meeting scheduled on 18/05 18/05pano: we are testing existed solution in Jeeves with new batch and basic settings 10/08pano: Pawle will back with conclusion of investigation 23/09 Pawel need more time to check it |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EZm_vEAcsq5KgpKKOjUvhpMB2Wek-JEhGGp0er1ZQjNs9A?e=W52bg4
06/03/2020 | Stephen Mepsted | Stephen Mepsted | Lennart Johansson |  | HL Display Harlow Ltd | HL Display Harlow Ltd | R20.11 Nov | 1J | Fixing a BIN (Kanban) to an item so that item can only be located in 1 BIN and no other bins can be used. | Full Automation can be fixed for Kanban | 5 | pano | 16 | 960 | yes | 16/03/2020 | 2020-10-01 | IN PROGRESS | 7952 | cost on Harlow factory |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVWnb74TJ45Pt4vlEGjziGQBKlnh9UywFRH0jHh1GEXbAQ?e=AO3Nb0
12/03/2020 | Patryk Baczek | Magda Oczko | Lennart Johansson |  | HL Display Gliwice Sp z.o.o | HL Display Gliwice Sp z.o.o |  | 1J | We would like to resignate of “order unique” flow in our factory (manufacture to order). Current flow makes a lot of problems especially in financial reporting (cost of production are booking in the moment of closing MO, not in moment of real material picking etc. which has impact of our financial results etc.), stock management and production reporting (order unique has specific location in warehouse based on reservation of materials for specific order, it makes us a lot of problems when we need to move something from this virtual location etc. because everything is blocked). | Easier financial reporting which will be based on simple criteria, less problems with stock management. | 5 | pano | 44 | 2640 | YES | 20/05/2020 | 2020-11-01 | IN PROGRESS | 7998 8139 | 16/03 Christer push Jeeves to answer on promised solution; Katarzyna will prepare team for more complex investigation, involve factories in preStudy 20/05 developement around 20hrs 08/10 additonal fetaure need to cover adjustment and secure similar flow like in unique flow |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWMuk6DEUWVCiESlRor3VEwBdF7ycclIav6ML2-MFGqBaA?e=6BmlnB
30/06/2020 | Agnieszka Dudek | Magda Oczko | Lennart Johansson |  | HL Display Gliwice Sp z.o.o | HL Display Gliwice Sp z.o.o | R19.10 Oct | 1J | Adding a field with the number of the quality template on report MO. | Less mistakes made by operators. Easier employee training Less quality complaints | 5 | pano | 6 | 360 | yes | 23/09/2020 | 10-2020 | IMPLEMENTED | 8121 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ET3hzdWltmlCjN7AsK1vFAEBQitm7YOZnflx7Uq9fUY7RQ?e=oUuPDh
02/07/2020 | Dimitrios Wlachojorgos | Magda Oczko | Lennart Johansson |  |  | HL Display Gliwice Sp z.o.o | R20.08 Aug | 1J | We need to add additional functionality in terms of discounts setting on appropriate ProductGroup level in Jeeves: | Adequate pricing policy Sales price control on a detailed level Sales volume development | 5 | pano | 16 | 960 | yes | 02/07/2020 | 2020-08-20 | IMPLEMENTED | 8050 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQHhucu33P9Opn3xcUjn6wQBly0YK2wTaIubKfQ_lGMjhw?e=0ehnvv
2020-08-13 | Katarzyna Zelwor |  |  |  | HL Display Gliwice Sp z.o.o | HL Display Gliwice Sp z.o.o |  | LOCAL APP | Replace/upgrade Plattnet | Constant problems, we need a more stable solution | 4 | Marika |  | 0 | investigation | 23/09/2020 |  | INVESTIGATION |  | 18/09 if we find 8hrs for investigation we could advice optimal solution demo will be presented by UK with new software 25/09 application should be more automtic than UK used it, similar to Plattnet; Chirster will check in source |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Production/RFC%20Plattnet.docx?d=wb6f1eaeb227d4401a3787cfe65a30fd1&csf=1&web=1&e=oC4yO4
03/09/2020 | Hakan Tjernberg | Håkan Tjernberg | Lennart Johansson |  | HL Display Sundsvall AB | HL Display Sundsvall AB |  | ERP2 SDL | We have a lot of our customers requesting additional labeling on the products they are buying from us. Tesco and SES are close examples. To be able to handle this, we need a possibility to design and print out customer designed labels. The printouts needs to be connected to items or orders in Jeeves to have an automated process to get the print-out for customer labels together with normal production labels. | • Increasing customer demand for special designed labels, especially from large customers • Help us in the work to get “easy to do business with” • Higher quality due to an automated process. • Less administration | 5 | pano | 28 | 1680 | yes | 23/09/2020 | oct/nov | IN PROGRESS | 8134 | 18/09 customize label in path: 16hrs for logic in Jeeves and template label 8-12hrs for label |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ETzCK8mdjQJDlqrNpgUrtUsBLJYIgcegPF0i8UQz50Gasg?e=Zb7rsY
10/09/2020 | Katarzyna Zelwor | Joanna Rosół | Lennart Johansson |  | HL Display Gliwice Sp z.o.o | HL Display Gliwice Sp z.o.o |  | 1J | Add a column “part description” in item BOM | Needed for the proper production planning vs. capacity during high season | 4 | pano | 6 | 360 | yes | 23/09/2020 | nov/dec | IN PROGRESS | 8133 | estimated time is 6hrs beacuse add function not movinf the field field 23/09 check if process is relevant for other units |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQvMkjKMb0JJrJlkFbDljzUBJzdYcWgkJ_eIBCtNezAFAw?e=05QtHB
11/09/2020 | Christer sahlen Erik.Sjoblom | Håkan Tjernberg | Lennart Johansson |  | HL Display Sundsvall AB | HL Display Sundsvall AB | R19.9 Sep | ERP2 SDL | Change in desing on shopfloor | More effective view for Operators | 5 | pano | 8 | 480 | yes | 23/09/2020 | 2020-09-01 | IMPLEMENTED | 8113

## Supply Chain
Process Leader |  | Lennart Johansson
Business Coordinator |  | Paweł Nowak
Date | Requested By | Authorized By | Approved By | Business Consultant | HL Unit | HL Area | Release | Product | Description | Justification | Prio | Added By | Est Dev (hrs) | Est Cost (EUR) | Decision | Decision date | Est Deliv Date | Status | Feature ID | Comment | Cust notified | RFC Link | Approved Date
| Caroline xu | [6 empty] | One Jeeves | We need a warning message when doing receiving in program: benilev without PO acknowledge. | We need this function to force BSO/CSO to confirm the order before receiving so every PO would be followed timely. | 5 | Pano/ALHU | 24 | 1440 | YES |  | 24/09/2018 | IMPLEMENTED |  | 5022 | Sprint 109
15-1-2018 | Pawel Nowak | [6 empty] | One Jeeves | Investiagtion of flow Collective invoice and extend for bigger invoices | Secure flow invoices in portal Tieto, to avoid problem with stuck invoices or mismatch rows between invoices | 5 | PANO | 6 | 360 | Yes |  |  | IMPLEMENTED |  | 6708
12-02-2018 | Jolanta Basiaga | [6 empty] | One Jeeves | To convert supplier LT from calendar to working days replicating item from Factory to local companies | We need to convert calendar days to working days when we migrate new item from Master data to local company system. Conversion rate which should be applied is 5/7 i.e. LT in factory=18 should be converted to LT=18/7*5=12,8~13 in the hub | 5 | PANO |  | 0 | Rejected |  |  | REJECTED |  | After investigation factories said that use working days.
27.02.2018 | Boguslaw Kuczynski | Małgorzata Stasierska | Lennart Johansson |  | HL Display Polska SP.zo.o |  | R5.14 Dec | One Jeeves | Create Proforma for Aland Islands in 1810 | Additional area for existed Proforma | 5 | PANO | 12 | 720 | YES |  | December | IMPLEMENTED | 6824 | 6824 25/06/2018: rejected beacuse of move Nordic to another unit 12/12/2018: reopen and decide to release |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ee3AYWbn6OdHjfxC1c8L0z8B_GUjbL5WXpQv25sGS1YrJQ?e=m6NgGG
28.02.2018 | Boguslaw Kuczynski | [6 empty] | One Jeeves | Change mark on Pickig list for Early dispatch "E" instead Y | "Y" is already cover different field Fixed delivery date | 4 | PANO |  | 0 | Rejected |  |  | REJECTED |  | user knowledge
2017-10-18 | Patrycja Slusarek | Magda Oczko | Lennart Johansson |  | HL Display Gliwice Sp z.o.o | Factories |  | One Jeeves | Pro Forma invoice for Gliwice Factory | This is for customs purposes and they have previously created manual pro forma invoice. They are also requesting additional functionality in the OLHUCORL | 5 | AEL | 24 | 1440 | YES |  |  | REJECTED | 6839 | F6839 25/06/2018 waiting for users decision
02/03/2018 | Malgorzta Stasierska | [6 empty] | One Jeeves | Automatic change the Dispatch method in order1 program according to the number of rows in one order. | At the moment this needs to be done manually from customer service. This is a) bad as it is one point more they need to think about, b) takes some additional time in entering-process and c) causes troubles in HUB when customer service forget to change the dispatch method (which happens often). If we implement this feature Customer Service and Hub will be more efficient. | 4 | Pano | 20 | 1200 | YES |  | 24/08/2018 | IMPLEMENTED |  | F6861
13/03/2018 | Jolanda de Vis | Stephane Carrivain |  |  | HL Display France SAS (+ SASU DESIGN) | West |  | One Jeeves | Possibility to overwrite datas from factory in case of Drop Shipment | Extend feature 6604 to allow user to change date on header, to safe time,not do this row by row | 4 | pano | 24 | 1440 | ONHOLD |  |  | SENT TO PROJECT OFFICE |  | F6859 status Onhold 07/11; new project DS to be concern
20/03/2018 | Aurelie Picou | [6 empty] | OneJeeves | Removal of required purchase in HL Planning list | This line wasn't used to be in their old jeeves and is giving them a bad overview. They currently manually remove these rows. | 4 | AEL | 16 | 960 | YES |  |  | IMPLEMENTED |  | check parameters first 26/09 Erwan will contact Aurelie to test solution of Jeeves
19/03/2018 | William Elis | [6 empty] | OneJeeves | Make visible field HLBuyer in xarla from supplier level | Currently the standard report provides all requisition and there is no option to sort this list by buyer, so each buyer receives a copy of the list and has to search through the list for the items that they need to order manually. | 4 | pano | 12 | 720 | YES |  |  | IMPLEMENTED |  | 6886 created EL : has been release in R5.7
21/03/2018 | Maja Ostrowska | [6 empty] | OneJeeves | Manual LT in HUB 1810 | LT has huge impact on stock level, is one of the most important/significant driver. LT define booking horizon for each items. There is group of items which stock management works differently than by standard requsition and we would like to have possibility to have shorter booking horizon what is possible only reducing LT in the system. | 5 | PANO | 32 | 1920 | Yes |  | 24/08/2018 | IMPLEMENTED | 7052 | F7052 created |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdBrq6zdusBHod4PcPe7PAkB5MVoEK71I34YI4-4k_jQfw?e=cGt6rk
21/03/2018 | Maja Ostrowska | [6 empty] | OneJeeves | Unblocking sales order only by warehouse team after Picking list was printed in 1810 | Request from 1810, at the moment sales support receive warnning or blocking order and warehouse just email. They wish decide if unlock order is avaible from their perspective not sales support | 4 | pano | 40 | 2400 | to be confirmed with Maja |  |  | IMPLEMENTED |  | duplicate of action 27
| Laurence Lakafia Arnaud Pichonnière | [6 empty] | 1J | Post closing sales field 1/ Not on correct Tab in order 1 (should be moved to HL Entry 2/ To be displayed on olhucorl + fr picking list template | Information needed to be transfered to Warehouse staff to avoid sending goods that should not suring end of month period | 4 | EL | 6 | 360 | YES and On Hold ;) |  |  | IMPLEMENTED |  | 6887 12/04: point 2 sounds resonable and can be implemented. Point 1 to be discussed with Marcin P during next CAB meeting EL : Has been implemented in R5.7
12/04/2018 | Laurence Lakafia | Stephane Carrivain |  |  | HL Display France SAS (+ SASU DESIGN) | West |  | 1J | Delayed orders management improvement As soon as a PO is delayed : For ICT factories an automatic mail is alerting the procurement dpt (with po nr, item, delayed qty, new delivery date) This is not enough. This functionality must be extended : For ICT, EDI, External suppliers, such mails need to be generated as soon as the PO has status 25.Order Acknowledged Moreover, this mail must be sent to sales support impacted by this delay (not only the purchase dpt, but also sales) |  | 5 | EL | 16 | 960 | use Jeeves standard functionality NO | 09/01/2019 |  | INVESTIGATION |  | Erwan contacted Jeeves for new development Lasse Svensson has ansered that Workflow module can be used 09/01 request with expertise will be send to Jeeves 18/03 waiting for feedback from Jeeves 04/06/ we had meeting with Jeeves and we talked about all request regarding ICT/DS flow, they promise back with feedback about possibilities in Jeeves
12/04/2018 | Laurence Lakafia | [6 empty] | 1J | Unbooking of order rows moved from "Entered/Entry in Progress" to status "Preliminary" | As soon as a Sales Order is moved from Status “Entry in Progress / Entered” to “Preliminary”, an automatic unbooking of corresponding order rows must be done + a warning message should be displayed to the user informing him about this unbooking | 4 | EL | 12 | 720 | YES |  |  | IMPLEMENTED |  | This can be a reason of overbooking in all companies in 1J F6912 EL : Has been released in Prod with R5.7
12/04/2018 | Stéphane Carrivain | [6 empty] | 1J | Overbooking after Stock take adjustment | Jeeves Node in xinvj + Query is existing to provide items affected by overbooking. This is not enough, the system should also : • Unbook automatically all overbooked items (first unbooking the most recent order rows till the most oldest order rows) • Alert through email the sales support concerned (picking list printed or not) + same mail to the warehouse manager (so that the picking list can be collected and destroyed) + remove the PL print date | 4 | EL | 24 | 1440 | YES |  | 24/08/2018 | IMPLEMENTED |  | F7038
12/04/2018 | Stéphane Carrivain | Stephane Carrivain |  |  | HL Display France SAS (+ SASU DESIGN) | West |  | 1J | Change of Items status by the factory / hub | As soon as an item status is changed and is related to an active pricelist, an automatic email should be sent to sales dpt alerting about such items status changes | 4 | EL | 24 | 1440 | rejected |  |  | REJECTED |  | From West project action list : When items status is moved from Sellable to Discontinued/Obsolete and item belongs to customer pricelist 29/06 should be escaleted to Peder (StCa) 02/10 PM provide list of items 20/12 communication works well,close request
12/04/2018 | Stéphane Carrivain | [6 empty] | 1J | Booking horizon improvement | As we know, the automated booking is working fine according to current rules : Booking horizon according to Item Lead Time + Safety window Purpose of adjustment : Booking routine using as Booking horizon a fixed booking horizon (which would be setup in a JVSP and adjusted each month). Example : 01/04 : setup of the booking horizon till the 06/05 01/05 : setup of the booking horizon till the 06/06 01/06 : setup of the booking horizon till the 06/07 01/07 : setup of the booking horizon till the 06/08 Etc… But still keep as priority, the creation date of each order row. | 5 | EL | 24 | 1440 | YES |  | 24/07/2018 | IMPLEMENTED | 6995 | investigate the solution, how to hande this F6995 created with description of the solution |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/HL%20IT%20Change%20Request%20Form%20-%20Booking%20job%20improvement.docx?d=w1268fdbebd954be48a355d3d8b2c1a8e&csf=1&e=Qlrsbx
24/04/2018 | Malgorzta Stasierska | [6 empty] | 1J | Additonal template Proforma for different countries in 1810 | Adjust template report with address depends of country | 5 | PANO | 8 | 480 | Rejected |  |  | REJECTED |  | to be confrimed with Finance departament not need anymore,beacuse of HUB movement
25/04/2018 | Stéphane Carrivain | [6 empty] | 1J | Manufacture items book against Sales orders | Adjust standard include manufacturing items and safe time | 5 | PANO | 20 | 1200 | YES |  |  | IMPLEMENTED |  | F6934
25/04/2018 | Malgorzta Stasierska | [6 empty] | 1J | Automatic email notification after Clear with shortage balance list of items | To notify Warehouse about shortage on stock and make efficient rebooking bins on order, that will avoid overbooking on items | 4 | PANO | 24 | 1440 | YES |  | 24/08/2018 | IMPLEMENTED |  | Excel File F7037
25/04/2018 | Maja Ostrowska | [6 empty] | 1J | Transfer via centiro information to Johan Weiss regarding special service | AT SU has a demand to have possibility as in the past in old jeeves to choose special service from forwarder and that iformation should be sent directly to Johan Weiss | 5 | PANO | 12 | 720 | YES |  | 24/09/2018 | IMPLEMENTED |  | F6953
26/04/2018 | Stéphane Carrivain | [6 empty] | 1J | Possibility of adding the creation date of the PO in the planning list (Field CreDtTime) | It would help to check if creation date of the PO is consistent vs creation date of the SO (Data already existing in the planning list) | 4 | PANO | 4 | 240 | YES |  | 24/08/2018 | IMPLEMENTED | 7089 | pano: Need to be discuss again,it's no Jeeves issue but design changes Alt 2 : creation of new filed in the planning list containing either : - so row creation date - po row creation date - mo row creation date Feature 7089 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdtAFVT3vtJGu7MzkUgdbfABnQpY1_BBIlpK72Cd2XyuLQ?e=2gTERc
21/05/2018 | Malgorzta Stasierska | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | 1J | Adjust functionality of email/warning message regarding changes on sales order | Sometimes we are processing orders twice (old picking list and new picking list) and finally we have to put back to stock one picking (old one). Also there is a risk that we will send wrong qty to final customer because SU didn’t inform us about change of qty. | 4 | PANO | 24 | 1440 | rejected |  |  | REJECTED |  | Discus at Pree CAB 29/06: investigate how many pop up message are on sales order 08/08 check with Marcin (vacation), check messages and how many we have of some conditions (Pawel and DEV team) 20/08 list send to Gosia,Erwan 26/09: should be discuss on Sales preCab 02/10 separetly meeting needed with SU and Marcin.Pawel Erwan 20/12 discuss comon process with SU |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Eas7Rp7FTIxCj95Y5txwFvsBAul5lfsAKEnTxXPCQ3P_LA?e=OCM6BE
21/05/2018 | Stéphane Carrivain | [6 empty] | 1J | Reasonable usage of item status | If items are moved from sellable to discontinued, PO won’t be placed, then customers won’t be delivered. CSO do not be able to change status for only both cases: Sellable to another status (important as if moved into centrally prepared, SO registration and PO can’t be placed), and Discontinued or to be discontinued to sellable Provide a description of driving forces for the change being requested. | 3 | PANO |  | 0 | Reject |  |  | REJECTED
08/06/2018 | Maja Ostrowska | Małgorzata Stasierska | Lennart Johansson |  | HL Display Distribution Center Europe sp zoo | Central |  | 1J | Stock protection tool | Current forecast process demands solution which will protect Sales Units which provide forecasts. Some of items are regularly forecasted by some Sales Units and these Units demand availability for that products in accordance to provided forecasts. Now there is no such solution and HUB purchase products only based on forecasts for group of items with very long LT and very often occurs that SU which do not provides any forecasts use stock built by HUB for particular Sales Units. Due to that fact there is a need to develop solution which will protect available stock and reserve it only for SUs which are allowed to use it. | 5 | ERLA | 60 | 3600 | onhold | 18/03/2019 | March/April | ON HOLD | 7276 7327 7331 | 29/06 check EasyStock solution 04/07 : Lennart approval is needed 29/08: escalate to Lennart 26/09 decison should be taken with Lennart during next preCab 02/10 common rules need to be placed 12/02 after meeeting with Maja,we found solution of improvement 25/02 delay of implementation of lack business impact 11/03 move topic onhold, low piority according to new piorities in HUB and move Noridc units |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EfrNa3ULuUdKuxb1jiLJlZsBhn8n5R1X1bWvQaz41UWc8g?e=haCYce
12/06/2018 | George Xu | George Xu | Andreas Astgard |  | HL Display Shanghai Co Ltd |  | R5.14 Dec | 1J | For threshhold block mails, we would like to show more information of the PO, at least the Jeeves number and description of the products we want to purchase, unit price and total price | Otherwise, every time when I receive this mail, I will need to log on to One Jeeves to check for these information which costs time and also it’s very inconvenient when I am travelling and no access to Jeeves I want to have more information on the automatic reminding mail as I travel a lot and if I can find what are those items, qty, price concerned for that PO, it can help me to judge and approve or question with no delay to the order. It’s beneficial for me and I trust no harm to others. | 3 | Pano | 16 | 960 | Yes |  | end of this year | IMPLEMENTED | F7172 | 17/08 let's concern this once again it can only improve the level of information and improve efficiency of users approving PO through mail 02/10 F7172 created |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ec4sr_jKACdOkU35bAZ7dJ0BeGsAYWt_3YfVtS2b2ikxXw?e=NYrRsW
19/06/2018 | Rob Smith | [6 empty] | 1J | Copy master button to copy BOM and operation localy as well as pricing calculations. | being more responsive in the item preparation will lead to less delays getting orders onto the system and ultimately improve service to the customer whilst reducing the impact to lead times | 5 | Pano | 20 | 1200 | Yes |  | 24/09/2018 | IMPLEMENTED | 7090 | estimate time is only for copy bom and operation extra time needed for calculation process, need to be discuss on preCab if really needed 04/07: to be sent to Andreas and inclluded in Production CAB 10/7: OK in Production pre-cab /AEL 30/07: F7090 created |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXM7C9vGaqZCn9z0Z5hsyWEB1FToAXKKdSXvdU9p9pN05Q?e=qTdn3g
20/06/2018 | NORDIC HUB AL39 /all/ P. Mazurewicz | [6 empty] | 1J | Planning list adjustment : 2 informations need to be added on the screen : - Tickbox Fixed Delivery Date from order row - Requested Disp Date | It is about streamlining the process to achieve operational excellence, because at the stage of ordering we will know that the customer wants the goods on a specific date - we can pass this information to the supplier at once. | 4 | PANO | 16 | 960 | YES |  | 24/08/2018 | IMPLEMENTED | 7089 | F7089 created |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESwL5KuTdxtDlniOHG7tm2wBAddyrWtCmvnxFU-8ZnhisQ?e=3cMzBp
25/06/2018 | M.Stasierska | [6 empty] | 1J | Logs on booking done in system + adjust QV report MTO | This is necessary to be able to check who took something from other orders. For now we have situations where Sales Units accused each order that someone have stolen goods from their order and there is no possibility to track and prove it. | 4 | PANO | 40 | 2400 | YES |  | 24/09/2018 | IMPLEMENTED | 7091 7092 | 30/07: F7091 created F7092 created to cover QV report |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ETmxuv6GczlPhBFh4IjbJxcB_kYL_sBtdkd35nVTqmc2zA?e=bnCBIW
27/06/2018 | Nathalie Constantin | Stephane Carrivain | Lennart Johansson |  | HL Display France SAS (+ SASU DESIGN) | West |  | 1J | Add on the sleeping stock QV report : - Last Received date (ars.seninlevdat) - Last Dispatch date (ars.senutlevdat) - First receipt date (not sure such field is already existing 1J) - First Dispatch date (not sure this field is already existing in 1J) | Will allow to calculate aging of the stock | 4 | ERLA | 16 | 960 | YES |  | 22/10/2018 | IMPLEMENTED | 7131 | check the querry option 20/07 waiting for Stephane 31/08 Stephane provided the Query used in CJ (company 1600). It is of course out of question to recreate such query in 1J, therefore, these 4 fields need to be added to the exisitng Sleeping stock report F7131 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/Logistic%20%26%20Procurement/HL%20IT%20Change%20Request%20Form%20-%20Sleeping%20stock%20QV%20report%20imporvements.docx?d=w2eb5aa4a97ba4ad3906da71225b4850c&csf=1&e=ppn2AZ
2017-03-03 | Stephen Mepsted | [6 empty] | One Jeeves | Delivery date issue on picklist and order. Promised delivery date is taken from order header and not order row | See actual promised delivery date on order row level | 4 | AEL | 12 | 720 | yes |  | 24/09/2018 | IMPLEMENTED |  | SRX12148: Andreas to investigate with HUB Managers. MOVED FROM PRODUCTION TAB 04/07: functionality implement for West can be use it for UK,Nordic F7105 created
02/05/2017 | Boguslaw Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Comparison of newly added goods and picking list | Virtually sending goods but physically not. Problem is that inbound can work and put in goods while pickers don't see on picking list. 50 % of claims used to be because of not sending complete order | 4 | AEL | 40 | 2400 | rejected |  |  | REJECTED |  | Christer, Help? It happen because for example we are printing Picking for order with status- Part delivery allowed (11:00) and after that (11:10) our Inbound dep is booking item needed for this order, later Order picker while closing process is taking all rows and between them there is a ‘new line’- fully booked. I know that this we should to check but for ‘big’ orders it will take some time. 23/8: Take a meeting on arrival Entry and explain use of that and that you then can see that goods are in WH but not on bin./ 04/07:schedule meeting and find reasonable solution 29/08 Pawel and Erwan will contact Emilia to review process 02/10 check with Bogus 20/12 Reject, problem was with dates on Noridc SO |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ea4FqFIEiApAmzLU_JMVr9EBq0wF-rhIQEk7ANxnyWPiew?e=hmtzTV
05/04/2017 | Boguslaw Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Journal closing option | Avoid validating big discrepancy in the system | 3 | AEL | 32 | 1920 | yes |  |  | REJECTED |  | Waiting for Tomek's reply. Reject if no easy fix is possible since this sounds more process related. Check what has been prepared for Area West then look if more "DEV" Needed EL : same issue in Area West. Inventory journal can be closed generating a big discrepency. Idea would be to block stock take journal update above a certain value generated by a single item (only allowed users could close such journals, and comment should be mandatory to be able to explain the discrepency) 02/10 F7173 created 17/12: After consulation with users we agreed to reject this request
09/06/2017 | Boguslaw Kuczynski | [6 empty] | One Jeeves | New pop up window or fee row on right site of order to eliminate not released fees Only for Polish Sales company ! | Lot of extra administrational work and less money to HL due to missed fee to customer | 3 | AEL | 24 | 1440 | investigation |  |  | REJECTED |  | Waiting for confirmation from Marcin P about what kind of indication that can be used to alert about fees in the system. We need more facts about what kind of fees we talk about for Polen Company. 04/07: possible to add type credit order to button Preperation date to exclude from the list to print PL plus schedule meeting with Bogus 08/08 Request to stop print PL for Creditr orders will cover that point from position 60 29/08 cover by point 60
04/07/2018 | Malgorzta Stasierska | [6 empty] | One Jeeves | We would need to have a change regarding functionality of “Capacity control tool”. For now it works in this way that if SU has big order composed of numerous rows and capacity-warning message appears, it appears so many times as number of order rows. We would like to change that functionality in that way that if we have order rows schedule in the order for the same preparation/dispatch date than pop up is appearing only once if capacity limit is closed to be reached or exceeded. If however order has more than one preparation/dispatch date than pop up should appear so many times as number of different dates (if applicable of course) | This is to reduce work in Back offices | 4 | PANO | 20 | 1200 | YES |  | 24/09/2018 | IMPLEMENTED |  | 04/07: to check IT solution how to implement F7104 created |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWGKklvq1rBJhn68lFHwbe0Bute6DYE_uhJx4j1iaIJi8Q?e=HKSAKJ
04/07/2018 | Emilia Hermio | [6 empty] | One Jeeves | Update on all Nordic Freight Charge matrixes -> price increase of 10% | General request from Group level to increase profit on freight, effective from 1st of August | 5 | PANO | 4 | 240 | YES |  |  | IMPLEMENTED | 7054 | F7054 created, installed on Prod 31st July |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeTHvCyrkdFGnnp5G4zFqlcBVfAEaXS0lSPQRonKodrPoA?e=gc0Exm
29-05-2017 | Malgorzata Stasierska | [6 empty] | One Jeeves | Pick list restrictions with advanced payment - Add warning when using advanced payment and exclude orders without paid invoices on picking list | A lot of orders gets prepared today without invoice payed. To avoid operators to place uneccassary work and have goods batched up without being able to be dispatched we want to have a warning displayed when printing pricking list for unpaid invoice if printing for 1 order. If batch printing "picklist to date" we want the report to exclude unpaid orders | 4 | AEL |  | 0 | investigation |  |  | IMPLEMENTED |  | OTF:6202 04/07 feature was rejected beacuse can be use standard functionality,email send to Gosia 26/09: Jeeves solution not satisifed SU, decison will be taken on next preCab
| Maja Ostrowska | [6 empty] | One Jeeves | Improve Po layout | Still not efficient layout, loosing to much space, wasting to many sheets | 4 | Maja Ostrowska | 10 | 600 | Yes |  | 24/09/2018 | IMPLEMENTED |  | 5758 05/07 email send to Maja
11/07/2018 | Boguslaw Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | improvement of the process when orders with multiple point of deliveries need to be dispatched in the Warehouse | Right now (example 1168469) we are losing ~1 person / shift to close distribution list and create (manually) dispatch labels for each address. If time of closing will be reduced to max 30min it will safe 7h= 297,5PLN (then warehouse operator can Prepare next orders) | 5 | EL | 124 | 7440 | PreStudy |  |  | ON HOLD |  | Several options are available : Adjust some functionalities in olhucorl program in order : 1 / to be able to select a range of sales order (search criteria to be decided) 2 / Being able to process for all these selected orders the move from left to right operation (20h) 3/ Being able to populate only once the closing information (in a popup window) and duplicate / apply to all selected orders (20 to 30h ?) 4/ Being able to process all delivery notes for the selected range of orders (20h ?) 5/ Being able to process all transport label for the selected range of orders (taking into account the integratio with Centiro) (30h ?) 6/ How to handle exceptions : example : an order which is not fully booked is in the range of orders to be dispatched. How to handle such cases ?? (40h ?) Second option is to investigate a program in Jeeves called "Joint picking" (olhusam) which allow to do mass picking. We should contact Jeeves to get feedback if such program would support our requirement As we see, this will be a project estimated to 180 to 200h 2 actions : - Continue the improvement of performance in dispatch order program - Investigate with Jeeves consultant (Lasse S after his vacations) the "joint picking" that Julia has found 06/08 Guide how to do massive picking/dispatch was provided to users (waiting for answer what can be improve), test performance was done and defect 1980 logged to fix issue with long closing 29/08 waiting for feedback from warehouse PL team |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXDrA5ItbEdDhXin7Iq7XTUBYzcMXiZifykrEkcO24g2Xg?e=cEamLx
| Linda Yang(Monica Yi | [6 empty] | Current Jeeves (2940,2970,2960) | - Upload bin location list with items in 2960,2970,2940 - Show bin NO. on the picking list in 2960,2970,2940 | No current Bin locations generating ineffecient warehouse handling. Decrease personal mistake. | 3 | AEL |  | 0 | Closed |  |  | IMPLEMENTED |  | 05/07 mail send to ladies 17/07 topic not valid anymore confirmed with user
16-6-2017 | Krzysztof Mizielski | [6 empty] | One Jeeves | Optimize packing report in OLHUCORL | Rationalizing, Improving competetivness? |  | AEL |  | 0 |  |  |  | REJECTED |  | More investigation needed with Krzysztof 20/07 topic not valid,confimred with Bogus
29-05-2017 | Jeeves Support | [6 empty] | One Jeeves | Shortage report in Xarla now shows shortage based on full order quantity instead of remaining order quantity. | Shortage report should display actual shortage. With larger orders or any part-delivery shortage is incorrect because parts of the order have been dispatched and invoiced. | 3 | AEL |  | 0 |  |  |  | REJECTED |  | Andreas to investigate more. Agreed with Jolanta that the current report is not sufficient for warehouse use. A bigger discussion should be taken with key HUB users. Could eWMS or EazyStock provide be used for this or should we change the current logic of the reports? |  | https://hldisplay.sharepoint.com/sites/itdocumentationrepository/_layouts/15/WopiFrame.aspx?sourcedoc=%7BDF4C6541-1B79-48B6-9BD5-E771193865AE%7D&file=XXXX%20-%20Shortage%20report%20remaining%20quantity%20comparison.docx&action=default
04/09/2017 | Boguslaw Kuczynski | [6 empty] | One Jeeves | XLS file connected with a RF scanner to proceed with wireless dispatching of all parcels | Not Given | 5 | CS |  | 0 |  |  |  | REJECTED |  | project proposal eWMS? Waiting for management decision 20/07 topic not valid,confirmed with Bogus |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ef8R_OKemWZPq12U9J2uOtYBvUMPCW4iIp9HGpWraLqROQ?e=DX1EJ2
28/03/2017 | Boguslaw Kuczynski | [6 empty] | One Jeeves | Already confirmed historic locations should be identified in the system | Currently they are double working by constantly confirming all historic locations. We should differentiate already confirmed historic locations from locations TO BE confirmed. | 3 | AEL |  | 0 |  |  |  | REJECTED |  | More Investigation needed and AEL to aks for example. 20/07 topic not valid,confimred with Bogus
| Gosia Stasierska | [6 empty] | One Jeeves | Pb with picking list in following case : 1/ Order with Part delivery allowed 2/ Booking done against few order rows (the one available in stock) 3/ Picking list printed for part of the order 4/ Receive delivery done while the picking is in progress making new order rows fully booked but not on the picking list Issue : When the warehouse staff is dispatching the goods, risk to dispatch in the system more goods that originally on the picking list | Secure the dispatch flow and avoid customer claims | 5 | EL |  | 0 | Investigate more EL |  |  | REJECTED |  | Topic duplicate in positon 36 Comparison of newly added goods and picking list
15/03/2017 | Boguslaw Kuczynski | [6 empty] | One Jeeves | Night put away and replenishment process - Replenish Pick location(low) from bulk location (high) based on current orders | Big potential cost savings | 5 | AEL |  | 0 |  |  |  | REJECTED |  | eWMS? Bogus to send current replenishment functionality in jeeves which isn't enough. We should then schedule a meeting with logistics managers/WH managers 20/07 topic not valid for Bogus
17/07/2018 | Marina Stachowicz/ D.Glajcar | [6 empty] | One Jeeves | Change format email template of Release PO | Current form is not polite, no polish characters, unnecessary words which confusing supplier | 3 | PANO | 0 | 0 | YES |  | OCT /2018 | IMPLEMENTED | 7113 | 08/08 send email to Gosia/Maja with proposal form 29/08 use txt solution for units with different legal rules 02/10 F7174 created 30/11 F7174 rejected beacuse it was covered by 7113 in Salmon project |  | https://hldisplay.sharepoint.com/:b:/s/itdocumentationrepository/EYxLo2UHYTNPuTRbcqQafXUBpj5V5tOs-akHB1Ns9iyVnw?e=CntXrg
06/08/2018 | Olivier Pedroncini/K.Lesniewska | [6 empty] | One Jeeves | ICT flow and direct shipment - delivery cost added to PO | Today for this kind of cost we aren’t able to allocate to the right pipe. -If we have the pieces is stock at the end of the month or at the end of the year we shouldn’t have this cost on P&L but on stock, we could have some input from the tax authority and will have to pay more income tax. Impossible to treat this manually. That is to say we have an issue on an operational point of view, and legal point of view | 4 | PANO | 40 | 2400 | investigation |  |  | REJECTED |  | 08/08 should be discuss on pre Financial CAB 27/08/2018 KIPA: RFC already disscused on fiance CAb - deatils sent by mail to Pawal, Erwan and Olivier. In my opinion point should be canceld from logistic CAB |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXzEKzDGD15MmvSZjy9n_NcBJtDkeVIvFlyGzyIkYyS7JQ?e=7LLLVw
06/08/2018 | B.Kuczynski | Małgorzata Stasierska | Lennart Johansson |  | HL Display Distribution Center Europe sp zoo | Central | R19.1 Jan | One Jeeves | Additonal column on Planning list - tickbox with mark PL was printed or not | We are checking stock per items each day (Daily stock counting). Our Stock Controller should to check every time did we have some orders with already printed PL. He need to do it because can happen that when he is counting stock on bin there was ~5min ago an Order Picker to pick 10pcs and now (when he is counting) there is 10pcs less. Later Stock controller will confirm (when he will close the inventory Voucher) that there is 10pcs less on the bin but really there should be correct amount on the bin. To check it faster we need to see it on the planning list like below is there any picking list already printed. | 4 | PANO | 4 | 240 | yes |  | Q1 2019 | IMPLEMENTED | 7307 | 08/08 check report stock take journal 13/08 report cannot be use beacuse is generated after run journal 29/08 accept solution with Planning list crystal report on item level, Bogus will back with feedback 17/12: Bogus agreed for solution to add column in crystal report. Dev hours can be decrease. 20/12 cost need to be divide between all units 09/01 release 19.01 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXojSJfQo6BAn7-cW1JOrTYBCooLEv2OTpo_6q8ILfTpdg?e=SruOze | 20/12/2018
06/08/2019 | B.Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Change default bin for DOCK on Inventory level | We have a lot of items on main WH which have assigned bin- needed to tell us (on ‘in delivery program’) where we should to go while put-away process. Because of many potential issues we should to put only one SKu on each bin. To do it in correct way we would like to set up all of those items just to one bin/SKU and before it we need a support from IT with transferring all ‘assigned bins’ to DOCK but without qty transferring. | 4 | PANO | 0 | 0 | update in progess,to avoid development |  | Dec/Jan | IMPLEMENTED | update | 08/08 check with Bogus at Monday this request 13/08 Pawel will help and update bins 29/08 Pawel prepare update 09/01 update in progress, update done on PROD |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYXKfhMBCn1JoRcDblodvLwBsYYnkvBPfG8gUzLOt-0E5w?e=ErNTZo
06/08/2018 | Stéphane Carrivain | Małgorzata Stasierska | Lennart Johansson |  | HL Display France SAS (+ SASU DESIGN) | Central | R19.3 Mar | One Jeeves | Management of the request for dedicated truck | When volume to be shipped is > to 3 pallets, or more than 750 kgs, we need to search for a dedicated truck, then not managed in the normal flow. Pickers need then to fill a standard document(Word) with date of delivery, address, customer code, delivery instruction which the need to copy paste in jeeves the menu “order 1”. They thus need to switch between 2 different programs, and pick these information already mentioned in jeeves(double work). From they own side, they just have to mention the qty of pallets and the total weigth. Once done, they need to send by e-mail this document to the transport dpt in order them to start searching for a company. How often this issue occur? 9 times a week Time needed for picker: approx 8 mn => Total time per week: 72 mn x 4.33 = approx. 5 hours per month. Time could be saved for transport company (could avoid to check all parameters in jeeves-date, delivery adress…) : approx. 3 mn => 27 mn x 4.33 = approx. 2 hours per month Total time savings : 7 hours per month. 7 hours = approx. 200 €. Cost for development : XXX€ Return on invest :??? | 3 | PANO | 32 | 1920 | YES | 29/08/2018 | MArch | IMPLEMENTED | 7302 7381 | 08/08 check with Stephane request 29/08 comment form SC: I just want to have a functionality which will trigger a matrix/document already populated with some field from the sale order. Pickers should only write manually the qty and type of pallet, and the weigth. 09/01 sprint 177 12/02 based on last test, extra demand of development needed. Feature 7381 created.We decided to release full solution in March 18/03 solution on Prod |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUFv2fACEm9OiaoXhWhyq30BaMEpiYDPcmVYmXXaly0u7Q?e=rQafK4
06/08/2018 | B.Kuczynski | [6 empty] | One Jeeves | Additonal fields in HL Orders per date olhucorl program | we’re estimating type of truck (to save the transport costs) for the next day we would like to receive all important informations from system once. | 4 | PANO | 16 | 960 | Yes |  | 24/09/2018 | IMPLEMENTED | 7100 | F7100 created |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EZSfsqqtRztIggMq-mLKd9UBjBy1d6dVEIGQoC17bBz0dg?e=CyYAnF
06/08/2018 | B.Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Block print PL on not booked KiT items | For orders ‘part delivery allowed’ and/or orders with kits system should not print this picking list till 100% of kit parts will be fully booked. At this moment we can’t relese for invoicing order when even one part of kit is not fully booked. | 4 | PANO | 24 | 1440 | rejected |  |  | REJECTED |  | 08/08 check with Stephane,Erwan flow in FRA 29/08 Erwan and Pawel contact Emilia to review process EL : linked to the way that sales order are registered with date management. No such point for 1600 and 1710. Emilia knows this is a challenge for the nordic countries move 20/12 reject of move Nordic to 1210 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXmcWdPNktNKkMEy4zR_WqwBzsIbeFCQxMMlvr5oqzo7BA?e=AMelfQ
06/08/2018 | B.Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Block possibility release orders after 2PM during closing month | To reduce nb of this potential issues we would like to have an option on jeeves that all orders after 2PM will be stopped by system with releasing for 12h. Maybe this is good idea that one of our managers can activate it manually in the system at 2PM (Gosia, Maja or me)? | 4 | PANO | 24 | 1440 | rejected |  |  | REJECTED |  | 08/08 check with Alicja M, Ola Cieloch, Kinga L.,B.Paszkowska tax risk if occur that situation 28/08 this is not legal demand but process request 29/08 Gosia will check with Finance and back with feedback 20/12 no need to develop, check with Jeeves and Marcin posilbity to change date of release during invoicing |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ER7YCzktuwpJpu3goAio3ksBI08c8_d10Rlod9c9yZTUHg?e=uFqI5Y
07/08/2018 | B.Kuczynski | Małgorzata Stasierska | Lennart Johansson |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Pop up window on scrap process in xarsm | Every time when we need to create a new scrap there is a huge risk that (example): Day D 10:00 - scrapping decision Day D 13:00 – we received new SO and picking list for this item Day D+1 9:00 – system scrapping Day D+1 10:00 – when we are picking this order location is empty or there is less qty Is it possible to receive an pop-up window (!!! Be aware there are some ORDERS for this item !!!) when we are doing scrapping in ‘xarsm’ in case when we want to reduce stock and there is still some ‘needs for SO’? | 4 | PANO | 0 | 0 | in progress | 09/01/2019 | 2020-11-20 | IN PROGRESS |  | 08/08 check standard functionality with Bogus, Nathalie will help our test confirmed that no warning message appear during the scrap process 29/08 ask Jeeves about missing warning message in new Jeeves, check if it's configuration issue or suggest development 17/12 question send to Jeeves 20/12 cost should be divide between all untis 09/01 correspondence with Jeeves 10/01 Jeeves logged defect 181219-000058 to fix issue with scrap :), so no development needed 28/02: reminder send to Jeeves 29/04: Jeeves still answer that they have huge list of higest priority incidents 15/05 defect in Jeeves was prioritized 14/06 fix is delivered and need to be tested 05/07 fix will be ready to test on CFT 04/09/ fix can be install only with new Kernel, discovered issue on solution delivered by Jeeves 19/08/20pano: new Kernel test installtion predicted in Autumn |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWqV2Yc77VRMlllbRB8E_gUBXs1qcaz7wvzb8hxVaT-UeA?e=P3sg7v
10/08/2018 | B.Kuczynski | [6 empty] | One Jeeves | Block printing PL for Credit orders in button Picking list to date | We don’t want to spend additional time to sort the picking lists | 4 | PANO | 4 | 240 | YES |  | end of November | IMPLEMENTED | 7120 | F7120 created |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EX7QUTqn0lNMiUyUfC19XqIBvh467gZkmCmVGkqm9zEAag?e=s7fIDA
16/08/2018 | Laurence Lakafia | [6 empty] | One Jeeves | Customer specific item datas (from kuar) are not appearing on picking list and delivery notes | Kuar informations (Customer item nr, Item description & Specification) should appear on picking list and delivery note templates (fr and English versions) On picking list, the customer item nr field is already appearing but not the 2 others On delivery note, none of these 3 fields are appearing at all | 4 | PANO | 16 | 960 | YES |  | end of November | IMPLEMENTED | 7122 | F7122 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EX6rfVlWbcpLsohtNqajeBIB3i5m0wjjdTx-bqDgKdyy9A?e=BfEJMR
16/08/2018 | Stephane Carrivain | [6 empty] | One Jeeves | Phone number forwarded in EDI –Géodis and DPD 2 options: 1) Put another Phone details on PoD if that filed not exist. Probably it will be needed to add design to create that filed and then transfer that contact to correct delivery on “olhucorl” program. 2) Change mapping with Carrier and Delivery notice 2 will be always transfer to Telephone in carrier side. | This is not acceptable to get only the phone number from customer only as we need to get a contact at place for each delivery, not the purchaser or project coordinator one. This create lot of wrong delivery information and delay delivery at customer whereas phone number is mentioned on “delivery notice 1” or “delivery notice 2”. | 5 | PANO | 32 | 1920 | investigation |  |  | IMPLEMENTED |  | EL : Are we talking only about massive operation with multiple POD ? Suggested solution : 1/ Add on POD level, 2 fields : Delivery notice 1 & 2 (exactly as we already have on customer level) that will be transfered to the dispatch and sent to the carrier company 2/ Include these 2 columns while POD are loaded through excel file (containing all POD) and make sure they are imported into each dispatch and sent to the carrier company 3/ Make sure with the carrier company that Delivery instructions 1 & 2 are well taken into account by them Estimate based on points 1 & 2 above 29/08 discuss with carrier company, Geodis ,Erwan Pawel will check it 07/09 EL : I have prepared 2 test orders in order to get the txt file and check the trasnfer of informations with Geodis (Jeremy Pereira) 02/10 Geodis change software |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVTGpHv7ZMNJkpObnT7IBZgBzTuBmn6YeNAAbH3BQ4gFqw?e=J9NHlB
16/08/2019 | Pawel Mazurewicz | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Availability report QV | We would like to have a tool showing Items with inventory’ – ‘ in horizon of LT At the moment there is no report in QlikView that would show it, from our point of view it is necessary to provide support for our SUs at the highest possible level and this tool will help us a lot. Stock availability report is to manage products that are in high demand. Thus, one goal in operations is to keep the level of inventory in the supply chain as to low as possible thus freeing up funds for other purposes. Main purpose: • To have enough inventories to fulfill orders of outer and inner clients in a manner satisfying them. Or with other words – assure high level of customer service. Usually this customer service level is measured as availability (fill rate). • To minimize inventory carrying costs, first capital tied into inventories for maximizing the company`s profitability | 3 | PANO | 20 | 1200 | onhold |  |  | ON HOLD |  | EL : this is exactly the requisition report that we have in Jeeves, isn't it ? 29/08 EasyStock check on action list 26/09 next week Workshop is scheduled, Erwan will check it with Easystock people if this requirement would be covered by their application or not EL : Eazystock does have some "risk of shortage" report. 20/12 wait for implementation of Eazystock |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESha00so3dZKnf5RDnEcAcABHQcxONlwGIwQzXMvglusKQ?e=MPNrrY https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EaOnZPfQtl9Bi0d47WgXOWEBybed36mkluDWDaLxuNYAag?e=Okth9P https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EauO1ESsg8JDhJPjH71qsIIBO3yRxbvd3jx8tA0EtipMdw?e=6WOdv5
20/08/2018 | Stephane Carrivain | [6 empty] | One Jeeves | Inventory Transaction MO number When we need to check an MO it’s necessary to go in inventory transactions menu. To check the 120-Transaction + double click on it in order to get it. After Yellow arrow we go immediately on the item menu – it would be better to stay on the drop-down menu in order to continue the research | How often this issue occurs? Few times per week it depends on the problem and the need for research Average: 3 or 4 times per week - Time needed per issue: it depends of the problem – 2mns to 5mns Cost per week (based on 3 mn): approx : 4.50 € | 4 | PANO | 2 | 120 | YES |  | end of November | IMPLEMENTED | 7121 | F7121 created |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYWfv2HEzKRPtn1H8gzre1EBNeauiX5XiSpI-4_ohd0cFw?e=gEMRZn
17/08/2018 | Stephane Carrivain | [6 empty] | One Jeeves | Change on QV report Item cost breakdown | We have in all HUB’S overstock for which we try to find solution to decrease. We think that having a report on which we could be able to see items with a BOM created by factories could help us to suggest our own overstock in order them not to produce /order to external supplier but to order us those items. It will help us as well not to order them these items by first checking in our stock and to create a MO in order to unpack the finish item and to use the component needed. | 3 | PANO | 16 | 960 | NO |  |  | REJECTED |  |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ETrHViyJ-_BFpRzuQRQiGO4BQk4GyebmzBUJwEn3ZXDsug?e=ltzFab
02/08/2018 | Stephane Carrivain | [6 empty] | One Jeeves | Change of a field printed on the picking list | We have in the delivery note the customer order number printed and we want the same thing on the picking list. These information’s are used when it’s necessary to book trucks + appointment needed. The pickers send a special document and they put customer number instead of customer order number. In this case it’s necessary to check and to correct the document before to send it at the carriers. We lost time. | 3 | PANO | 4 | 240 |  |  | end of October | IMPLEMENTED | 7122 | 29/08 it will be cover from point 61 F7122 created |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVGbEh74TyBAlkZs3OQkswYBsvzOB5-0pVG1sOpt2MxIjg?e=LzbOoI
06/08/2018 | Boguslaw Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | WMS | IN delivery issue Setup ping response between scaner and Jeeves | When we are booking to stock (Main WH) new shipment there is a risk that single pressing button causes multiple receivings to the main WH when system will wake up after some connection issues. Later because of that we need to transfer back to PO some ‘virtual’ qty. Please change/rebuild the architecture of ‘in delivery’ that we will be sure that system will not register more qty than we need to. It happens because connection/system is still not stable on the scanners. | 4 | PANO |  | 0 | ONHOLD |  |  | ON HOLD |  | EL : not part of the architecture of the WMS sytem. 1810 is the only unit reporting this point. This has been escalated to infra guys (Tomas Wetterlund) regarding unstability of the wireless network in the WH and actions are ongoing 29/08 Erwan separetly discuss with Gosia 18/12 new scaner in HUB, test by user , Gosia will back with feedback 28/01 problem with log to scanner after changes server, IT need to check 25/02 SD is checking logs Access points 11/04 pano: I recreated this issue on test application, IT log defect 2167 to analize problem on scanner process |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EaPEIl8FNeZGpkyaFhqRxYQBDdTMRDE0-wHssxVUy9lBVw?e=6tsgeq
10/07/2018 | Boguslaw Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Inbound real OTD | We are counting some KPIs on the WH. One of them is ‘OTD to stock’ so this is time between physically unloading the truck on the Inbound area and transferring to Main Warehouse. To count it we need to see when (date and time) shipment/pallet/item was unloaded to some ‘temporarry Inbound zone’. At this moment there is no possibility to check when item was unloaded, we just see only when goods was registered on the main wh so KPI counting is not so easy like it should to be. I think this new function should be implemented to our scanners to ‘In Dellivery’ system. Is it possible to add something like this? | 3 | PANO |  | 0 | onhold |  |  | ON HOLD |  | EL : shouldn't it be a process change here in the system (there is some module which allows to make ? 1/ arrival entry 2/ then receive delivery example of flow used at T-Emballage that we visited in May 2018 Other alternative : 1/ Make the first receive delivery to a bin called "INBOUND AREA" 2/ Then make a manual stock trasnfer from "INBOUND AREA" to the real BIN LOCATION 29/08 DEMO will be present by Christer 18/12 review flow with Bogus 09/01 missunderstand RFC, additional review needed 17/01 improve scanner application 28/01 other way to calculate KPI 30/01 adjustment can be done by remove logic on bin - F5216 12 hrs max |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWMWv3chESRDsM6xcUdmQ_oBWlOn45TWbWbwYzoapdOfqg?e=5AXiYt
28/08/2018 | Katarzyna Zelwor | [6 empty] | One Jeeves | Production stock of components decimal places increase | We need real value of components stock with at least 3 decimals, this is important in case of components like tapes where the components unit is meter. We have wrong components stock. | 4 | PANO | 32 | 1920 |  |  |  | REJECTED |  | 29/08 continue discusion on Production CAB |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVFxlMSUrXVGpf1pYfPU75gBfwCzGrqDq1Ep0ogR6-fd7g?e=HeZpsm
2017-03-14 27/06/2018 | Stephen Mepsted M.Stachowicz |  |  |  | HL Display Gliwice Sp z.o.o | Factories |  | One Jeeves | Original promised ack date on PO and also able to set manual Date and who confirmed | Dates changes happens a lot, hard to follow up what was original promised | 3 | CS PANO | 32 | 1920 | investigation |  |  | REJECTED |  | Will need to touch EDI, ICT, external orders 02/10 arrange meeting with units 15/05 waiting for Polish HUB 10/06 request only concern chnages in factory flow with external suppliers 06/08 Gliwice Factory not interested any more |  | https://hldisplay.sharepoint.com/:b:/s/itdocumentationrepository/ET5N_n1mc2VFudL9mWhaIOEBWzmFi0IKTr6kz4IznmilAg?e=VoYxxj
30/08/2018 | Christer Sahlen | Lars Amtenmyr | Lennart Johansson |  | HL Display Sundsvall AB | Factories | R19.11 Nov | CJ | Printing Problems in Sundsvall - new solution to be implemented uregntly in order to avoid problems with old application. Biztalk solution to be investigated by Erwan, Kamil And Christer | Risk of using the old apllication is very high. The issue raised 29th of August had an impact on daily dispatch estimated for 400-500k SEK. | 5 | KaSc | 40 | 2400 | YES | 02/10/2018 | January | IMPLEMENTED | 7171 7215 | EL 02/10 ; a first investigation feature for 40h but it will be in total at least 100h 02/10 F7171 created 25/02 since two months Business don't want test solution 18/03 Chirset will puch users to test 15/11 Solution for SDL factory only
21/05/2018 | Pawel Nowak/ Kinga L | Julia Homik | Lennart Johansson |  | HL Display AB - IT | Headquarter |  | 1J | Correct replication on fkst table | To clarify way of adding special cost to this table,to consist data in Jeeves | 4 | PANO | 10 | 600 | YES | 29/06/2018 | 22/10/2018 | ON HOLD | 7063 | Implementation within the Salmon project 18/12 ONHOLD, problem with Jeeves replication, reported to Jeeves
10/08/2018 | Emilia Hermio | [6 empty] | One Jeeves | Increase Nordic charges by 10% | General request from Group level to increase profit on freight, effective as sson as possible | 5 | PANO | 2 | 120 | YES |  | 2018-09-21 | IMPLEMENTED |  | 7142 cretaed,installed on PROD at 21/09 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYlM0QaZKf9JmqjP4y7UxqcBhayTgZ_BW256wBdPGxwsIw?e=TWsfKv
28/08/2018 | Stephane Carrivain | Stephane Carrivain | Andreas Astgard |  | HL Display France SAS (+ SASU DESIGN) |  | R9.2 Feb | One Jeeves | Improve Threshold blocking PO | Would it be possible for only few suppliers, and as soon as the goods have been moved into status good in transit(means already approved once by the purchase manager), not to have anymore this threshold during adding another cost row as this is really heavy and time consuming ? | 4 | PANO | 20 | 1200 | YES |  | 1Q of 2019 | IMPLEMENTED | 7275 | F7275 created 09/01 BT feature, few question send to user |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ET0uaLC8ZRFGsJi6oD5r4eAB1z0pr4eRDPNxQveogPYIpA?e=GIBIXk
01/10/2018 | Erwan Lardic | [6 empty] | One Jeeves | Track and Trace link for Geodis not working anymore | be able to follow up deliveries from HL to the end customer | 5 | PANO | 2 | 120 | YES |  | end of October | IMPLEMENTED | 7175 | 02/10 F7175 created 9/10/2018 on Prod |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQdQxumMW_ZJvRQ3fNB_I0oBVlsElZo6C2_AQk9KycBIcg?e=1oJpiE
03/10/2018 | Sarah Lucy | Margareta Karlsson | Lennart Johansson |  | HL Display Schweiz |  | R5.14 Dec | One Jeeves | stock take in Switzerland upload |  | 5 | PANO | 4 | 240 | YES |  | end of November | IMPLEMENTED | 7178 | 03/10 F7178 created
17/10/2018 | B.Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Carrier code on Picking list For better management of picking process we need to find on the PL(PickingLists) ‘basic carrier code’ | Now is happening that driver from Toptrans is waiting for the order(package) preparation because we don’t know that this order is not DPD like 99% of the rest. | 4 | PANO | 2 | 120 | ONHOLD |  |  | REJECTED |  | 13/11 wait beacuse of backlog 18/12 Gosia confirmed it's low impact on daily routine and wish to reject this topic |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ES8EeH7fbj5OhfpHM73uQMMBNmVtI8SzTFE8FcUROLPbRA?e=tTzIzu
15/10/2018 | B.Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Picking route To increase speed of picking for some ‘bigger’ orders Usually 50-75% of all orders dedicated to 1810 are small (1-3rows) means that those orders are small and picking route (if we are picking each one separately) is not s helping us* but when we are picking orders like 10+ rows this rule will reduce times for the physically picking because we will drive according to route not like now in chaotic combination | It will increase our productivity on WH. | 4 | PANO | 40 | 2400 | investigation | 14/08/2019 |  | INVESTIGATION |  | 13/11 need to be discuss with business contact Jeeves,check different request, check with Gosia and Bogus cases 18/12 prestudy in half of year 2019 28/01 contact Bogus and check with him solution 25/02 IT will prepare fix to defect 2121 to see if that will help 15/03 fix was installed on Prod 06/08/2019 current booking solution not include picking route but qty on bins, new idea is to adjust crystal Picking report with new rule of routing process advised by user 14/08 check with other units this idea 07/10/2019 after meeting we tested standard parameters and works fine - we need only adjust Text between rows process with SU 07/07/20pano: Gosia need to contact Sarah L. to check with Austrian sales maket posibilites |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EW6RCB9ZCmlJsDWTsE3LQk0BDRr5ksENvn0fT8iXqnAPzg?e=4hTDr7
07/11/2018 | Pawel Nowak | Julia Homik |  |  | HL Display AB - IT | Central |  | One Jeeves | Booking refactoring? | Remove standard and create new logic Connected with RFC from Bogus with new booking logic | 5 | PANO | 100 | 6000 | ONHOLD |  |  | ON HOLD |  | 13/11 IT try to fix current issues and then collect from units all requirements, back to this topic in January to check status of progress fixing issues
03/10/2018 | B.Kuczynski |  |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Adding new fields on lth list To better calculate our basic KPIs we need to find new informations like rows/picker/packer. To do it more precisely we need to find in one place (XLTH report here) two additional fields/columns from: * Olhucorl: Picker and Packer | better calculate our basic KPIs | 4 | PANO | 1 | 60 | ONHOLD |  | 29/01/2019 | IMPLEMENTED |  | 13/11 wait for Gosia and more imput 18/12 Erwan will send querry and put status onhold 28/01 remind Erwan to make querry 29/01 querry was send to Bogus, we avoid development time in Jeeves |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EY5orHDwjzRLkzsRane7Wt8B9E4x0MUFTyFX8-WtCVbndg?e=sXiW2C
17/10/2018 | B.Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Central |  | One Jeeves | Scanning solution/tracking solution in WMs | Possibility to tracking shipments | 4 | PANO | 16 | 960 | ONHOLD |  |  | ON HOLD |  | 13/11 wait for Gosia and more imput 18/12 wait for decrease backlog 28/01 keep on onhold |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EZDeNGcvYcRDh_EeevT3hL8B_tlZeqeAdg_rrbi4sLL6ZQ?e=TG6qmR
13/11/2018 | Maja Ostrowska | Małgorzata Stasierska | Lennart Johansson |  | HL Display Distribution Center Europe sp zoo | Central | R19.2 Feb | One Jeeves | The request is to add additional information on item level locally. That is mainly related to item cathegory connected with projects (P) and items kept for one endcustomer, specific item (S). We need to be able to connect kept stock with particular SU and as well add information regarding dead line when stock should be sold out. That means that we need two fields – 1st for SU, 2nd for date. Both to be field manually. In next step we need to have QV report which show us stock kept for each SU – in value and in pallets, + information regarding date when should be sold out. This way we would be able to alocate costs and as well to track when request is already past due and we still have stock which should be sold out. | We need to be able to alocate cost for stock kept on request to particular SU. Now we do not have such information in jeeves and we need to check history of movements or gather data in excel. | 4 | PANO | 24 | 1440 | yes | 18/12/2018 | Q1/march | IMPLEMENTED | 7303 7327 | 13/11 check with Maja O. this request 18/12 EL : cost will have to shared between all HUBs |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Eb4tCzh18ZdErRa_mfSabv4Bgen9ZihF4nBSMbrnxER_yg?e=fm8S13 | 18/12/2018
09/11/2018 | Erwan Lardic | Stephane Carrivain | Lennart Johansson |  | HL Display France SAS (+ SASU DESIGN) |  | R5.14 Dec | One Jeeves | In the past (before 1J Go Live for Area West), when an order was dispatched through Geodis and DPD, the transport file generated for the carrier company was containing email address that was used by the carrier company to inform about a new dispatch ongoing from HL HUB. This functionality was not moved to 1J as this was supposed to be covered by Centiro integration which didn’t happen during West Go Live as there was too much difficulties to have Geodis integration with Centiro. Therefore, there is a need to re-integrate this email address to the flat file generated Purpose if to add at the end of the flat file generated in olhucorl program through the button “Transport file fra”, the field from order header : oh.q_hl_emailtt | customer satisfaction, they will know when a dispatch is done for HL Warehouse that some goods are on their way to the customer | 4 | PANO | 4 | 240 | YES |  | December | IMPLEMENTED | 7271 | F7271 created |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXCi-tRS669Ev1EiMMzUg_IBYNYfftyigjKd_I-8YoW3wQ?e=YDemOg
07/12/2018 | Marcin Nowicki | Małgorzata Stasierska | Andreas Astgard |  | HL Display Distribution Center Europe sp zoo | Central | R19.1 Jan | One Jeeves | External supplier text | Missing correct information to supplier, no professional looking report in business eyes | 5 | PANO | 4 | 240 | yes |  | Feb | IMPLEMENTED | 7301 | 18/12 after request from Romania 09/01 release 19.01 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUDmqJ9CCYRDi3G0BNIy2RMBGNF-ij9ObA7wB_fWl5wKFQ?e=5aOPvf | 18/12/2018
12/12/2018 | Joanna Rosół | Magda Oczko | Lennart Johansson |  | HL Display Gliwice Sp z.o.o |  | R5.14 Dec | 1J | Adjust Bartender labels in 1190 Prod_POLLAGER_KTW_PRN_003New_DB | Adjust label with extra infromation of country of origin - to fit request from customer | 5 | PANO | 2 | 120 |  |  | 12/12/2018 | IMPLEMENTED | 7293 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ee3AYWbn6OdHjfxC1c8L0z8B_GUjbL5WXpQv25sGS1YrJQ?e=PWbuZ3
05/12/2018 | Kamil Saczka | Tomas Osbjer | [6 empty] | New label printing solution - Jeeves2Label | Current solution (Bartneder) is out of date - not supported any more, causing a lot of issues in production environment with high impact on running operations (business). |  |  |  | 0 | Project Office |  |  | SENT TO PROJECT OFFICE |  | Kamil to call for the meeting (Project Pre-Study) in January. |  |  | 18/12/2018
14/11/2018 | Joanna Dabrowska | Magda Oczko |  |  | HL Display Gliwice Sp z.o.o |  |  | 1J | We need to add pallet dimensions to packing list | Our Sales Hub in Dubai requires pallet dimensions to be added on each packing list. This is needed by the customer to avoid additional costs connected with local customs clearance. | 5 | PANO | 8 | 480 | rejected | 14/06/2019 |  | REJECTED |  | 18/12 check what kind of cost customer paid, mail send to requestor 09/01 wait for user 20/05 still no answer from user 11/06 reminder send to users 14/06 Dubai is not interested anymore of this request confirmed by Anthony Oyales |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ecks1ZUH-utFi7JRjArU7bUBc3E4dL-O5bCKAMjmATbFIw?e=hs4afi
18/12/2018 | Sarah Lucy | Małgorzata Stasierska | Lennart Johansson |  | HL Display Romania | Central | R19.1 Jan | 1J | PO Romania report | Romanian Sales Unit started the process “local sales”. Which means they are sending POs directly to their local suppliers and the supplier is delivering goods directly to Romanian customers. HUB in Poland is not involved in this flow. Right now, there is no PO template for Romania. They need to have the template in English. | 5 | PANO | 6 | 360 | YES |  | 2019-01-01 | IMPLEMENTED | 7300 | 09/01 release 19.01 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcNK-Pji9JNOgpShKHxbshQBicMe5qQo6c_J98o3Ws_ixA?e=bUkQN2 | 18/12/2018
07/01/2019 | Maja Ostrowska | Małgorzata Stasierska | Andreas Astgård |  | HL Display Distribution Center Europe sp zoo |  | R19.3 Mar | 1J | The request is to be able to indentify items for which we will use new booking horizon approach. Now we can see that we change booking horizon only in alt supplier pgm but it needs to be visible on item planning list for everybody | New booking approach is a new development and needs to be clear for everybody which approach is used for particular items, otherwise it might be misleading for users. | 5 |  | 6 | 360 | YES | 25/02/2019 | March/April | IMPLEMENTED | 7394 | 09/01 it's samll desing change in Planning list 28/01 check with Nordic if they want share cost and interested of develop 25/02 Nordic agree to share cost with 1810 18/03 solution on Prod |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESXd11UvT1lLih9oFK7L9j4BdxrWDaFyCO9dmQQyMzT40Q?e=gYZ49r
07/01/2019 | Maja Ostrowska |  |  |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | To block manual modification of price after reception in beinlev program. Now system allow to modify what cause descrepancy between report F02 and account 14500. | Defect cause descrepancy between report F02 and account 14500. Jeeves allow modification after reception what is a defect. First reception which is done with wrong price should be corrected but system allow to do that wrongly – just editing price. | 5 |  | 24 | 1440 |  |  |  | REJECTED |  | 07/01 pano: issue happen after receive goods without refresh view. Jeeves answered that it's not proper way of changing price and it's more user mistake. 28/01/ Pawel will create guide with proper process and contact all units 31/01 Pawel send guide to all units, request can be rejected |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWE3yY0XUw9CgCXjQQ4UWQIBEMHfMOfUiTVrNK0v9EwR8A?e=nB695N
10/04/2017 | Birgitta Möllerskog | Anders Lautmann | Lennart Johansson |  | HL Display Nordic | Costs info in comment |  | 1J | Improve ulpoad catalogs, improve PoD transfer on order Circle K need to make changes/improvements in Ariba/Jeeves . According to Vanda Kanavina there is a new version CIF extendend that allows more than 1 picture. They also want to group our items so it will be easier for the stations to understand what item that belongs to another item. | From Circle K we receive orders through their system Ariba System are connected to each other through our customer number and their station numbers. The problem that we know have appeared is when they need to have delievry to unemployed statios but to another dekiveryadress for example a local salesoffice. IN Ariba they write this information ( see enclosed ) which do not follow over to Jeeves. | 4 | CS | 12 | 720 | YES | 09/03/2018 | 2020-11-20 | IN PROGRESS | 6843 6844 7535 | 01/03: review needed with EDI project. meeting on 8/03/18 14/01 features assigned to Maintenance, improve existed functionality with cooperation of ARIBA team; need to discuss points of development on preCab -more hours needed 25/02 development based on cooperation with Ariba 19/04 F6843 was not released on Prod, Ariba env. was not prepared 04/06 F6843 released on Prod on 24th of May, additonal feature needed 7535 to cover grouping items |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESDD1BitSkZEgm1fAtsGgIABtcROWW_h2vHk41Cr59ZO8Q?e=W0ewmb
08/02/2019 | Stephane Carrivain | Stephane Carrivain | Lennart Johansson |  | HL Display France SAS (+ SASU DESIGN) | West | R19.8 Aug | 1J | Switch of carrier company in France HUB from Geodis to DB Schenker | Reduce transport costs | 5 | EL | 72 | 4320 | YES | 08/02/2019 | April/May/June/July/August | IMPLEMENTED | 7378 7379 7399 7430 7476 7505 7537 | 18/03 Features 7378,7379,7399 released on Prod 24/04 additional feature 7476 was created to cover partial shipment mapping 15/05 additonal feature 7505 was created to cover solution for different local station 06/06 additonal feature 7537 was created to cover all new transport matrixes |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbaRrptAogxCvKDKgVzvZcABHSkxUs_nN7fwwyTZR3hfRg?e=ZD2sgO
23/01/2019 | S. Carrivain | Stephane Carrivain | Andreas Astgård |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | Booking on PO for multiple SO linked on the same project nr Secure the stock for common items | We’re currently able to book items on purchase order, but sales order per sales order. We have an important project for which we should have 200/300 sales orders that cannot be manually booked on PO as huge time consuming. The aim is to be able to book on PO according to a project nr instead of going trough each SO. It seems possible by : Menu XORPBOK Get back the field “Project ID” in the button HL Standard | 5 | pano | 24 | 1440 | onhold | 13/02/2020 | July/Agust | ON HOLD | 7509 7510 | 24/01/19 Pawel found solution in Jeeves 25/02 currently tested solution and defect 2055 need to be release in March 15/03 probably we need to think about improve scanner application 12/04 solution for PO booked SO with project is not implemented in Jeeves 27/06 waiting for business decision about improve process 13/02 wait for WS March 2020 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EZ8ndrsdYlZCgGyd4WTTq_0Bux3Y7JL3nUnUNcAdsiETsw?e=h0njh5
15/02/2019 | B.Kuczynski | Małgorzata Stasierska | Andreas Astgård |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | When we are receiving items to MainWH we have to make sure that item will be registered to one of the current ones: 1. We don’t want to increase nb on bins for the same item = reduce nb of bins with the same item 2. We would like to pick later this item from the lowest bin (low picking bin) without using high forklift = faster picking 3. Replenishment will be faster because fixed bin will be full= faster replenishment process To do so we would like to see fix bin on top in application. Then list should be sorted: • On the top of this list- current locations with item, qty >0 • Later- current locations for this item with qty =0 • Later- empty locations without any qty and without any item | If we will fix all high rotating items on low picking bins then we have to be sure that system will tell us where to go (while put away process) without increasing bins for this item. | 5 | PANO | 8 | 480 | YES | 25/02/2019 | April/May | IMPLEMENTED | 7396 | 25/02 cost share between UK, FRA, PL (check with 1210) 26/02 conflict within units with development, meeting scheduled 07/03 during meeting we decided go with changes accordig request |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVVzgcTgL_JBmIIdlM5y04ABbTbr8SB2U2qYH8ljYqM77g?e=QBfGyN
19/02/2019 | Arnaud Pichonniere | Stephane Carrivain |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | When using the function to upload multiple point of delivery on 1 order, the transport labels are not printed properly. Therefore the generation of Transport file for carrier needs to be adjusted to cover the possibility to use multiple points of delivery for one single order | Avoid to handle such operations manually in the Carrier application (manual registration of each dispatch in case of multiple point of delivery for one single order) | 4 | EL |  | 0 | rejected | 19/09/2019 |  | REJECTED |  | EL 25/02 : Needs to be more more invetsigated by ErLa before any decision 19/09 not valid anymore confirmed by Stephane C.
19/02/2019 | Stephene Mepsted | Stephene Mepsted | Andreas Astgård |  | HL Display (UK) Ltd |  | R19.3 Mar | 1J | FedEX button improvement Change description of FedEx button to “Parcel carrier” Secondly, when this button is pressed, it sends a text file to a folder located = “\\SDL-CLU-003\JEEVES\SWAP\PROD\FEDEX” I need this to work when both carrier codes of FedEx and D&G are selected, currently FedEx carrier code is set up for this, but D&G is not, can this be set up please? | New carrier Cost saving | 5 | PANO | 12 | 720 | YES | 25/02/2019 | March/April | IMPLEMENTED | 7395 | 25/02 cost will be cover by UK 18/03 solution on Prod |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EX7-mvSs-vxJghxDKSxm8zwBFbVh_hX4xfdlpPU5HEU3Iw?e=zhYA6r
14/03/2019 | Maja Ostrowska | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | Changes done locally in item end customer program should not be replicated and impact other local jeeves. That require development – company number needs to be added automatically then changes will impact only that company which enter data even if data is visible by other companies. Additionally changes needs to be implemented for already existing records. | Item end customer table when is filled locally replicate to Master Data and to all other local companies impacting work in all companies. | 4 | PANO | 20 | 1200 | onhold | 18/03/2019 |  | ON HOLD |  | 18/03 prepare list of DEV cost, make onhold to check impact on other units, check frequency of impact 09/07 topic connected with request from Fredrik F.; 1810 and 1210 interested |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYHIOpEtBadPjAbUIQ5LI10BXQ5cO2FSMVIJyG_zR7EOrg?e=QjPnri
14/03/2019 | Bartosz Wowra | Fredrik Ström |  |  | HL Display Nordic |  |  | 1J | WE WOULD LIKE TO MAKE QUICK ESTIMATION OF TIME AND COST FOR NEW FUNCTIONALITY IN JEEVES. WE HAVE A PROBLEM WITH MAKING OFFERS FOR RACKS FOR EXAMPLE CANDY KING STANDS (EXAMPLE ITEM 523447 IN 1810). STANDS ARE BUILT IN HUB AND ITEMS HAVE STRUCTURE THAT CONSIST OF APPROX. 20 COMPONENTS. CALCULATION IS MADE IN HUB. MANY ITEMS ARE BOUGHT BASED ON PURCHASE PRICELISTS [BPRH]. PRICE FOR THOSE COMPONENTS DEPENDS ON QUANTITY AND THEREFORE WE NEED TO MANUALLY CHANGE PRICE ON ALTERNATIVE SUPPLIER [AL] AND RECALCULATE PRICE FOR STAND [ARKH]. | IMPLEMENTATION WILL ALLOW TO CALCULATE PRICE FOR ITEMS THAT CONSIST OF COMPONENTS WITH PURCHASE PRICELISTS. THIS WILL DESCREASE OFFERING TIME IN BOTH PURCHASING AND ADDED VALUE. TODAY IT TAKE 1-2 HOURS TO MAKE FULL CALUCLATION FOR ONE CANDY STAND. FUNCTIONALITY CAN BE USED TO OTHER TYPES OF PRODUCTS. ROUGHTLY ESTIMATED MONTHLY SAVING AROUND 500 EUR | 5 | pano | 24 | 1440 | onhold | 10/05/2019 |  | ON HOLD |  | 15/03 THE IDEA IS TO MAKE A NEW BUTTON WITH LOGIC SIMILAR TO TODAYS ITEM CALCULATION, THAT WOULD INDEPENDENTLY CHECK PRICE FOR GIVEN QUANTITY ON PURCHASE PRICELIST FOR EXTERNAL ITEMS [PRODUCT GROUP = OTHER] AND USE BASE COST FOR INTERNAL ITEMS. FUNCTIONALITY WILL CHECK IF EXTERNAL ITEMS HAVE VALID PRICELIST AND CALCULATE PRICE IF THIS CONDITION IS FULFILLED. THIS CALCULATION WILL NOT HAVE ANY EFFECT ON CCP OR BASE COST. WE WOULD LIKE TO USE IT FOR OFFERING PURPOSE ONLY. 18/03 wait for Gosia feedback after when she checked with AV and finance dept 29/04 investigate with Lars, go ahead if will be accepted by Lars 10/05 ONHOLD The background of such decision is that Lars just started discussion with sales/purchase how we should work with the calculation. The basic assumptions and steps are included in Lars presentation which you can find in enclosed files. The goal is to limit number of recalculation which are done today and learn to work with deviations Till the end of this business discussions all developments concerning the way how items are calculated should be put on hold |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERrc9MGeU6hJsLvIJ8EVcHcBjiVEqiOz12SbYz_S4CTPiQ?e=DkJk9b
18/03/2019 | Christer Sahlen |  |  |  | HL Display Nordic |  |  | 1J | We need improve Proforma printing option. Current solution not works well when we have carrier which not fit basic requirements. We don’t have temporary table which could keep already printed report. So, then after when we change carrier to proper delivery we cannot reprint report even we have Proforma number assigned. | Safe time to reprint Proforma instead change to fit requirements. Handle to exclude row from Proforma which suppose not be send. Contact IT to correct template – 0,5 hrs of time reaction. Other option is to manually change carrier on order, make reprint and then change back to avoid faults in system – 2 min per order. Total time per week: 40 min * 4,30 = around 1 hr. 4 hrs per month. 4 hrs = approx. 100 € | 4 | Pano | 32 | 1920 | investigation |  |  | IMPLEMENTED | 7437 | Yesterday I discussed solution with Hania and Kamil and we estimated time of development - 92hrs. If you look into file you will realize that total of development suggest even small project. We would like go with three points instead. That will take around 24 hrs: Possible to print few times per day CPI Possible to check what kind of orders are collect Possible to exclude some of orders which suppose to be not send regarding manifest list from Centiro Based on this solution we can create new view table which will collect order numbers and items which will be show when try print CPI report. Then user can compare with list of manifest printed from Centiro and exclude orders which suppose to not show. In default list all orders will be mark to show, then it will be easy remove tick from specific orders. Also numeration of CPI report can be easy adjust. Currently is taken year and calendar year. So,when we print first time or second time it will start with number 19063-1, 19063-2 etc. Solution to integrate Centiro list with EDI file that will take more time and involve both sides. So, to IT dev time we need add time/cost from Centiro side. That will take the most time. Here we need to create additional table which will collect EDI information. We need to also think about process of review file and proper process to create correctly data in new table. I assumed here we don't have control of the list of orders what will be shown on CPI. Also, we cannot predict how long could we use Centiro or if we change Carrier ? Another problem which could be also concern is temporary missing connection (network issue, server etc.) then we will not have list from carrier. 18/03 Request should be handle in Salmon project, check with Bjorn on 19/03 29/04 solution provided in Salmon project 19/04 Feature implemented 7437 on Prod, maybe it will cover most urgent topic |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EehN3-dxKr9DpYXfIJZO8pQBg49bioe08k-rwDdNW1jnfw?e=3jFqpW
18/03/2019 | S. Roinard |  |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | Add a column on the BL in order to add the Innerbox for the customer Pricer (n°125927) | The customer Pricer ask us to provide the Innerbox on our BL. Is is possible to add it only for this customer ? What will be the cost ? | 4 | PANO | 0.5 | 30 | investigation | 18/03/2019 | 25/09/2019 | IMPLEMENTED |  | 18/03 shall we use solution by kuar program? 11/06 reminder send to users 25/09/2019 Paweł run update in kuar program |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbYA4Qt9b01Cmewsz4odjcoBCaEaqUHcxjow3UE0C9zkhQ?e=8EZNj8
26/03/2019 | M.Porczak | Małgorzata Stasierska | Andreas Astgård |  | Costs info in comment |  | R19.6 Jun | 1J | Add type Inventory order for Prospect supplier | Enables edition PO on the header directly on Prospect supplier the same way it works for Panel supplier, without need to make changes per line. Time saving especially for orders with double-digit lines to be confirmed or changed. Allows also to add info in field Notes. | 4 | PANO | 12 | 720 | yes | 29/04/2019 | May/June | IMPLEMENTED | 7491 | 29/04 cost will be shared in all units |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ebm8hMEd8CpGlpAEer8vUfEBqqkbjzHqdnqB7sEqDsBqdA?e=kEdhL0
29/03/2019 | William Ellis | Stephen Mepsted | Andreas Astgård |  | HL Display Harlow Ltd |  | R19.8 Aug | 1J | I would like to increase the use of barcode scanning in the KanBan flow to also incorporate the purchased materials which are used in the production of KanBan items. Currently these are managed manually with laminated sheets, with the warehouse and production teams having to do daily stock counts and then tick the products below their trigger before passing this tick sheet to purchasing who then manually raise each PO. | As the re order quantities are set, I think it would be much more efficient to have a barcode on each pick face with the trigger level, which once scanned creates a requisition to purchase the EOQ for that product (which we would set to the KanBan reorder qty). This then allows the procurement team create the PO’s from requisition. | 5 | pano | 16 | 960 | yes | 08/07/2019 | September/ November | IMPLEMENTED | 7584 | 29/4/2019 Kamil Saczka: 16 hours needed for pre-study only! 20/05 wait for Stephen Mepstead 06/06 pano: Stephen approved the cost of development, dev time will take around 16hrs |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ea0AuJPHLBNIttumpFB2WRIB3ASIBXYoARQtthAw_dHJiQ?e=9tG3hb
09/04/2019 | Iwona Gasz | Joanna Rosół | Andreas Astgård |  | HL Display Gliwice Sp z.o.o |  | R19.6 Jun | 1J | Please add Estimate nr of pallets on report CR Shipment | The possibility of faster information on the number of pallets for shipments to the customer. Picker can easy prepare zone for specific orders and contact carrier of specific truck. Faster estimation of the number of pallets for shipment, quicker information to the supervisor regarding the number of pallets for shipment, saving paper. | 4 | PANO | 6 | 360 | yes | 29/04/2019 | May/June | IMPLEMENTED | 7472 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EZW_qVk_iw5JucSyUBeDmK4Bgl79kf_uMr-_rIsiNAmHiw?e=IukKQl
09/04/2019 | Iwona Gasz | Joanna Rosół |  |  | HL Display Gliwice Sp z.o.o |  |  | 1J | Adjust Picking list in program ffhlevp to exclude bins which are block by Quality department. Currently there is no information on PL about blocked qty, and report show full list of goods ready to send. That cause problems with delays orders because picker notice that fact during picking date. Sales support is not aware of blocking qty and not notify customers of available qty what can be send. | Improve effectivity of picker work, planning department and sales. Avoid delays in shipments, better planning, increase customer satisfaction. We lose about 15h per month, we lose time for verification and planning, delay in issuing the invoice, delay in preparing the shipment. | 4 | PANO | 10 | 600 |  | 20/05/2019 |  | REJECTED |  | 29/04 Joanna will check process with different stock and back with feedback 20/05 go with solution Inspection process, this request can be rejected |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWk1Qje5xm5BgEmbh8yZ2o4Bm58eo4DWA5zWP-bR3t4O9w?e=xwYL3i
10/04/2019 | Laurence LAKAFIA | Stephane Carrivain | Andreas Astgård |  | HL Display France SAS (+ SASU DESIGN) |  | R19.6 Jun | 1J | We need to have the field “external text” (orp.editext (644)) printed on the picking list. This will avoid copy and paste for all offer per area which are transferred into order. | This will avoid a lot of mistakes or forgetfulness and save time for CSOs and Hub (who has to ask for instructions when forgotten). | 4 | pano | 4 | 240 | yes | 29/04/2019 | May/June | IMPLEMENTED | 7471 | 10/04 cost should be placed on Sales unit France |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERc0uRzCiCRPrLuuGuom9DYBn5_fsTcUScVGzAsqxPcR7A?e=2dcPio
20/02/2019 | Fredrik Ström | Fredrik Ström | Lennart Johansson |  | HL Display Nordic |  | R19.3 Mar | 1J | Add Stamp in Proforma/CPI reports in 1210 | moved from Salmon project | 5 | pano | 10 | 600 | yes | 11/04/2019 | March | IMPLEMENTED | 7392 | Feature from the scope of project Salmon
26/02/2019 | Christer Sahlen | Fredrik Ström | Lennart Johansson |  | HL Display Nordic |  | R19.4 Apr | 1J | Additional flow for DHL and Freight values part1 | moved from Salmon project | 5 | pano | 19.25 | 1155 | yes | 11/04/2019 | 19/04/2019 | IMPLEMENTED | 7402 | Feature from the scope of project Salmon
11/03/2019 | Christer Sahlen | Emilia Hermiö | Lennart Johansson |  | HL Display Nordic |  | R19.4 Apr | 1J | Freight cost calculation DHL Parti part 2 | moved from Salmon project | 5 | pano | 14.75 | 885 | yes | 11/04/2019 | 19/04/2019 | IMPLEMENTED | 7420 | Feature from the scope of project Salmon
28/03/2019 | Emilia Hermio | Emilia Hermiö | Lennart Johansson |  | HL Display Nordic |  | R19.4 Apr | 1J | Improve QV report MTO for inventory management class | moved from Salmon project | 5 | pano | 15 | 900 | yes | 11/04/2019 | 19/04/2019 | IMPLEMENTED | 7447 | Feature from the scope of project Salmon
19/03/2019 | Christer Sahlen | Fredrik Ström | Lennart Johansson |  | HL Display Nordic |  | R19.4 Apr | 1J | Proforma reprint improvement | moved from Salmon project | 5 | pano | 16.5 | 990 | yes | 11/04/2019 | 19/04/2019 | IMPLEMENTED | 7437 | Feature from the scope of project Salmon
26/02/2019 | Christer Sahlen | Fredrik Ström | Lennart Johansson |  | HL Display Nordic |  | R19.12 Dec | 1J | Freight matrix cost UPS | moved from Salmon project | 5 | pano | 4 | 240 | yes | 11/04/2019 | Nov/DEC | IMPLEMENTED | 7401 | Feature from the scope of project Salmon 27-06 still waiting for Centiro 12/11 Centiro prepared labels, IT need to upload data into system; during test
05/09/2018 | Erwan Lardic | Fredrik Ström | Lennart Johansson |  | HL Display Nordic |  |  | 1J | Automatic Dispatch notice information - Part 3 Mail engine | moved from Salmon project | 5 | pano | 12 | 720 | rejected | 04/03/2020 |  | REJECTED | 7144 | Feature from the scope of project Salmon 27-06 still waiting for Centiro 04/11/19 files are sending now, we can start development 17/12 Ida will check if still needed this solution 16/01 Project Logent will cover that part
05/09/2018 | Erwan Lardic | Fredrik Ström | Lennart Johansson |  | HL Display Nordic |  | R20.01 Jan | 1J | Automatic Dispatch notice information - Part 2 Reception of Track and Trace link from Carrier company | moved from Salmon project | 5 | pano | 20 | 1200 | investigation | 17/12/2019 | Nov/DEC | IMPLEMENTED | 7143 | Feature from the scope of project Salmon 27-06 still waiting for Centiro 04/11/19 files are sending now, we can start development 17/12 Ida will check if still needed this solution; Development is ready
28/03/2019 | Sarah Lucy | Peter Moser | Andreas Astgård |  | HL Display Schweiz |  | R19.11 Nov | 1J | As each year we have our stock take inventory. This year on 31st October + 1st November. We need your help to upload all new balances on 1st November 2019 in the afternoon | To save time cost and improve effectiveness | 5 | pano | 8 | 480 | yes | 12/11/2019 | Oct/Nov | IMPLEMENTED | 7680 | 29/04 we will keep this request open till October and then start working with it |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ed1GsEUtTFlOotBF36mwsZwBXZjEOQ_tiHnNsc5cu9CURg?e=gYYxbN
19/04/2019 | Joanna Rosol | Joanna Rosół | Andreas Astgård |  | Costs info in comment |  | R19.11 Nov | 1J | At present Gliwice factory use WMS application only to make simple warehouse transfers between locations by manual typing in smartphone. We would like to expand functionality of this application through adding additional features for manufacturing orders preparations. Program mru 2. Detailed specification in separate document. | Thanks that feature we will improve time for manufacturing order preparation, eliminate mistakes made by manual management of picking components and materials to manufacturing orders, eliminate stock discrepancies. This functionality can be used within all factories and to added value orders. Estimated annual savings 58 k PLN | 5 | pano | 44 | 2640 | yes | 20/05/2019 | Nov/ Dec | IMPLEMENTED | 7508 7685 | 29/04 check with Stephane and other units 20/05 cost will be share within FRA, GLiwice HUB and Factory 10/06 suggestion of new way advised to all unit. Proposal to use PowerApps tool instead WMS application |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESI3hF61EmBHmpz402ZR5tkBOwdUtjsPCX6Zy9KcvEwP7Q?e=pOTRXD https://hldisplay.sharepoint.com/:x:/s/itdocumentationrepository/EW2c8iQRh2RGhtjdHngk5lMBog6a-QCsfnzi_nzZdjOvPQ?e=sRpqgt
25/04/2019 | Stephane Carrivain | Stephane Carrivain |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | Switch supplier Blysk | Mandatory to be able to continue partnership with Blysk Avoid manual creation of 172 records Needs to be deployed to Prod ASAP if possible without waitning the HL IT release | 4 | pano | 1 | 60 | yes | 29/04/2019 | 29/04/2019 | IMPLEMENTED |  | 25/04 pano: no developmnet needed, tool GIFT in Jeeves can do that 29/04 update done on Prod no feature - GIFT |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ef3JQbV04C9NmsLjMKGdvXIBzU1BFhWx84SCCj-YaazVbw?e=7EntB0
29/04/2019 | Kinga Szygula | Małgorzata Stasierska | [5 empty] | 1J | CURRENTLY WE DO NOT HAVE A SOLUTION THAT WOULD SUPPORT CALCULATION OF ADDED VALUE ITEMS THAT CONTAIN COMPONENTS FROM EXTERNAL SUPPLIERS. SIMPLE FLOOR DISPLAY CONTAINS OVER 20 COMPONENTS, WHERE HALF OF THEM IS FROM EXTERNAL SUPPLIERS (EXAMPLE ITEM 985522 IN 1810). CALCULATION IS MADE IN HUB AND NEEDS TO BE UPDATED SEVERAL TIMES PER YEAR. MANY COMPONENTS ARE BOUGHT BASED ON PURCHASE PRICELISTS [BPRH]. PRICE FOR THOSE COMPONENTS DEPENDS ON QUANTITY AND THEREFORE WE NEED TO MANUALLY CHANGE PRICE ON ALTERNATIVE SUPPLIER [AL] AND RECALCULATE PRICE FOR STAND [ARKH]. THE IDEA IS TO ADJUST CURRENT CALCULATION LOGIC, SO THAT IT WOULD INDEPENDENTLY CHECK PRICE FOR GIVEN QUANTITY ON PURCHASE PRICELIST FOR EXTERNAL ITEMS [PRODUCT GROUP = OTHER] AND USE BASE COST FOR INTERNAL ITEMS. FUNCTIONALITY WILL CHECK IF EXTERNAL ITEMS HAVE VALID PRICELIST AND CALCULATE PRICE IF THIS CONDITION IS FULFILLED. | IMPLEMENTATION WILL ALLOW TO CALCULATE PRICE FOR ITEMS THAT CONSIST OF COMPONENTS WITH PURCHASE PRICELISTS. CURRENTLY, MOSTLY BESPOKE FLOOR DISPLAYS (CA. 200 TOP ITEMS) COMPONENTS HAVE PRICE LIST, MAJORITY OF EXTERNAL ITEMS HAVE PRICE RANGE WRITTEN IN NOTES, BUT PRICE LIST SOLUTION IS PLANNED TO BE DEVELOPED FURTHER BY PURCHASING IN NEAR FUTURE. PROPOSED REQUEST FOR CHANGE WILL DESCREASE MANUAL OFFERING TIME IN BOTH PURCHASING AND ADDED VALUE. TODAY IT TAKE 1-2 HOURS TO MAKE FULL CALUCLATION FOR ONE FLOOR DISPALY. CALCULATION HAS TO BE UPDATED SEVERAL TIMES A YEAR. PROPOSED FUNCTIONALITY CAN BE ALSO USED TO OTHER TYPES OF PRODUCTS. RIGHT NOW, IN SUCH CASES, DURING EACH MASS CALCULATION, PRODUCTS WITH EXTERNAL ITEMS INSIDE HAVE TO BE MANUALLY VERIFIED FOR CORRECT PRICE CALCULATION. PROPOSED DEVELOPMENT IS ALSO CRUCIAL FOR AVOIDING MANUFACTURING DIFFERENCES, AS PROPERLY DONE CALCULATION WILL ELIMINATE BIG DEVIATIONS DURING PRODUCTION REPORTING. ROUGHTLY ESTIMATED MONTHLY SAVING AROUND 500 EUR | 5 | pano | 80 | 4800 | onhold | 10/05/2019 |  | ON HOLD |  | 29/04 expanded request from B.Wowra, discussion will be continue on Simplified Value Added solution on 7th of May 10/05 ONHOLD The background of such decision is that Lars just started discussion with sales/purchase how we should work with the calculation. The basic assumptions and steps are included in Lars presentation which you can find in enclosed files. The goal is to limit number of recalculation which are done today and learn to work with deviations Till the end of this business discussions all developments concerning the way how items are calculated should be put on hold |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcaSngIKvCVLjUPlgTUUp-gByjw6tno5iKZNisowk3dj3w?e=uFbIVx
04/06/2019 | Fredrik Strom | Lars Ämtenmyr | Andreas Astgård |  | HL Display Nordic |  | R19.6 Jun | 1J | We have discovered that in Jeeves we have wrong transport LT for parts of Norway and Finland. | High impact on business since we provide internally and to customers wrong ETA. | 5 | pano | 8 | 480 | yes | 04/06/2019 | June | IMPLEMENTED | 7536 | 04/06/2019 Urgent request approved |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESY40DkMx7xGuwNRsFaZxjgBwWm1eM1eLkBi0lCfDgW0pQ?e=MVcLOc
14/06/2019 | Wiliam Ellis | Stephen Mepsted | Andreas Astgård |  | HL Display Harlow Ltd |  | R19.11 Nov | 1J | Improve REQ delete button Within Xbia, currently when Planning, Purchasing or Procurement delete past requisition rows before re-planning One Jeeves delete all users requisitions in the current company. We require the functionality to select a particular range of requisitions, after selecting delete rows until button, ideally to select type of requisition manufactured or purchased and the users name. | This would allow the users to work independently from one another rather than having to check with all users in your department and others before deleting rows. The tick boxes and the dropdowns inside this program suggest that this functionality was intended when developing Jeeves. | 4 | pano | 4 | 240 | yes | 14/08/2019 | Sept/Oct | IMPLEMENTED | 7608 | 08/07/2019 PL, FRA HUBN not interested, Eazystock generate itself REQ and PO orders, REQ not run then in Jeeves 15/07/2019 Last week we talked with William about this topic and we think we can improve solution for manufacture requisition. We would like create new button in program "bia2th" which after run will remove existed not used Manufacture REQ. 04/09 cost will cover by Harlow Factory |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EahVyxrPuP5Bp9N17owJ9OABuyTeOWC_0x-TuEushIOvOA?e=T6WRtW
11/06/2019 | Bartosz Wowra | Lars Ämtenmyr | Lennart Johansson |  | HL Display Nordic | Costs info in comment | R19.10 Oct | 1J | I would like to put some additional columns in background tables: LT for booking in “al” Supply MOQ and Inv Mgt Class in sr (package/BOM from article) Inv Mgt Class and Q-ty per pallet in “ar” | Being able to create extracts from 1J and create excel analysis from background tables which we use in order to manage data in 1J Set correct MOQ on MO articles Safe time to IT workers (today we need to ask to data) It’s around 0,5 hrs per month of IT team involve to extract data. In scale of year: 0,5x60 eurox12= 360 euro | 4 | pano | 4 | 240 | yes | 14/08/2019 | Sept/Oct | IMPLEMENTED | 7610 | 08/07-2019 contact all untis with full description 25/07 no obection from other units, cost will be taken by Nordic HUB |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EduIZtnRuDdFkNH0Nof64VwBkGvKm2IY-FU9_Pyc_nYBDg?e=oThHeC
05/07/2019 | Erwan Lardic | Lennart Johansson | Lennart Johansson |  | HL Display Distribution Center Europe sp zoo |  | R19.8 Aug | 1J | Export of 1810 company data for Eazystock | Purpose is to analyse how to handle BOM items with decimals in the components (whereas Eazystock reports errors as soon as a BOM cntains decimals) | 4 | ErLa | 2 | 120 | yes | 19/08/2019 | August/September | IMPLEMENTED | 7573
18/07/2019 | Stephane Carrivain | Stephane Carrivain | Lennart Johansson |  | HL Display France SAS (+ SASU DESIGN) | Costs info in comment | R19.9 Sep | 1J | Improve report Dedicated truck | RFC accepted and process implemented, but we need now one extra field to be taken into consideration It can happen that we have some order to be prepared, bur which needs to be send to a forwarder who will have to send on an island or abroad This kind of information is mentioned in the field ”Delivery notice 2” How often this issue occur? 1 per month Cost for development: 60€ | 4 | pano | 3 | 180 | yes | 14/08/2019 | Sept/Oct | IMPLEMENTED | 7609 | 14/08 cost will be cover by French HUB |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EfWx8zFwO2dPrJHgtlhub9cBZXVeoOvZF813KTafnWykKA?e=Y5qyyY
19/07/2019 | Katarzyna Zelwor | Magda Oczko |  |  | HL Display Gliwice Sp z.o.o |  |  | 1J | Data on item Multivo |  | 5 | pano | 1 | 60 | yes | 14/08/2019 | August | IMPLEMENTED |  | 12/08/2019 no feature needed but assist BC necessary 14/08 updates done |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVae4pYqn9tHi7_PJS6Za4IBcTjGuFIcyExz3UDivoPVOw?e=PYNy8B
22/07/2019 | Boguslaw Kuczynski | Małgorzata Stasierska | Lennart Johansson |  | Costs info in comment |  | R19.11 Nov | 1J | Rebuild view of dispatch program in tab HL Orders per date. Exclude Drop shipment orders from view. | Every department in our organization need to plan workload based on system data/forecast. To do so we are using jeeves report in olhucorl ‘HL Orders per date’ and according to this information we should to have a capacity to cover orders. Current view is not correct and it make mistake with counting capacity of shipment. | 5 | pano | 20 | 1200 | yes | 19/09/219 | Oct/Nov | IMPLEMENTED | 7648 | 14/08 cost should be share with sales unit RO,GE and HUB; check with Nordic and FRA, UK if they would like this change and share cost and check if they have the same challenge 12/09 cost will be taken by UK, FRA, PL, Nordic HUB plus RO, GE and AT sales unit |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdgBjpNnT2tJgwQloosB4CABU_25NHQOYemzm_VdZj8E0w?e=wDR4bg
10/07/2019 | Boguslaw Kuczynski | Małgorzata Stasierska | Lennart Johansson |  | Costs info in comment |  |  | 1J | Night rebooking job is good but covering only orders OK to pick (may be picked) without the picking list during the night. Because we are doing put away process between 6AM and 10PM every 1 full hour stock is adjusted and we have brand new order ok to kick = we are receiving the picking list. Those ‘new’ picking lists will be processed by warehouse in the same day. Because night rebooking job is not touching these orders we would like to have the same rebooking during the day. | To reduce number of physical operations on items where full needed qty is on one location | 5 | pano | 24 | 1440 | onhold | 13/02/2020 |  | ON HOLD | 7721 | 14/08 topic will be check with Stephane, Ida, Erwan, Christer 07/10/2019 FRA, Nordic and RDC 1810 are interested 17/12 check on meeting according booking chnages with other units 13/02 wait for WS March 2020 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EZj5oj31PDNKmif01DfD_EkBn3nfkz7mpIJl4p2zaFF5-g?e=Yieimv
09/08/2019 | Boguslaw Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | Customer Own delivery after Place order Every day we are closing the orders. Some of these orders require singed ‘customer delivers’. Those documents are added by SU on order1 as attached. When we are closing this kind of orders (always on olhucorl) we should to receive this extra needed delivery directly from the printer after pressing ‘place order’ button. Now ‘customer delivers’ are not visible as attached on olhucorl level and to be sure that all this kind of orders will be processed as final customer requires we have to receive an email from SU example: “Please be sure that order….. with dispatch date next week require signed (his) delivery note attached in order1”< this is bad way and we would like to be sure that we will receive this delivery directly from the printer and give to the truck driver. | At this moment we have to remember the email form ~3days ago otherwise we don’t have any field/information on picking list that order require customer deliver doc. | 3 | pano | 0 | 0 | closed | 17/12/2019 |  | IMPLEMENTED |  | 14/08 check on preCab Sales unit flow on Polish market and check if they would like share cost Marcin: Discussed within Pre-CAB sales meeting in August. Possible to use solution from 1710 with some adjustmend. Next steps within logistic CAB process. 12/09 during meeting we decided created guide (verify by Emilia) and training SU 17/12 agreed to close and check with Gosia if development is needed in future; current solution without dev IT |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EV5EcN_ypmxPp-i0EhtThJ0BJmkalHGfAIoj35mqqHRA5A?e=JVyCH5
09/08/2019 | Kinga Szygula | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo |  | R20.02 Feb | 1J | Create RedBull labels in 1810 HUB opened new KIT items for customer Red Bull and special labels are required. Factory already have Red Bull label implemented (REDBULL_BOX_LABEL_KTW_PRN_004). We need the same or similar solution in HUB to be printed on KTW-PRN-401. It should contain RB article number with barcode, RB PO no and other fields like in factory RB label. | This is customer requirement. Without this development, each time HB would need to ask factory for labels. After Bratwurst, number of HUB Red Bull kits increased. | 5 | pano | 8 | 480 | onhold | 14/08/2019 | 2020-02-20 | IMPLEMENTED | 7791 | 14/08 wait for project Priting Solution 16/01 this request will be cover in new project, sprint 204-205 est time for delivery 20/02 deliver on Prod in project Printing solution |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWqiRpL6Ya1Opm1HB82Mrc0BASRlQa0HeNDqt5BZXSmGNQ?e=XiX4OT
19/08/2019 | Laurence Lakafia | Stephane Carrivain |  |  | HL Display France SAS (+ SASU DESIGN) | Costs info in comment | R19.9 Sep | 1J | Additional text on Picking list regarding Sales online process | To have control of incoming Sales online orders and prioritized orders in warehouse | 5 | pano | 8 | 480 | yes | 19/08/2019 | August/Sept | IMPLEMENTED | 7605 | 19/08 cost supposed be taken by Sales French department |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUopiMoTPONPunKIYJ0_gvwBsPJbxP7sS1oom5nHSez0Ow?e=3NFixX
26/08/2018 | Stephane Carrivain | Stephane Carrivain | Lennart Johansson |  | HL Display France SAS (+ SASU DESIGN) | West | R19.9 Sep | 1J | Adjust Track&Trace with Schenker | Reduce transport costs | 5 | pano | 6 | 360 | YES | 26/08/2019 | September | IMPLEMENTED | 7621 | 26/08 last feature 7621 needed to improve button track trace it will be release Sept |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbaRrptAogxCvKDKgVzvZcABHSkxUs_nN7fwwyTZR3hfRg?e=ZD2sgO
04/09/019 | Iwona Gasz | Joanna Rosół | Lennart Johansson |  | HL Display Gliwice Sp z.o.o | Costs info in comment | R19.10 Oct | 1J | Please remove copy of report Delivery note in Gliwice factory, program ffhlevp | We throw away 4 reams of paper for a month. Savings of around 150 euros per year. | 4 | pano | 1 | 60 | yes | 09/09/2019 | Oct/Nov | IMPLEMENTED | 7644 | cost taken only by Gliwice factory |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Efox2Tm7dTBOrln3JpFo1eABH85EZm_KaGtUXJP9OzbY-Q?e=BDJhAM
17/09/2019 | Ida Modigh | Lars Ämtenmyr | Lennart Johansson |  | HL Display Nordic |  | R19.11 Nov | 1J | We have 4 computers used by pickers in the WH. I would like them to have a Zebra printer each to print labels (Centiro integration) | This will improve the effectiveness and speed of the pickers. It will also help to avoid mistakes as now everyone gets their labels from one printer it is easy to take the wrong one. | 5 | pano | 8 | 480 | yes | 07/10/2019 | Oct/Nov | IMPLEMENTED | 7662 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcjzH1L-ZHlLjwUvVBglaioBG_NWRMnJPY3G0OqRgpn3ng?e=QNk9N1
18/09/2019 | Boguslaw Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | We got Stokrotka Project for Poland with 210 POD to be send on DPD Stokrotka account (in the end of September 2019). We just need new CC to be added “DPD Stokrotka” anable to create labels by Jeeves (olhucorl) | We got a lot o shipments. Creating it on DPD Web portal and then labeling pkgs will take a lot of time. In the end of month | 5 | pano |  | 0 |  |  |  | REJECTED |  | 07/10/2019 fixed in different way without dev |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EfHX_61cVBhIt7g-UFtsp4MBBj0AMKlYbQivLrOOFmQaWw?e=hsaBco
27/09/2019 | Boguslaw Kuczynski | Małgorzata Stasierska | Lennart Johansson |  | Costs info in comment |  | R20.01 Jan | 1J | Remove empty bins while journal closing process. My request it to remove from the visible stock all empty bins to reduce the time of ‘hand work. This should be done automatically by the system and also it will be better visible when we have to receive to stock the same item in the future (on the scanner). | We are counting stock almost every day. When we are creating Journal list we can see empty bins with (historical bins but not so far). When we are closing this journal we have to remove those empty bins. We are sure that there is nothing because we are checking it. | 4 | pano | 16 | 960 | yes | 07/10/2019 | 2019-01-20 | IMPLEMENTED | 7720 | 07/10 cost will be shared within 1810,1210,1600,1710 RDC units |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUcRK6yGHnxDuC6e8u0eANwBnGCOEtuBNKq8eBMYbbpZFw?e=8XfJg1
27/09/2019 | Boguslaw Kuczynski | Małgorzata Stasierska | Lennart Johansson |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | Improve report Bin Replenishmnet | Since 2018 we are doing almost every day Replenishment (transfer from high located bins to low picking bin). This is very important because later operator who are doing order picking is taking goods directly from low picking bin. Picking process if faster. To be sure that we are doing replenishment correct without making a bad transfers we would like to see no of booked qty bot not in chaotic way like now but directly on the bin where jeeves did some reservation. Then we know that this buffer bin with booked qty and we cannot touch- it must stay because picking List is printed directly to this buffer bin. Right now we can see booked qty in total here and we would like to see per each bin. | 5 | pano | 10 | 600 | onhold | 07/10/2019 |  | ON HOLD |  | 07/10 wait for Stephane C. if he will start use it in 2020 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeZUjoLWIZlEkye1TOIPSC8BMY8Yov_oED6dSbm4RcApnA?e=h3uAsp
27/09/2019 | Boguslaw Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | For a long time we are creating RFC to improve our processes, reduce no of bugs, change something for better/easer future in all RDC’s. It happened many times when RDC Kleszczów create RFC and later completely accidentally we saw that ‘new tool’ is working since many rears in France Jeeves or Sweden. Examples: • Picking route- topic created in 2017 but now after 2 years we know that this is working fine for a long time in Sweden. Now we need to secure only departments on Picking List and improvement will be implemented. • Bugfix to reduce no of receiving qty but not more than on PO. This is working in France for a long time. Ty topic from 2018. | I think we should to meet minimum 1x year to see how much we are different and what we can implement from other RDC’s on our site. Since 2017 there was 4 Logistics coordinators in IT dep and now it’s really hard to find who/when did some improvements long time ago. | 5 | pano |  | 0 | SPECIFIED | 07/10/2019 | in whole year | IMPLEMENTED |  | No development needed? 07/10/ Gosia will setup meeting in twice per year within units and IT to discuss process |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcYCb_JcSkROlMzGXBq701cBeRTSstgIT6DsqgIm57XRRQ?e=p3ljbp
27/09/2019 | Stephane Carrivain | Stephane Carrivain |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | QV | A QV report already exists (On Time Delivery), but needs to be improved by adding a choice “Project” in the selection below Information will be collected in the field “project ID” from jeeves” oh.projcode | We currently measure the customer Lead Time, but would like To separate normal from “project” orders | 4 | pano | 4 | 240 | investigation | 07/10/2019 |  | REJECTED |  | Hania to check if Project ID already exists in DWH (2 hours dev needed) 07/10 different approach between 1810 (cube) and 1600 QV; meeting with Emilia and Laurence to check process wtih LT calc and Project assign 07/07/20 can be close it, Stepahne use cube |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUQrtRes43xKqZ2vnTc0fjUBrlqAYWxQUlt_rYfWL-NS7g?e=7uc2Cc
08/10/2019 | Stephane Carrivain | Stephane Carrivain | Lennart Johansson |  | Costs info in comment |  | R19.11 Nov | 1J | When we dispatch the SO – for some customers it’s necessary to make appointment and in this case the customer ask the “customer number” and for the carrier it’s necessary to check our deliveries notes on the boxes. They lost a lot of time. Sometimes on the boxes the delivery note is lost and in this case we receive a claim from them. Schenker ask an action very quickly Additonal field needed for extraction csv file | Some deliveries are delayed for this reason | 5 | pano | 6 | 360 | yes | 09/10/2019 | Oct/Nov | IMPLEMENTED | 7668 | cost will be taken by French HUB |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EW_mi4TD479DrVSVRC5SsJoBeiFLstyxWrMGJTccZiWNLQ?e=X2lvyp
14/10/2019 | Christer Sahlen | Håkan Tjernberg | Andreas Astgård |  | HL Display Nordic | Costs info in comment |  | 1J | Daily update alt supplier from INV mgm class | Create job to check once per day value on item inv mgt class and LT for booking on main agreement and do update according LT on INV class. | 4 | pano | 16 | 960 | yes | 12/11/2019 | Feb/March | REJECTED | 7722 | IT need to check perfomance of solution directly update or implement job to check differences and update LT 24/02 moved from release till WS Smoothie in April 04/05 moved to late Release (still wait for Project Smothie) 19/08 reminder sent to members 03/09/2020request was moved from Salmon project na drequested by Area Nordic, due that logic of classifiaction was changed it's not needed
22/10/2019 | Stephane Carrivain | Stephane Carrivain |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | Fixed the problem in order to win time when we print PL Avoid the risks of forgetting. When we want to print PL we haven’t an automatic button It’s necessary to select the fields needed. | The Pl are printed five times per day and per dpt- it’s necessary to select: Order Status (entered + planned) + to choose preparation day + allocation status: fully booked + Picking list print date (blank) + added value field. Time needed per issue: 2mns*5per day = 10mns / ADV+ preparation dpt = 20mns => Total time per week: 100 mns = 1h40mns | 4 | pano | 8 | 480 | onhold | 07/07/2020 |  | ON HOLD |  | Stephane will check if he can work in the same way like other units 07/07 onhold till check by Stephane |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXE_haZntiBEpX73dtUbnKIBwcw9JJ82rj4NDg_11Fhq4Q?e=lkQLol
24/10/2019 | Malgorzata Stasierska | Małgorzata Stasierska | Lennart Johansson |  | Costs info in comment | Costs info in comment | R19.11 Nov | 1J | LT calendar days to change in RDC units to working days | To stop causing problems for RDC and SU on replenishment, planning list and necessity to rebook stock between orders. | 5 | pano | 24 | 1440 | yes | 24/10/2019 | Nov | IMPLEMENTED | 7689 | Cost will be taken by all RDC/HUB units in 1J plus SDL factory |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcYOtc_1BUhNvbn7RmVgFdMBePjM9NC2BUd1LjYGLobjbg?e=BRL9Bi
30/10/2019 | Ida Modigh | Małgorzata Stasierska | Andreas Astgård |  | Costs info in comment | Costs info in comment | R20.01 Jan | 1J | Currently the Capacity Tool in jeeves is taking it’s data from order1, which means that when it’s looking at the number of orderrows it is not taking into account if the item needs to be picked in several locations. To get an accurate data we need to change this so it will take the data from the OLHUCORL program, where you can see orderrows per picking location. We would also like to keep the limitation on item class as it is now. | A it is now the tool doesn’t work properly. We may have 500 orderlines in order 1, but it’s actually 650 orderrows to pick, which means that the tool doesn’t trigger the pop up for sales at the right time. | 5 | pano | 10 | 600 | yes | 12/11/2019 | Jan/Feb | IMPLEMENTED | 7723 | cost will be shared within 1210/1810/1600 17/12 go first before Daliy update INM class |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EU1HS3Bda6dJs28L2FKuInkBKdgZwwfJNlhFzd7GI55LJw?e=hub6dn
04/11/2019 | Asa Wigren |  |  |  | Costs info in comment | Costs info in comment |  | 1J | Field for artwork needs to have more characters. Today it´s 30 but we would like to have 50. We also need to be sure that all text is visible on PO to supplier | We will then not need to rename artwork from customers and can use same artwork name as our customers. It will help us not to mix artworks and produce right content | 4 | pano | 8 | 480 | rejected | 13/02/2020 |  | REJECTED |  | Asa W:Split cost within sales and 1810/1210 RDC units. 12/11 contact Emilia if 50 signs is enough 04/12 Emilia/Asa confimred 50 signs are enough 17/12 Gosia will confirm with Maricn cost 13/02 Pawel will back to Asa W with conclusion - Supply Chain not cover the cost, no impact on reports (checked by Pawel). 04/03 moved to Sales, email was sent to Asa and Emilia |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWH31eFSenFCg0sSagaNXTIBZfxWZH5BoCv6Qi_Qc1d2pA?e=1iSktZ
04/11/2019 | Marina Stachowicz | Joanna Rosół | Christer Sahlén |  | Costs info in comment | Costs info in comment | R20.06 June | 1J | I want to change below marked boxes to be automatically entered. It should be editable for us.Program: BE →Received Deliveries Delivery note date,rcv: current date Bin: indelivery | This solution will help us at work every day. In 2018 factory Gliwice received approx.8.000 rows. If assume that it takes only 30second for one we spend 65 hours for enter the same data. It cost our factory almost 3.000 pln every year. | 4 | pano | 8 | 480 | yes | 16/01/2020 | MAy/June 2020 | IMPLEMENTED | 7809 | 12/11 no Joanna on the meeting 17/12 meeting will be scheduled with Marina and HUB 16/01 800E cost per year; cost will cover Gliwice factory |  | https://hldisplay.sharepoint.com/:b:/s/itdocumentationrepository/EbYdEdTnQtVPsmnpHaFN0NQBj2COrfU_ktlWpxryJy7o9g?e=QtVG7h
05/11/2019 | Stephane Carrivain | Stephane Carrivain |  |  | HL Display France SAS (+ SASU DESIGN) | Costs info in comment |  | 1J | We would like to be able to separate normal than Value Added dpt in order to be more accurate in terms of working-load prediction and as well for the CSO not to receive fake pop-up(In Area West, both normal and Value-Added orders are treated within 2 separate departments) | Create a button ensure Value Added order can be removed, and being sure that the pop-up to be received by the CSO is well created(meaning when a CSO is entering a normal order, mean the Added Box is NOT ticked, then the capacity defined by the warehouse for this dpt is well taken into consideration and not mixed with Value-Added orders – and vice versa) | 4 | pano | 10 | 600 | onhold | 13/02/2020 |  | ON HOLD |  | Request only for French HUB 12/11 no Stephane 17/12 no Stephane 16/01 no Stephane 13/02 relevant only for FRA, put onhold- Stephane will check with SU with new pop-up message |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeMbY3EPN1tHs-dclqSBgfoBuAcCSwcIp2LeT5ZI5gqLEg?e=K3Gnvz
06/11/2019 | Roseline Labrune | Stephane Carrivain | Christer Sahlén |  | HL Display France SAS (+ SASU DESIGN) | Costs info in comment | R19.11 Nov | 1J | Rebuild Code with ANSi signs in order to see accents in webtel service | The accents and umlauts aren’t forwarded correctly in EDI Schenker in the address. We risk some deliveries problems and it’s necessary to correct this problem as soon as possible. | 5 | pano | 4 | 240 | Yes | 12/11/2019 | Nov | IMPLEMENTED | 7716 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUJq8BfS8cxBolOtQoWo_H0BB9s9CX2YNQ7PfBqFpELNVQ?e=l5gURT
06/11/2019 | Marcin Nowicki | Małgorzata Stasierska | Lennart Johansson |  | HL Display Distribution Center Europe sp zoo |  | R19.12 Dec | 1J | Changing forwarder in order to generate substantial saving. Current forwarder to be replaced with two new forwarders. | Benefits Up to 400kSek R12 | 5 | pano' | 12 | 720 | Yes | 12/11/2019 | Nov/DEC | IMPLEMENTED | 7724 | 12 hrs for upload data into freight matrix |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdvN-XBImB5EiGWaI9Y0f1YBXQQNHetO5pUh01BR5kCsJA?e=tyHmHw
19/11/2019 | Jeannine Stutz | Emilia Hermiö |  |  | HL Display Schweiz |  |  | 1J | It does not accept the PoD address into the proforma invoice. (program “be) On the proforma invoice there is always the customers address for the delivery address and not the specific PoD address. | Correct proforma invoice, so we do not have to correct it manually. | 5 | pano | 8 | 480 | Move to PreCab Sales | 17/12/2019 |  | REJECTED |  | 17/12 moved to Sales PreCab |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdEO-bZRtZhCqMX-ew42hygBXWy4LhencHcnfQkKmllJ_w?e=vpZvSR
22/05/2019 | Andreas Astgard | Lennart Johansson | Andreas Astgård |  | Costs info in comment |  | R19.12 Dec | SHAREPOINT | DevCore contract system | With the agreement management you can monitor important dates for renegotiation, renewal and termination. With reminders with different alert levels and multiple levels of responsibility, you get a secure check of your agreements. | 4 | pano |  | 3300 | yes | 10/12/2019 | 2019-01-20 | IMPLEMENTED |  | The invoice should be sent to HL AB (ref Lennart Johansson) 10/12/2019 moved from Logistics CAB |  | https://hldisplay.sharepoint.com/:p:/s/itdocumentationrepository/ETZBF4yHCMBGmOd_UhpBRzEBs0Bs84geJkLC5qaL8igQKg?e=y9Zrzs
16.12.2019 | Malgorzata Stasierska | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | We would need to have a change regarding Sales orders booking rule. The intention is to have allocation of available stock to be limited to the PO/MO delivery confirmed date or item replenishment LT if no PO/MO placed. That logic should be aligned also with the new request regarding booking based on dispatch date and not any more based on order row creation date. In such solution the new booking horizon is defined by PO in status order acknowledged or higher and by MO in status preliminary planed. As soon as there is an open PO or MO in the planning list (which is already confirmed), system should only book the SO row if preparation date is before or equal to incoming PO or MO. All SO rows with preparation date after incoming PO/MO should not be booked and system should unbook them automatically. If there is no PO in the system, the booking horizon remains unchanged and equal to the item replenishment LT | The change will allow to limit booking horizon and synchronize it with replenishment. It will decrease the effective stock & increase stock rotation | 5 | pano | 48 | 2880 | yes | 07/07/2020 | 2020-11-01 | IN PROGRESS | 8034 8089 | 17/12 schedule meeting regaridng new changes in bookig logic to see full view of implemtantion and imapct on units 16/01 check with Lennart and Amin 13/02 waith for WS in March2020 17/06 probably it's a huge change, custmization needed from business, IT need to check posiblities - additional 12 hrs for investigation 18/06 organize meeting with members to get full list of conditons 01/07pano: first feature created for find technical solution F8034 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B88142D56-A667-43FF-A887-05E6420B6C3E%7D&file=M.%20Stasierska%20RFC%20SO%20booking%20rule.docx&action=default&mobileredirect=true
18/12/2019 | Emilia Hermio | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | Costs info in comment |  | 1J | Remove and adjust pop-ups during order update process after picking list is printed – today we have too many pop-ups and they appear when the order update is not relevant for WH. | Improve efficiency in CS and reduce frustration | 4 | pano | 16 | 960 | moved to Sales | 16/01/2020 |  | REJECTED |  | cost will be shared within CENTRAL RDC, UK, Nordic and Switzerland 16/01 contact Emilia, changes prepare on order are for customer satifaction and daily process 28/01/2020 moved to preCab Sales |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ETGPE385-MFHh_uinO1T5DwB8oirlSm5-A4MAcaWQltlVA?e=dY2woa
07/01/2020 | Maja Ostrowska | Małgorzata Stasierska | Lennart Johansson |  | HL Display Distribution Center Europe sp zoo | Costs info in comment |  | 1J | To inform regarding elephant order there is automatic e-mail send to the procurement. But that email is as well send each time when any change on SO is done e.g. change in date, status etc Elephant rules should concerns items where OP and EOQ are greaten then zero or OP is greater than zero. Items where OP is equal to zero and EOQ is greater than zero should be excluded from the rule. | Decrease time needed to read all e-mails informing about elephant | 4 | pano | 8 | 480 | yes | 19/08/2020 | oct-2020 | IN PROGRESS | 8117 | 16/01 Ida will check issue if is relevant like in 1810, contact Stephane if he is interested 24/01 FRA and Nordic not interested (but modifaction inside rule in 1210 will be happened) 13/02 Gosia/Maja will check if they would like adjust logic 30/06 meeting Scheduled, Sales wish additional changes 08/07pano: meeting with RDC and Sales, cost will be shared within Area North Sales + 1810,1210,1600 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Edi6shQEyuxOucc5WDgnjY8BGLEuNPHnmacMcFcsOiWyHQ?e=8rCitX
09/01/2020 | Boguslaw Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | Integration with GLS (similar solution to DPD): Here we need full integration: JVS <> GLS. To do so we need to have a meeting with their IT. | From wk2 we switched carriers to Romania from Gebruder Weiss to GLS (pkg). This change will save ~150tys PLN per year on transport costs (this is complete saving with Raben implementation also) per year on transport costs. Unfortunately, because of this switch we will are losing integration via Centiro. | 5 | pano | 40 | 2400 | onhold | 13/02/2020 |  | ON HOLD |  | 2020/01/13 Kamil: we need an investigation first in order to better estimate the development time. 16/01/ check other solution semiintegration, contact Bogus 13/02 wait for Logent |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVca8zmcpZBDgSV00WR6OkcBZqoZ9HfmnlJRgeK0bOC_tw?e=9M8Ksn
09/01/2021 | Boguslaw Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | Integration with Raben (solution similar to Dachser): Here we can have half-integration: JVS > WH Administrator (once per day) > Raben. To do so we already know how to do it and it is much faster to implement than for GLS. | From wk2 we switched carriers to Romania from Gebruder Weiss to Raben (pll). This change will save ~150tys PLN (this is complete saving with GLS implementation also) per year on transport costs. Unfortunately, because of this switch we will are losing integration via Centiro. | 5 | pano | 20 | 1200 | onhold | 13/02/2020 |  | ON HOLD |  | 16/01 check with Lennart if we should go this way or whole integration will be replace? 13/02 wait for Logent |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EU3NqLbqM7VGlI6y-CCS9aQBGJUT7nKVHMHiYScGjRJGCQ?e=Eu0N3i
16/01/2020 | Ida Modigh |  | Christer Sahlén |  | HL Display Nordic |  | R20.03 Mar | 1J | Currently when we make proformas for Norway the Drop Shipment orders also appear with a cost. Since they are not shipped with our goods they should be excluded. | Save time, as now WH admin has to remove this manually, or if they miss then we pay to much customs costs. | 5 | pano | 6 | 360 | yes | 16/01/2020 | Feb/March | IMPLEMENTED | 7808 | cost will be taken only by Nordic HUB |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXcNeMaF3kNNjhoQRt66b5YBa8_0ujmREoBlfa1JqEo_qg?e=dQ9Kwb
23/01/2020 | Stephane Carrivain | Stephane Carrivain |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | Booking logic for items with acquisition method “Manufacture to order point” | The booking is done according to the LT of the item. In order not to book a part of the stock in advance, we had decided to remove the 10 safety window days added on top of the Item Leadtime. Due to that, the booking, for such items, is done based on preparation date In order not to book too late and ensure that WHS will have time enough to prepare and ship the order (and to print earlier, ship earlier and then decrease the Customer Leadtime), we would like the system to book according to the LT from menu artikel:ac:ars | 5 | pano | 16 | 960 |  | 13/02/2020 |  | ON HOLD |  | 13/02 wait for WS in March 20 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcjqcqjHtJFLkRuP0PGTw34Bju60zLdGYbNczdJuAZfzMg?e=R1XHtR
30/01/2020 | Bartosz Wowra | Håkan Tjernberg | Lennart Johansson |  | HL Display Nordic | Costs info in comment | R20.06 June | 1J | Change desing in item balances of item view OrdQtyMO | Stock status is more visible | 3 | pano | 1 | 60 | Yes | 13/02/2020 | May/June 2020 | IMPLEMENTED | 7862 | 13/02 user can change that desing manually,payback quite quick; cost only on NORDIC |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B354C65E1-BE8C-4A7F-8BC4-AE04B2884C63%7D&file=B.%20Wowra%20Item_Balances.docx&action=default&mobileredirect=true
06/03/2020 | Krzysztof Mizielski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo | HL Display Distribution Center Europe sp zoo | R20.08 Aug | 1J | Actually, when warehouse worker is pressing button “place order” in program olhucorl in Jeeves, if carrier code is Dachser or Dachser FIX he received from Zebra label with SO number. We need on this label also postal code of POD address and country (if exist, if not form customer address) from jeeves that are: fr.ftgpostnr, fr.landskod – if below do not exist vfr1.ftgpostnr, vfr1.landskod - if exist It would be nice to get also total number of collies in this shipment, but it is additional. | Because of only SO number printed on those labels last time we made hudge mistake during labeling, what has impacted Red Bull customer (very important one) and generates additional 10k PLN of total costs to fix it. We need to avoid this in the future. | 4 | PANO | 6 | 360 | in progress | 16/07/2020 | 08/2020 | IMPLEMENTED | 7956 | 18/03 wait for Printing solution project 16/07 solution implemented during Printing solution project (label only for 1810) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQVKMEgdmlZIlamG2-aAwX4BAvIIZcp99sjgkR3_tKoOkQ?e=FcKIKE
18/05/2020 | Katarzyna Zelwor | Joanna Rosół | Lennart Johansson |  | HL Display Gliwice Sp z.o.o | HL Display Gliwice Sp z.o.o |  | QV | Adjustment in QV report MTO | Needed for the proper production planning vs. capacity during high season | 4 | pano | 36 | 2160 | yes | 22/09/2020 |  | INVESTIGATION |  | 17/06 request moved from Sales 18/06 Joanna need to check request with Katarzyna Z; Pawel will check options 16/07 Pawel prepared query which generate Planning list of orders from RDC - waiting for Kasia verification 19/08 Pawel will schedule meeting; consider ICT connection within factory and RDC - 36hrs dev time 22/09 Joanna wil check if Magda O. accept this cost, yes from Lennart |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbAAKWHPCtdJoODE2o3yt1YBVPVQFsHH_6iF_YUzqet43w?e=6qRAUt&CID=87384d84-138d-f0ef-095b-b24acf933298
11/05/2020 | Bartosz Wowra | Håkan Tjernberg | Lennart Johansson |  | HL Display Nordic | HL Display Nordic |  | 1J | We want to automate class entry for all items in 1210. When clicking "sellable" should appear: ars.artabc = E (main warehouse) and ar.q_hl_invmgtclass = N | Improve Eazystock extraction data from 1J. The benefit is proper stock organization and warehouse inventory control. | 4 | pano | 16 | 960 | NO | 19/08/2020 |  | INVESTIGATION |  | 18/06 check if requets if valid for all units used ES 16/07 request valid only for Nordic 19/08 schedule meeting, no approval from Lennart as solution is not for whole organization |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbzfFJ8UeFZJi0qnx1sYh00BVr5xu10xnJVEltatr3z_cQ?e=ycQykq
28/04/2020 | Fredrik Fallding | Håkan Tjernberg | Lennart Johansson |  | HL Display Nordic | HL Display Nordic | R19.10 Oct | 1J | 1. Add field in “Items” that shows the dynamic lead time from Eazystock (if dynamic lead time is used). 2. Change q_itemendcustomer.q_hl_deadline to local field and add to background list on “item” 3. Add ars.artabc to background list on “item” close to ar.q_hl_invmgtclass 4. Move ars.artabc close to ar.q_hl_invmgtclass in “xarla” background list 5. Add ars.artabc close to ar.q_hl_invmgtclass in “sr” background list (BOM) 6. Change field description of ar.q_hl_invmgtclass to “Sub class” and ars.artabc to “Inv Mgt class” | related to the Smoothie-project and EazyStock implementation. | 5 | pano | 1 | 60 | yes | 22/09/2020 | oct-2020 | IN PROGRESS | 8132 | 1. Create new field in Jeeves with working days logic 16hrs+ integration process improvement - interested 3 RDC units 2. Already exist request - 20 hrs (seperate request in row.97 from Maja O.) - interested only 1810/1210 3,4,5,6 1hrs 18/06 check request wiith other units related with ES 19/08 additional meeting is needed to review is necessary for all units 22/09 only desing chnage accepted - 1dev hr (point 1/2 not accepted) cost within 1810/01210/1600 08/10 during design changes we noticed that item and item blance doesn't have standard connection adn to secire correct visible Class values from stock we need to create macroterm |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EU8Nb6vyqcdLnHMVRgDr8iYBmHROegioSKYzJaX9J0583A?e=ROgTuU
26/03/2020 | Lennart Bjork |  |  |  | HL Display Nordic |  |  | 1J | We have a functionality in Jeeves where drawings are automatically uploaded / connected to a specific jeevescode when drawings are put in status production release. That works fine but it doesn’t include underlaying drawings in for example assembly’s we order. In my opinion this is not ready we must have all drawings attached so we avoid the manual work and mistakes. | We will reduce the number of manually added drawing to a minimum and in that way also reducing mistakes. It will also be more transparent for all that needs information. | 4 | pano | 32 | 1920 | investigation | 18/06/2020 |  | INVESTIGATION |  | 17/06 during investigation, waiting for feedback from CAD person to check technical posibilities |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EZNEh5RsX79HptBfTMi1MdkBKWMEQcGLuq42jDfsirVhYg?e=W9Ni5N
0
0
0
0
0
18/09/2020 | Lena Persson |  | Lennart Johansson |  | HL Display Sundsvall AB | Costs info in comment | R19.10 Oct | ERP2 SDL | Add Cusomter Order nr on Pallet spec labels | Increase customer satifaction | 5 | pano | 16 | 960 | Yes | 22/09/2020 | 2020-10-01 | IMPLEMENTED | 8115 | 22/09 two features needed each 8hrs per HL unit SDL 8hrs + change on Pallet spec report in 1J
23/09/2020 | Ida Modigh | Håkan Tjernberg |  |  | HL Display Nordic | HL Display Nordic | R19.10 Oct | 1J | DHL integration by Logent |  | 5 | pano | 8 | 480 |  |  | 2020-09-01 | IN PROGRESS | 8120
08/10/2020 | Emilia Hermio |  |  |  | HL Display Nordic | HL Display Nordic |  | QV | In the QV report ‘Freight Cost’ the field ‘Freight costs’ is not showing correct information from Jeeves. We want to see the real costs we pay for Logent from the field ‘Actual cost’ | Enables us to follow our freight costs vs freight charges | 5 | pano |  | 0 |  |  |  | IMPLEMENTED | 8146 | 15/10 implemented in Logetn RDC project |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Efzn-ewRqedIja4bbIAdk84BEWlpGkWNy-eAxMD_CsQOTQ?e=2Fcuqr
09/10/2020 | Paweł Nowak | Kamil Saczka |  |  | HL Display Harlow Ltd | HL Display Harlow Ltd |  | NICELABEL | Replace Receive row labels in beinlev program | [8 empty] | IN PROGRESS | 7936
09/10/2020 | Paweł Nowak | Kamil Saczka |  |  | HL Display Gliwice Sp z.o.o | HL Display Harlow Ltd |  | NICELABEL | Automatic labels for dispatch process in factory GL/HAR | [8 empty] | IN PROGRESS | 7660
09/10/2020 | Paweł Nowak | Kamil Saczka | [5 empty] | NICELABEL | Create documentation for Bartender (wiki) | [8 empty] | OPEN | 8086
09/10/2020 | Paweł Nowak | Kamil Saczka | [5 empty] | NICELABEL | Upgrade Bartender 2019 to version 2020 | [8 empty] | IN PROGRESS | 8099
Note on O102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pre-Study Cost only!

## Sales and Quotation
Process Leader |  | Emilia Hermio
Business Coordinator |  | Sonia Kurtz
Date | Requested By | Authorized By | Approved By | Business Consultant | HL Unit | HL Area | Release | Product | Description | Justification | Prio | Added By | Est Dev (hrs) | Est Cost (EUR) | Decision | Decision date | Est Deliv Date | Status | Feature ID | Comment | Cust notified | RFC Link
| Aleksandra Pawlińska |  | Emilia Hermio |  |  |  |  | 1J | After processing button "Adjust order for deliveries" system overwite existing information in field "External text" with info about PoD. There should be question if system should overwite ot add new text below | Avoiding errors | 3 |  |  |  | YES |  |  | REJECTED |  | 5034
| Aleksandra Pawlińska |  | Emilia Hermio |  |  |  |  | 1J | "Get multi file" button should work in order1 and xti https://drive.google.com/open?id=0B76Z_xXyAkTsV29SeTFEUWt5bU0 | To save a time | 3 | MP |  |  | YES |  |  | REJECTED |  | 4049
5-6-2017 | M. Pianka |  | Emilia Hermio |  |  |  |  | 1J | Button "print credit note request" should be local. | Currently in 1190 and 2400 we have old values from Nordic | 3 | MP |  |  | YES |  |  | REJECTED | 6171 | 12-3-2019 Marcin to check with Emilia. Mail sent with details. To have local values under button “print credit note requests” (claims) Rejected as too old requests
4-7-2017 | E. Lardic |  | Emilia Hermio |  |  |  |  | 1J | Trade Policy Adjustments | In case of creation of credit orders, it seems that these orders are appearing on the copied order automatically as cancelled. | 5 | EL |  |  | YES |  |  | IMPLEMENTED |  | 6255
21-8-2017 | A. Karlson |  | Emilia Hermio |  |  |  |  | 1J | Canceling of sending invoices | To have possibility to fix an error | 3 | MP |  |  | YES |  |  | REJECTED | 6310 | 12-3-2019 Marcin to check with Emilia. Mail sent with details. Additional button (program q_hl_maillog) to cancel email with invoice. Rejected as too old requests
22/08/2017 | Jannicke Holdorf |  | Emilia Hermio |  |  |  |  | One Jeeves | Already booked rows against incoming PO should be marked yellow in program order1. Currently users have to go to the planning list | To save user's time and increase overview. | 4 | MP |  |  | NO |  |  | REJECTED |  | 6363 / mail sent to Erwan if makes sense 01/03/2018: Marcin to check if the request is still valid
09-01-2018 | Małgorzata Stasierska |  | Emilia Hermio |  |  |  |  | One Jeeves | Email to procurement/added value department when sales order (or just row) is cancelled | To secure that proper actions in HUB are taken once the order/order row is cancel in aim to avoid over stock. | 5 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6694 // Mail to Erwan nad Paweł Nowak if we can use this functionality also in the rest of companies
24-1-2018 | Ewa Moskal (Stępińska) |  | Emilia Hermio |  |  |  |  | One Jeeves | 1) Need to block possibility to create item without logistic data 2) factory should have information about answer 3) Adding to main price list has to be improved | It is necessary to allow users to create items in HUB | 5 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6713 - Mail sent to Xavier - waiting for response
21.2.2018 | Marcin Pianka |  | Emilia Hermio |  |  |  |  | One Jeeves | Proper margin calculation. Two fields in estimator were prepared only for proper calculation of added value items. Purpose is to have proper vlue also for estimated items | There should be proper margin for estimated items - lots of complains from users | 5 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6798
28.2.2018 | Marcin Pianka |  | Emilia Hermio |  |  |  |  | One Jeeves | Export from QR to Word | Layout of quotation report after export to Word format is not ok. We found way to fix it. Exporting to Word is kind of workarounf (estimator has not so many option of adjusting layout like CRM) | 4 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6811
28.2.2018 | Katarzyna Zelwor |  | Emilia Hermio |  |  |  |  | One Jeeves | Sales assistant should appear on orders during drop shipment process | To improve customer cooperation (in factory we have persons responsible for key customers) | 4 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6814
2-3-2018 | Jannicke Holdopf Emilia Hermio |  | Emilia Hermio |  |  |  |  | One Jeeves | Field "Sales type" should be mandatory in ordofh | This is mandatory in order1, but not during creation orders based on offers. this is very important statistic information. It is just adding rule to program q_oblfieldh | 4 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6841
2-3-2018 | Vivian Li |  | Emilia Hermio |  |  |  |  | CJ Jakarta | "Sales person" in program fh | This is needed to have statistics to analyze invoices by KAMs | 4 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6858
08-03-2018 | West SU |  | Emilia Hermio |  |  |  |  | One Jeeves | Page break in quotation report. There should be checkbox to have possibility to put page break - to have next option/category on separate page | To improve control on report. Currently there is no such possibility | 4 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6837
08-03-2018 | West SU |  | Emilia Hermio |  |  |  |  | One Jeeves | There should be warning message "please choose proper localization" during drop shipment order creation | To increase control | 3 | MP |  |  | NO |  |  | REJECTED |  |  |  | Marcin to contact to Erwan about decision (such request should be handled within drop shipment process improvement)
08-03-2018 | West SU |  | Emilia Hermio |  |  |  |  | One Jeeves | Field "order specific text" needs to be created in estimator to have possibility to transfer information from offer to picking list row | Needed to have additional information for added value department or other information for warehouse which are connected only with special row | 4 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6830
8/3/2018 | Tinne Adams |  | Emilia Hermio |  |  |  |  | One Jeeves | Sorting quantity when we tiering in estimator | To have proper overview in quotation report. Currently it looks ok only when on row level we have lowest quantity. | 4 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6868
15/03/2018 | Area West Sales (Tinne Adams) |  | Emilia Hermio |  |  |  |  | 1J | Connection between customer offer and added value quotation. They want to have an added value item to show the work and the cost. And the added value dpt. Should be able to easily find this in the estimator | Less navigation in Jeeves Easier connection added value quotation. No connetion exists today | 4 | AEL | 12 | 720 | YES |  |  | IMPLEMENTED |  | Investigate exact requirement before creating feature. 2018-03-28: Laurence to investigate France needs. Business to decide on working flow that suits both. Then look if development/education is needed. Will be released 25/5 - feature 6830
27/3/2018 | Marcin Pianka |  | Emilia Hermio |  |  |  |  | 1J | Discounts in tiering | Discounts from tiering (estimator) are not properly displayed and transfered into order. | 5 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6872
28-3-2018 | 1600 Sales SU |  | Emilia Hermio |  |  |  |  | 1J | Default text for DS is missing on row level | To save time - such text is on row level (when type of DS) but many time there are mix types and such text should be place on row level | 4 | MP |  |  | YES |  |  | REJECTED |  | Request put on hold due to back to Excel in Area West 14.01.2020 - rejected due to proposed improvements within DS project
5-4-2018 | Laurence Lakafa |  | Emilia Hermio |  |  |  |  | 1J | Taric code and country of origin in advance payment template | Legal demand - necessary for sales outside EU | 5 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6896
12/04/2018 | L. Lakafia |  | Emilia Hermio |  |  |  |  | 1J | Sales support report improvements - Part 1 (easy changes) | 1/ Being able to exclude from the report all rows for which the allocation is done against stock (they want to keep only rows for which the goods are not available) => This seems to me reasonable and a good improvement 2/ When the user wants to see only rows with negative difference => They also can see rows with difference = 0 They want to remove rows with difference = 0 => This looks to me to be more a defect 3/ Default values Stock Item Only Y/N (No by default) DS order rows = Ticked by default 4/ Removing zeros (similar to 2?) REFACTORING!!! | 3 | EL | 16 | 960 | YES |  |  | REJECTED |  | Sales support report imporvements 6 points were highlighted, discussed within It dpt 2 weeks ago. I explained that we are reaching the technical limits of crystal report It is a MUST to have these improvements (correction of bugs + imporvements). Not being able to export datas to Excel is OK IF a query providing exactly the same datas can be created. It is a MUST to have these datas not only in Paper but being able to rework in Excel Erwan will discuss with Kamil and divide points depending on priority. (done points 24 & 26) Feature put on hold due to problems with developement of this report. refactoring is needed (or even writing from scratch using different technology). 14.01.2020 - Rejected - point is connected with the old version
12/04/2018 | Laurence Lakafia |  | Emilia Hermio |  |  |  |  | 1J | Sales support report improvements - Part 2 (impossible changes) | Laurence says she can’t export in a nice way to Excel and that has been already reported. To check together the status | 5 | EL |  |  | NO |  |  | REJECTED
12/04/2018 | L. Lakafia |  | Emilia Hermio |  |  |  |  | 1J | Sales support report improvements - Part 3 (important changes) | 1/ One more point to investigate : Order row booked against PO => as you know such rows appear in yellow in the planning list and in the edit field we can see the allocation with PO nr and PO row nr. It seems that such rows (booked against open PO) are appearing as available in stock whereas it should of course not => Can we check that together ? 2/ PO Booking (request from Emilia) What I mean is that in the Sales Support Report it doesn’t show any discrepancy on the EDD date compared to PO OA date since allocation is Fully Booked when the SO is booked against PO.CS should see the discrepancy in the report as “minus days” when EDD is not correctly set according to availability. | 5 | EL | 12 | 720 | YES |  |  | IMPLEMENTED |  | 10-7-2018 -> Mail to erwan to discuss details Skype meeting with Erwan planned to 13-7-2018 EL 13/07 : correct . In case of booking against PO (from program xorpbok), the allocated resource is "stock" (that point is correct), but the "Resouce available date" information is incorrect : currently it takes todays date instead of the date when goods will be availble in stock from the PO (should be est receipt date from po row) Moreover for such rows booked against PO, the allocated resource should be "Booked PO" Feature 7073 created to cover this point Release: August 2018 14/08/2018 : Feature moved to BTP status
17-4-2018 | L. Lakafia |  | Emilia Hermio |  |  |  | R19.2 Feb | 1J | Create of POD based on Excel file | To save a time, no not needed to create every single POD manually | 4 | MP | 24 | 1440 | YES |  | 15/2/2019 | IMPLEMENTED | 7140 | Marcin: Spoke with Kamil. Such developement will occur problems with database - replication issues. Another idea - tool to checking if such POD exist in system. 24 hours Kamil answer: Yes, there is such possibility, new feature could be created after approval from sales team This request could be done later due the fact, that it is time consuming. Of course there are benefits. It should be divided into two phases - just upload (part 1) and checking existing PODs (part 2) feature 7140 - release in February 2019
18-4-2018 | Joanna Skiba |  | Emilia Hermio |  |  |  |  | 1J | Upload of ORDERS based on Excel file | To save time. Currently orders with 300 lines and different customers has to be entered manually | 5 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6921
18-4-2018 | O. Pedroncini |  | Emilia Hermio |  |  |  |  | 1J | Information about advance payment in the summaryof invoice as summary, instead of row | To have proper information and make view clear for customers | 4 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6901
24-4-2018 | S. Roinard |  | Emilia Hermio |  |  |  |  | 1J | Move discount fields from "all fields" tab to "HL Entry" | Possibility to cancel dicount on rows with fees. | 4 | MP |  |  | YES |  |  | IMPLEMENTED |  | 6925
07-05-2018 | V. Auger |  | Emilia Hermio |  |  |  |  | 1J | Claims - messages about existing invoices should appera during registering, not saving | To save time and to avoid doubled records | 3 | MP |  |  | NO |  |  | REJECTED
9-5-2018 | M. Yi |  | Emilia Hermio |  |  |  |  | SZV CJ | They want to use ork for claims management. Return agreement template is needed | To manage claims, standard functionality in 1J. Only 1 crystal report is needed to be moved | 5 | MP | 20 | 1200 | YES |  |  | IMPLEMENTED |  | 6967/ To be investigated further by Marcin P.
9-5-2018 | S. Keller |  | Emilia Hermio |  |  |  |  | 1J | Text between order rows is not on correct place on invoice template from Austria. It needs to be printed on top of the order row. Same as on all other templates (order confirmation, order acknwoldegement, picking list, delivery note etc.) | To have the same layout like in OC, OA, etc. | 4 | MP | 10 | 600 | YES |  |  | IMPLEMENTED |  | 6965 / Relese earliest in June
20-2-2018 | S. Keller |  | Emilia Hermio |  |  |  |  | 1J | Adjust of global quotation report. | To implement global report in company 2400 and deliver there solutions, already developed for 1J. | 5 | MP | 24 | 1440 | YES |  |  | IMPLEMENTED |  | 6641 / release in June 2018
15-5-2018 | L.Lakafia |  | Emilia Hermio |  |  |  |  | 1J | Offer Analysis Number of offers registered Offers analysis Details of offers Hit Rate calculation ( conversion from offer to order) | Backoffice workoad analysis Track the business opportunities | 4 | LL | 16 | 960 | YES |  |  | IMPLEMENTED |  | To be investigated further by Marcin P. - report is existing in QV -> Marcin P. will send a link to everyone for testing and feedback Separate meeting 12-6-2018, waiting for feedback and propositions of change ----\Summary and RFC in point 55 (7058) Release: August 2018 | kaze 12/06: Quotation qlickview report: 1. Quantity - total, sum of all quotation rows. Price: sum of all prices. Why? Different quotation rows = different options. Value of the quotation row? 2. Hitrate - row status ordered. How will it look like in ordofh flow? 3. Timeline of offers in report - per quot date / inq date or valid to? | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/HL%20IT%20Change%20Request%20Form%20-%20Backoffice%20Management%20tool.docx?d=wec78691343b8487c9c4864625138fa00&csf=1&e=VkOLxT
15-5-2018 | L.Lakafia | [6 empty] | 1J | Sales per kit & Bom | Sales analysis => Number of kits sold + Corresponding Sales value / Item in BOMNot existing => Really needed for tender preparation . Manually done , one by one | 4 | LL | 24 | 1440 |  |  |  | REJECTED |  | To be investigated further by Marcin P. - report is existing in QV. Marcin P. will send a link to everyone for testing and feedback 10-7-2018 Meeting done, mail with info how to use it send 8-1-2019 Laurence needs too check it once again and back with more info 7-2-2019/12-03-2019 - Laurence will back with info 16.04.2019 - Stephanie will check with Laurence 21-05-2019 - Emilia will send info to Laurence about group decision. Laurence will check if this solution will cover her needs. 22-05-2019 Emilia sent email. Waiting for feedback 10.09.2019 Laurence will check and back to this point in the future. 11-02-2019 No feedback from French team. Closed. This point could be re-open based on info from 1600.
15-5-2018 | L.Lakafia |  | Emilia Hermio |  | HL Display France SAS (+ SASU DESIGN) | West | R5.14 Dec | 1J | Automatic Sales price & margin calculation from factory data | From factory pruchase data => be able to calculate the Sales price & apply the expected margin level Or from a sales price => be able to know what will be the margin | 4 | LL | 32 | 1920 | No common decision |  |  | IMPLEMENTED | 7016 | Erwan will share the link for Project Proposal for feedback: 7016 Erwan will prepare spec, to be discussed during next PreCAB meeting. OT 7016 is created and requires some minor adjustments regarding currency handling https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/Development%20Documentation/7016%20-%20Excel%20tool%20-%20Sales%20Price%20and%20Margin%20calculation%20(collect%20live%20datas%20from%201J).docx?d=w75fe80e23d1e447a921cd97909d4ad4a&csf=1&e=gbi6M4 |  | https://hldisplay.sharepoint.com/:p:/r/sites/hlabitprojectoffice/Delade%20dokument/Request%20for%20Candidates/Project%20Proposal%20-%20Margin%20calculation.pptx?d=wdd282086b7a04ae3af0265ec3297f02a&csf=1&e=OEdd07
15-5-2018 | E. Hermiö |  | Emilia Hermio |  | HL Display AB - Sales |  | R19.2 Feb | 1J | Automatic update of status in Estimator for all Areas | In UK quotations are automatically changed to status Expired when the due date is in the past | 4 | EH | 20 | 1200 | YES |  | 15-2-2018 | IMPLEMENTED | 7328 | Marcin P. to check the functionality. Incident SRX18519 Marcin: Checked by support and developers- we don't have such functionality, To discuss with Kay Answer from Kay 11-7-2018, new incident: 18864. For 1710 it was made within feature 657 kaze 12/06: very important for 1190 as well 8-1-2019: Marcin to check if we could adjust this job afor sales market level. If there is no possibility, then we can proceed with company level 7-2-2019 This functionality could be turn on when users will decide when it should be expired (number of day after expiry date)
15-5-2018 | M. Pianka K. Philips |  | Emilia Hermio |  |  |  |  | 1J | Global quotation report in company 1710 | Small feature (6-8h) is needed to enable global quotation report in company 1710. To give access to whole functionality | 5 | MP | 8 | 480 | YES |  |  | IMPLEMENTED |  | 6961/ release in June 2018
16-5-2018 | I. Santos |  | Emilia Hermio |  |  |  |  | 1J | Additional advance payment template. Just copy of existing one, but different title (INVOICE not TAX INVOICE) | Legal demand | 5 | MP | 6 | 360 | YES |  |  | IMPLEMENTED |  | 6964/ release in June 2018
24-5-2018 | A. Karlson |  | Emilia Hermio |  |  |  |  | 1J | Possibility to edit fields "district" and "municipality" in program customer (kus) | To save a time. | 3 | MP | 16 | 960 | NO |  |  | REJECTED |  | Kinga suggests to reject this point. Cleaning districts from Master Data
6-6-2018 | M. Stasierska |  | Emilia Hermio |  |  |  |  | 1J | Additional delivery notes (in all local languages) to have possibility to send goods from program ork. | To avoid Excel file, to have all information in Jeeves | 4 | MP | 60 | 3600 | NO |  |  | REJECTED |  | Info from Gliwice HUB: about 50 documents in April. Lots of developement is needed according to language versions. ======================== 12-6-2018 Leave it open, waiting for HUB move and additional investigation ======================== Mail from M. Stasierska (21.6.2018) - this issue will be covered outsuide Jeeves
6-6-2018 | S. Keller |  | Emilia Hermio |  |  |  |  | 1J | Additional changes in quotation report | Necessary to implement global report in company 2400 | 5 | MP | 10 | 600 | YES (one point from list) |  |  | IMPLEMENTED |  | Email (with details) sent to all participants. One point from list will be taken into account. The rest to be rejected.
7-6-2018 | T. Adams |  | Emilia Hermio |  |  |  |  | 1J | During copying offers in estimator system should copy information from fields “External text” and “End text” instead adding there default texts. | To save time and improve work | 4 | MP | 16 | 960 | NO |  |  | REJECTED |  | Currently default text is copying there Marcin will ask Tine how many times they have to change such text. Mail sent 12-6-2018 Marcin sent reminder 11-7-2018 Need to be decided how to work, because it is hard to set up parameters by sales markets.
12-6-2018 | M. Pianka |  | Emilia Hermio |  |  |  |  | 1J | Cleaning up districts in MD | To have real local data and to reduce number of elements in the list | 4 | MP | 8 | 480 | YES |  |  | IMPLEMENTED |  | Marcin sent (27-6-2018) list of districts and ask for assignement 10-7-2018 Few points left, probably from 1600, mail sent to confirm Feature 7088 (release = September 2018)
13-6-2018 | S. Keller |  | Emilia Hermio |  | Costs info in comment |  | R19.5 May | 1J | Additional fields in file using to upload order rows from Excel. Gliwice HUB is searching for an easier handling of “text between order rows” Erwan showed us category function in order1 program. To be able to use this function we need a small adjustment on automatic upload with excel in order1 program. Excel file should also include following fields: - Category -> Must have for the grouping of rows on picking list - Text between order rows -> Should be added while working on the file anyway - Order Spec Text -> Should be added while working on the file anyway - External Text -> Should be added while working on the file anyway | To save time and use functionality of grouping This will avoid to have to assign “manually” the category particularly in case of Austria / Slovenia where such orders can be quite important with 100 to 150 rows. Approx 80 such orders are handled by the warehouse 1810 per month. | 4 | MP | 16 | 960 | YES |  |  | IMPLEMENTED | 7424 | Marcin to check efficency and templates in 1810 Categories are visible only in crystal picking list. Crystal report is blocked in 1810. Need Erwan's decision here - it is connected with special picking list. Sarah to contact with Paweł Nowak - back to this point in January 2019 8-1-2018: To be discussed in February 25.1.2019 final proposition - OK with 3 new text - OST, TBOR and External Text. Paweł to check details how it works in the warehouse. 7-2-2019 Marcin to contact with Stephanie Roinard about details if it will do not distrurb 1600 sales process. Mail sent 8.2.2019. Confirmation by Stephanie 8.2.2019. To be released in May 2019 Costs: Area West, Area Central, Area NE, Area UK |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbOfw2S2nj5LmsAgboNIF78B8mid92Hj1BxcUfyzjyGvvA?e=eWNUJL
13-6-2018 | O. Pedroncini |  | Emilia Hermio |  |  |  |  | 1J | Additional templates for 1600 with UK VAT | Legal demand | 5 | MP | [5 empty] | IMPLEMENTED
04/11/2019 | Asa Wigren |  |  |  | HL Display Nordic |  |  | 1J | Field for artwork needs to have more characters. Today it´s 30 but we would like to have 50. We also need to be sure that all text is visible on PO to supplier | We will then not need to rename artwork from customers and can use same artwork name as our customers. It will help us not to mix artworks and produce right content | 4 | pano | 8 | 480 | YES | 10/03/2020 |  | SPECIFIED | 7908 | Asa W:Split cost within sales and 1810/1210 RDC units. 12/11 contact Emilia if 50 signs is enough 04/12 Emilia/Asa confimred 50 signs are enough 17/12 Gosia will confirm with Maricn cost 13/02 Pawel will back to Asa W with conclusion - Supply Chain not cover the cost, no impact on reports (checked by Pawel). 04/03 moved to Sales, email was sent to Asa and Emilia |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWH31eFSenFCg0sSagaNXTIBZfxWZH5BoCv6Qi_Qc1d2pA?e=1iSktZ
18-6-2018 | J. Bagniewska |  | Emilia Hermio |  |  |  |  | 1J | Country of origin should appear in invoice template | Legal demand - custom purpose | 5 | MP | 6 | 360 | YES |  |  | IMPLEMENTED |  | 7021 |  | RFC: https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESmz9Iua6o5LtwMItXMIVcABFUyctqgD-iEb2xtZrFB3Cg?e=wjJmEK
22-6-2018 | K. Zelwor |  | Emilia Hermio |  |  |  |  | 1J | Basic inquiry report from INQUIRY FORM. The report we have now consists of not enough information: only Inquiry number, country, product type (HB, IM, etc). What we need is more detailed information about: • quantities offered, • delivery dates required, • offered project value, • high value project, • material chosen for quotation, • printed or not. | We must have information from the market what is required by our customers and what are the trends. Without it we are blind to offer good solutions. We must react on time on potential big projects. We also should have better info about the material offered in quotations to set proper order points and react proactively on market requirements. Inquiry form is the platform of communication with Sales and gives us basic knowledge about the market needs. | 4 | kaze | 40 | 2400 | YES |  |  | IMPLEMENTED |  | Marcin: OK for me, but we should collect such data within QV report Double check if it max 40!! Feature 7067 Release: August 2018 |  | RFC: https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESNuVidreCVJroWOuPP-CAQBqtwVn335ewguFr-rP7UjQg?e=WR4BPN
05.12.2019 | K. Zelwor | [6 empty] | 1J | Estimator - information about base costs should be in HUB's base currency | Needed for HUBs | 4 | MP | 28 | 1680 |  |  |  | ON HOLD | 7799 7800 | Discussion is needed here - at least 16 development hours for 3 new fields (BC start, unit, pcs) 10.12.2019 Emilia will investigate business background and process. We will back to the point in January 2020. Marcin will check if there will be possibility to add information about BCs in customer's currency and check Harlow's solution. ================================== 2 suggestions: - additional 3 lines in estimator (row level) to have BC info in local/base currency - adjust Gliwice estimator template with customer's currency Marcin will investigate and estimate costs. 21.1.2020 Marcin sent info to Kasia with information about Harlow's solution. Additional meeting is needed. 10-03-2020 Marcin will explain it with Kasia 23.04.2020 Sonia will check the estimation of hours needed for these features 13-05-2020 7799 - 20h, 7800 - 8h |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERoM9Vbus-BGutU4TKi6Bp4BebH9zbhRszo4_6hrvb_eXQ?e=68u7yk
27-6-2018 | K. Philips |  | Emilia Hermio |  |  |  |  | 1J | When using Excel big order upload in order1, the lines on the order do not upload in the same order as the spreadsheet. | The lines do upload in the same order if using upload from excel or upload from csv therefore this should be the same. If you are uploading by store area or destination then the lines should be grouped accordingly on all paperwork (confirmation, delivery note etc. If picking as groups its easier to tell warehouse to pick lines 100-170 together instead of pick lines 100, 120, 170, 200 and 250 together | 4 | MP | 10 | 600 | YES |  |  | REJECTED |  | 10-7-2018 Marcin: Asked Kay to have example(s), which could be passed to our developers 17-9-2018 Rejected based on request from Kay. It seems to work correctly. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERH_N0G9s6xEn-Tl00uL8aQBmZqOPmgtJUmQCThuASoxKg?e=4Su2FF
06-03-2020 | K. Zelwor | [6 empty] | QV | Factory 1190 New report QV or new solution in Jeeves Based on current MTO report in QV What we need to see: 1. Open customers orders SO (exists or not) 2. Date of order creation 3. Order number, PO number 4. Item no, Item description 5. Stock item (MTS / MTO) 6. Quantity 7. Delivery date required. | Needed for the proper production planning vs. capacity during high season. Problem with daily requirements (stock or customer order - higher priority) | 4 | MP | 24 | 1440 |  |  |  | MOVED/DUPLICATED |  | 10.03.2020 Investigation should be done how to cover both points of this process (especially procurement). Nordic procurement (Fredrik)/Gliwice HUB procurement / Area West (Edwige)/ UK (Rob Smith) and Paweł Nowak (IT) 23.04.2020 Kasia will contact Fredrik and Pawel regarding the other solution |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbAAKWHPCtdJoODE2o3yt1YBVPVQFsHH_6iF_YUzqet43w?e=6qRAUt
3-7-2018 | E. Dufkova |  | Emilia Hermio |  |  |  |  | 1J | Only one copy of invoice is needed instead 2 in CZ and SK invoices | To save paper and money | 4 | MP | 2 | 120 | YES |  |  | IMPLEMENTED |  | 7066 Release: August 2018 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYF22f9XCn1LhRNA9vQ97FQBTQUJXNG7dJqEGFQoWZz2AA?e=kv4Rrh
5-7-2018 | L. Lakafia |  | Emilia Hermio |  |  |  |  | 1J | QV Offer reports adjustments: - both valid and offer date on header - Month/year/week dynamic dimension is needed both offer and valid date - Possibility to save favourite criteria - Add main customer segment (the same like on sales report) as dynamic value - hit rate is needed - both headers and rows | Have at Backoffice disposal a Qlickview tool enable us to follow, analyse and define monthly action plan in order to catch existing business opportunities . | 4 | MP | 12 | 720 | YES |  |  | IMPLEMENTED |  | 7058 Release: August 2018 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ef9-QiAsmbhIri8oc0NCaw8BEjpW8tCPjbQK9WFNXtZoVQ?e=yPledf
10-7-2018 | ALL Sales SU |  | Emilia Hermio |  | HL Display AB - Sales |  | R19.4 Apr | 1J | "Sales support report" review during next Pre-CAB meeting (November 2018) | There is no possibility to add more options, so we have to remove some less important functionality | 5 | MP | 8 | 480 | YES |  | 04/2019 | IMPLEMENTED | 7388 | Waiting for details from Emilia (discuss between sales units is needed). February - workshop - 2019! Common agreement. We will remove nearly half of fields and report will be created from the scratch. feature 7388 is for analyze.
22-06-2017 | Katarzyna Zelwor |  | Emilia Hermio |  |  |  |  | HLNet | Add Quotations to Article Search | My idea is to share quotes we make for one Sales Unit with other Sales Units. The aim is to give Sales Unit ability to find similar quote that has been done before and estimate to the customer. So generally, yes, I would like all valid quotes to be visible on hl net, but I think it would be good to have also an option not to show it (by specific status or field). | 4 | JH | 60 | 3600 | Move to Sales and ask for better justification. |  |  | REJECTED |  | 10/7: Use the offer report in QV instead /Kasia Moved from production to S/Q
13-7-2018 | L. Lakafia |  | Emilia Hermio |  | HL Display AB - Sales |  | R19.3 Mar | 1J | Add to the Excel file used to upload in mass orders into 1 J (different ways) the Project Number (not mandatory but as an possibility) | Being able to upload orders in mass is an important and real possibility to win in terms of productivity. This functionally is mostly used to manage important projects, with a huge amount of orders/ pod to registered. In main case this is linked to a project that need to be regularly followed and analyzed during and after the project period. We should be able to upload the project number linked, in the same tim instead of copy and paste it , one by one , in hundred different SO . => non value added task | 3 | MP | 12 | 720 | YES | 07/02/2019 | 15/3/2019 | IMPLEMENTED | 7374 | New 3 columns - sales type, project ID and customer reference |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXVcLWcNEH5FoqMcAHOqk2wB8M9KB8g3OhaBhmsgy-d11g?e=17CmgF
19-7-2018 | S. Keller |  | Emilia Hermio |  |  |  |  | 1J | Area West (1600) has the possibility to show subtotals of different options and categories on their offers: The same function should also work in all other entities (1210 / 1810 / 2400 / 3901 and probably also UK if it is not working there yet) | Customers want to see subtotals of different options/categories. That’s why we also need this function. | 5 | MP | 32 | 1920 | YES |  |  | IMPLEMENTED |  | No additional developement is needed. Only few developer's hours to prepre configuration and tests, but feature is needed./ Decision made by IT team 1-8-2018 due to previous comment 7093 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcZPU-f0LvZLqcnkShuxLJkBrbPbM7rIAQMZ6C2dhuwWrA?e=0kVfmp
19-7-2018 | J. Rosół |  | Emilia Hermio |  |  |  |  | 1J | Unblocked manual base cost change on offer level in estimator (program e) in factory. | At present Offering Team do not have possibility for manual price change. We would like to unblock this functions thanks’ which we gain: Speed and process simplification: average time for offer preparation in estimator program is approx. 40 minutes, for standard and modified standard items we can proceed with estimation based on historic data, there is no need to calculate price by estimator, our customers’ needs the official offer on pdf file; Price discounts/ global agreements: possibility to see and prepare official offer regarding price level according to management agreement; | 4 | MP | 16 | 960 | YES |  |  | IMPLEMENTED |  | Possibility to write only for factories? Parameter? 7111 - in progress, release October |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ES2d3qAML0pMl4ICg0-R4ewBGTSnDf4JqqcK60CpewRNXw?e=8eiFAo
27-7-2018 | L. Lakafia |  | Emilia Hermio |  |  |  |  | 1J | Country of origin should appear on FR and FR-EN invoices | Customers request. To improve customer satfisfaction. | 4 | MP | 8 | 480 | YES |  |  | IMPLEMENTED |  | We can copy solution from advance payment 7112 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EfzqUfaNz8tJjSeoXTRrqrQBmqk1hTMRbTR7LygbDFTYDw?e=FeQyAF
27-7-2018 | L. Lakafia |  | Emilia Hermio |  |  |  |  | 1J/QV | Field "Project" in QV "order statistics and details" report | Essential to a complete analysis of a project | 4 | MP | 12 | 720 | YES |  |  | IMPLEMENTED |  | 7110 (Release = October 2018) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ee6HoX5nYfNFhkU2EgwSPD0BbbERXaRyuuUwNU24c9vT6A?e=llSUmZ
27-7-2018 | T. Adams |  | Emilia Hermio |  |  |  |  | 1J | "offering lines start on page 2 – there is no automatic page break because jeeves takes info from 1 line automatically on 1 page so if external text is too long offer start on page 2" | "offer is something you send to the client, it looks terrible, you need to explain to the client that it looks weird because our system is not able to start offer on page 1" | 3 | MP | 16 | 960 | NO |  |  | REJECTED |  | Marcin: How much such offers (with big external text) do we have monthly? And how to control it? Workaround: export to Word format. rejected due fact, that this functionality will split also smaller texts. Marcin wiell send info. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERsQOd6VGlpOrVwO6nKVYXoBv0_I-ov14qh4tUR9e_zobQ?e=OCbxur
30-7-2018 | O. Pedroncini | [6 empty] | 1J | Additional address (sending address) is needed for some customers | Customers request. To improve customer satfisfaction. | 4 | MP | 40 | 2400 |  |  |  | REJECTED |  | EL, few comments : - All templates need then to be reviewed - sending of this information from estimator to sales order - ICT, EDI, external EDI ... - Integrations (carrier company Centiro, etc...) are probably out of the scope of this request 40h will be a minimum also depending on the number of companies impacted Laurence to discuss with Erwan, solution is needed BUT without such big developement. Meeting next week? 16-04-2019 Still no info 21-05-2019 Marcin will send email to Olivier and Erwan about result of investigation. Mail sent 23-05-2019 10.09.2019 Marcin will send a reminder 16.09.2019 Reminder sent 11-02-2019. Closed based on no input from FR team for a long time. It could be re-open based on request. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EX9WNl9uLJJOvs22FcNfh2QBcPdsGL2seqJ7rHpQpJynaw?e=CfTPzQ
1-8-2018 | K. Philips |  | Emilia Hermio |  |  |  |  | 1J | - Bigger HL and POS logos - Delivery address not visible in 1710 | Logo is for aesthetic purposes only but delivery address can affect VAT, delivery charges, dispatch terms etc so imperative that this is fixed | 4 | MP | 16 | 960 | Yes |  |  | IMPLEMENTED |  | - Logo - it has to wait, proposition from Kay is needed - Delivery address remove - accepted (feature 7107) Logo will remain the same. We will cover change of text "valid date" to "valid to date". To be closed in September. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbZDlW4TsXZIit08hYayJNwBr5BkXGS2AOrK6GZO0yYf2Q?e=QSB9i4
20-8-2018 | K. Zelwor |  | Emilia Hermio |  |  |  |  | 1J | Credit invoice templates are needed for compaany 1190. Currently there are only amendment invoice templates. Most important positions are: - Header: Corrective invoice/Faktura korygująca - reference to the invoice number and date of the credited invoice - VAT in PLN Neccessary to turn on functionality of corrective invoices (currently only in 1810) | New templates for credit invoice are required in 1190. In 2018 there appeared situations where only solution to issue amendment invoice was to do it by credit order (typically not used in 1190). Functionality works fine, but there is no template. | 5 | MP | 16 | 960 | YES |  |  | IMPLEMENTED |  | 7109 Issues during CFT in September. To be released in October. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYOCOth4bkZPiCT4jCMVessBX4LFdg5bTHw07AykkGXCyw?e=bfgiUz
20-8-2018 | E. Dufkova |  | Emilia Hermio |  |  |  |  | 1J | Additional texts regarding payment in CZ and SK invoices is needed | To improve customer satisfaction/ better payment management | 5 | MP | 4 | 240 | YES |  |  | IMPLEMENTED |  | 7108 (Release = September 2018) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbzDLaHYv-BLhfsKWAmFbWgBugLWnrtL15oZF8R4TNFY_w?e=OvxYic
20-8-2018 | M. Franke |  | Emilia Hermio |  |  |  |  | 1J | Small corrections of GTC (estimator) are needed for German version | Legal demands/ customer satistaction | 5 | MP | 4 | 240 | YES |  |  | IMPLEMENTED |  | 7107 (Release = September 2018) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdBeH-m1NolClnrkUgJ-tFcBzv0XYzWDfxFNtAw1hoBo2A?e=M3bbdn
29-8-2018 | P. Ślusarek |  | Emilia Hermio |  |  |  |  | QV | BOM fileds in Custom section in "Order statistics and details" QV report | To provide proper statistics and improving effectiveness | 4 | MP | 4 | 240 | YES |  |  | IMPLEMENTED |  | 7158 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQQfHSVc2HJGukGnSD1Nm-8BNqOZ2-aCvNFzKXdrykENEQ?e=PIZdmX
31-8-2018 | O. Pedroncini |  | Emilia Hermio |  |  |  |  | 1J | We have the possibility to send invoices directly by email when the tick box below is ticked on orderf. Even if the invoice has been sent by email, when we print all invoices, this one is printed and send to the customers. We would like to have this blocked, if the tickbox is ticked the invoice shouldn’t be printed. | With this functionality we will save paper, stamp, envelope, work time etc… the customer who would like to receive invoice by email, not need to receive it by paper and scrap it. | 4 | MP |  | 0 | NO |  |  | REJECTED |  | CSL to contact internally with all countries to check if this request will be ok for them. How about additional tick box for the print out? To be discussed in January 2019 Erwan to discus internally (q_hl_maillog + "print t o screen option"). To check results in February 2019. 7-2-2019 Laurence implemented solution without any developement using current functionalities in jeeves |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESX_bPYVVP9GuvN3gtkB0j4Bcge7KCwMuDGPERbh9Ix_Tw?e=X8wOdE
3-9-2018 | L. Lakafia |  | Emilia Hermio |  |  |  |  | 1J | Update of GTC. First version has to be implemented very soon. Second starting from 1.12.2018 Excel file with trade policy needed to be extracted | Company rules changed | 5 | MP | 8 | 480 | YES |  |  | IMPLEMENTED |  | 7157, 7189 Release in November 7273 - clean up |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ETlmMCjI1cJIiRSFw8f2NvUB7eaa6vpedCV92LxeHcbdxg?e=xej2vE
4-9-2018 | O. Pedroncini |  | Emilia Hermio |  |  |  |  | 1J | GBP VAT is needed for 1600 UK invoices | Legal demands | 5 | MP | 12 | 720 | YES |  |  | IMPLEMENTED |  | 7138 (Release = September 2018) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ef5tCyqyzHJGhAb_rxP49HkB9asMFJfIGAoLnD9lZn_YDA?e=ao9cuJ
5-9-2018 | J. De Vis |  | Emilia Hermio |  |  |  |  | 1J | Change description on BE/NL templates - 40 euro instead 35 | Changing of rules within these countries | 5 | MP | 4 | 240 | YES |  |  | IMPLEMENTED |  | 7156 - release in October |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeiwwKVL1vFMl7OAST7umzcBxK_oBWArp9uSYbprsg0D2g?e=ZChOXd
12-9-2018 | Mattias S. |  | Emilia Hermio |  |  |  |  | CRM | Dashboard update in CRM | To be synced with customer segment instead of user | 5 | KS | 10 | 1200 | YES |  |  | REJECTED |  | Kamil to decide next steps, responsibilities and who contacts Scirocco EH: To be postponed until Digital Transformation Manager starts with CRM project 14-01-2020: Quite sure, that it has been resolved |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/New/Request%20for%20Change%20-%20CRM.docx?d=we329b6111373412b81722a88c2c5d8b0&csf=1&e=sKFFlP
15-10-2018 | E. Serkina |  | Emilia Hermio |  |  |  |  | RU CJ | Update of all templates due to changes of VAT. In some templates such value is defined as stable text | Legal demand | 5 | MP | 12 | 720 | YES |  |  | IMPLEMENTED |  | Marcin to contact Margareta before decision Waiting for RFC 23-10-2018 - RFC and approval feature 7207 Release in November |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcoQU1C7QplIhkY2zfEkIysBEvZuizatMMvzkxIvo2E5Nw?e=H3Kf44
17-10-2018 | B. Rasinski |  | Emilia Hermio |  |  |  |  | RU CJ | Tool to export data from RU CJ to 1C. | Finance is not covered in CJ, but it is taken by external system. Currently data are prepared manually and 1C has right to run queries in HL database. Purpose of feature is to create job, which will be executing queries and send results using FTP server. It will make our system more secured and reduce manual work on our side. | 5 | MP | 12 | 720 | YES |  |  | IMPLEMENTED |  | Release in November |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EfArOBVpD2BNtVyGCqGGVUoBRnWI-lJ9RK6MBUI3oXR6TQ?e=QIxLhI
23-10-2018 | K. Zelwor |  | Emilia Hermio |  | HL Display AB - Sales |  | R19.2 Feb | 1J | Additional info about BC on estimator header | What we need is more detailed information about prices and also product (item description, item specification, quantity, base cost). We must have easy access to prices from estimator when searching the quotations (per material type, product etc.). We will lose sales. We will not be quick. We will have no chance to easy easily and quickly compare the prices. | 4 | MP | 12 | 720 | YES |  | 15-02-2019 | IMPLEMENTED | 7247 | Marcin: It should be done within program ofp, not estimator. 13-11-2018 Sarah will take opinions from HUBs and thet it will be combined with Kasia's request Feature 7247, which covers both points of view, To be released in February 2019 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ea_Pv9QDSY5HnmTg1FF686ABB1InGgf-A0_nlRidlK5Tcg?e=wI6ht7 https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYXoyKogmEVDnm0bpkSKM5gBPO2F0sFu7sG_WH5jYOK1Dg?e=gImGGe
29-10-2018 | M.Pianka |  | Emilia Hermio |  |  |  |  | 1J | Point to discuss: booking job, date management and sales support report | Current version doen not work properly. Bugs and performance issues. The same with sales support report | 5 | MP |  | 0 |  |  |  | IMPLEMENTED |  | Discussed 12-11-2018
02-11-2018 | K. Philips |  | Emilia Hermio |  | HL Display (UK) Ltd |  | R5.14 Dec | 1J | Customer item number should be visible in quotation report. There should be also kuar field in row level. | HL codes are not user friendly for customers. There should be tick-box to control it. | 5 | MP | 12 | 720 | YES |  |  | IMPLEMENTED | 7244 | Marcin: In program kuar (or estimator) we should have option to decide if kuar should be visible or not. 14-11-2018. There is no place to add new fields in main tab. Fields will be added in separate one. Functionality within feature 7244. release December 2018 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQ26RdTfcd1BqDwt1vp9L_sBHmL-OuAXQQnVBKosiqLu3A?e=iqHB5J
9-11-2018 | E. Hermio |  | Emilia Hermio |  |  |  |  | 1J | Point to discuss: ORK: closing day filled automatically and picking day as date from calendar | To provide SLA KPI | 4 | MP |  | 0 |  |  |  | IMPLEMENTED |  | Erwan will discuss internally if these rules are ok for Area West. Features 7241/7242. Marked as completed, becasue it will be provided within 6284 project
9-11-2018 | A. Mamińska |  | Emilia Hermio |  |  |  |  | 1J | Blocking of field with original invoice number | Users can modify this number, so there is number of errors in the system. | 4 | MP | 4 | 240 |  |  |  | REJECTED |  | Marcin to contact with support to check if it is defect. Yes, these are defects - 2073 and 2074. Covered as DEFECT - to be released in December 2018 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EX7CWLHz9uZCvBt_dsWCaYUB7FDCQ6FSKhkNPW92DfPEJg?e=tPLnl0
12-11-208 | E. Hermio |  | Emilia Hermio | [5 empty] | Point to discuss: Rules for non-Jeeves requests |  |  |  |  | 0 |  |  |  | IMPLEMENTED
13.11.2018 | L. Lakafia |  | Emilia Hermio |  | HL Display France SAS (+ SASU DESIGN) |  | R5.14 Dec | 1J | Update of BOMs and price lists | More info needed - missing file with details | 5 | MP | 8 | 480 | YES |  |  | IMPLEMENTED | 7240 | Feature 7240, plan for sprint 174 13-11-2018: Laurence will send details (what when item,hiwch should be used as replacement is already in price list). Erwan will check added value issues with MO (but it has no influence on feature). release in December 2018 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EavL7QilMu1Nr_NvGz8Kq9sBXk0cKi2yb2V781TK8zs7Yw?e=feIS8h
15-11-2018 | K. Philips | Duncan Hill | Emilia Hermio |  | HL Display AB - Sales |  | R19.1 Jan | 1J | Price unit factor should appear in global quotation report in company 1710 | It is necessary for customers | 5 | MP | 12 | 720 | YES |  | 18-01-2019 | IMPLEMENTED | 7290 | Marcin: There is idea to have dynamic price unit factor in quotation report. Depending on parameter: 0 – system doesn’t show price unit factor 1 – flexible solution, system shows price unit factor when at least 1 row has PUF > 1 2 – system always shows PUF Release in January 2019 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWMFm5h_TuNCiAVx_ALPNyoBuimrvYVZ3EE7B8WiRLi0KA?e=RVb07G
28.11.2018 | A. Wigren | [6 empty] | 1J | There is need to send 100-200 mails with invoices within the same time. | To save costs of labour | 3 | MP | 40 | 2400 | NO |  |  | REJECTED |  | Marcin to contact with Emilia to explain issue with sales unit |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbKkteFaMIRIrnTkLWubmEoBMxrdtotYgXUK5nME98l2nA?e=TqgPnx
29.11.2018 | S. Roinard |  | Emilia Hermio |  | Costs info in comment |  |  | 1J | Extend functionality of uploading orders from excel 1) POD is not handled in file 2) Sales assistant should appear automatically 3) PUF is not taken into calculation of price | If the RFC is not taken into account the interest of the functionality is very reduced because it will be necessary to return in each order uploaded to modify it (fulfill the sales assistant, check the POD and PUF…)and the risk of mistake is really high. | 4 | MP | 20 | 1200 | YES |  | 03/2019 | IMPLEMENTED | 7433 | Need to be discussed with France (January 2019). PODs on rows could be used within other Excel file. To be discussed in workshop (4th week of 2019) 7-2-2019 - PODs are handling - Marcin will contact with Stephanie about PODs/ Kamil to check if it should be a defect or maintanance - both mails sent 8.2.2019. 12-03-2019 Marcin to ask Kamil if we could decrease (remove point 1) - mail sent 12.3.2019 ============================== Decision from Kamil - costs should be splited 50:50 (IT:Sales). Cost for 1600 = 600 euro To be released in May |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ETah1vR1GMZCse-3G-rQc9gBGPnkKlnnYReVSVV6o8tHKg?e=bB4Smp
3.12.2018 | A. Wigren |  | Emilia Hermio |  | HL Display AB - Sales | North East | R19.1 Jan | 1J | Tickbox “large proj inv at end” should be also visible in program KUS. And populated to order1 during order processing | More efficient to have possibility to choos on customer than everytime on SO | 3 | MP | 12 | 720 | YES |  | 18-01-2019 | IMPLEMENTED | 7292 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ee57xJ3NQkFMsPUr-gG6Y48BShhd005W_cdTSvTRgLgz4A?e=KCZLpa
5.12.2018 | L. Lakafia |  | Emilia Hermio |  | HL Display AB - Sales |  | R19.1 Jan | 1J | As the GTC don’t fit any more on one single A4 page, the total number of pages need to appear on each Quotation report page (to be sure that the customer has received all pages and not only the first page of GTC). | Legal demand. We must be able to prove that the Customer has well received the full General terms & conditions (2 pages) | 4 | MP | 6 | 360 | YES |  | 18-01-2019 | IMPLEMENTED | 7289 | To be released in January 2019 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdLmSzMCao1MoTjn05wHvlgBCcZ5AQ-MZG6d5NZI7Ml8Yg?e=uL0Evq
5.12.2018 | S. Lucy |  | Emilia Hermio |  | HL Display Schweiz |  | R19.1 Jan | 1J | 2018 was the 20-years-anniversary for HL Display Switzerland. During the year we had an additional logo on all our templates. | As the anniversary-year is ending, we also need to remove the 20-years-logo from our templates again | 5 | MP | 8 | 480 | YES |  | 18-01-2019 | IMPLEMENTED | 7288 | To be released in January 2019 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EV7clJjI_aBPnxMnQhNrgekByp09u3UmjExCjN1S2nk_NQ?e=q2pg2g
10.12.2018 | K. Zelwor |  | Emilia Hermio |  | HL Display Gliwice Sp z.o.o |  | R19.4 Apr | 1J | Calculation of material costs per unit is needed. Point on hold due to investigation if such functionality for operation works fine |  | 4 | MP | 16 | 960 | YES |  |  | IMPLEMENTED | 7425 | Waiting for inc/defect. [#SRX20564] ODP: RFC_offering_estimator_material and operations value cost per unit.docx Marcin to contact with K. Zelwor to get details of investigation (8.2.2019) OK with developement. Ł. Sokół to discuss with K. Zelwor way of calculation |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Eduf-Yk7nfZLkQgPPKqsZZEBYUbgSjDkWQKHuxrpZBbg9Q?e=YinnRI
12-17-2018 | Howard Williams | Howard Williams | Emilia Hermio |  | HL Display (UK) Ltd |  | R5.14 Dec | EDI | EDI Booker Integrations |  | 5 | KS | 116 | 6960 | YES |  |  | IMPLEMENTED | 6951
20.12.2018 | K. Zelwor | [6 empty] | 1J | Country of origin should be visible on all invoices | Legal demand - necessary to send outside UE (custom purpose) | 5 | MP | 16 | 960 |  |  |  | REJECTED |  | Waiting for a final decision - discussion between sales and logistic departments in Gliwice factory. Workaround - possibility to add it as "external text". Marcin to find solution if we can have kind of flexible solution to cover this area. 8.2.2019 - still no answer from factory 12-03-2019 Kasia will take additional requirements 16-04-2019 Closed based on input from K. Zelwor |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYgnvXllAWtIkBHeRc3L_iIBINtOKgp6NsLCAXHScEYPvQ?e=QLhdy4
3.1.2019 | K. Zelwor |  | Emilia Hermio |  | HL Display Gliwice Sp z.o.o |  | R19.4 Apr | Inquiry Form | Update of Inquiry Form - Multivo | Changes necessary. | 4 | MP | 20 | 1200 | YES | 08/02/2019 | 19/04/2019 | IMPLEMENTED | 7387 | 8-1-2019 - Could not decided due to the lack of estimation from Euvic side. Will be proceeding in February Paweł Kardas took responsibility for IF. handover needs some time, so it could be done aproximately in April. Paweł Kardas and Mariusz Lekstutis will take this task when handover will be finished. Feature assigned to sprint 181 - expected to deliver in April 2019. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXK-ujCVCZ9OrxJtzRFjgVABDNdlUfBdLt78ou50CWQaPA?e=X4rrMv https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcyYswvAgklJoIDnVy7A1XEBQYUVbJ7qU1HgtEmscdqWuw?e=jmGtRA
4.1.2019 | A. Karlson |  | Emilia Hermio |  | HL Display Sverige AB |  |  | 1J | As we have dispatch terms DAP, we have an extra text on order confirmation that freight cost is added to the invoice. This text is now placed at the end of the invoice. We want to have the text at the same place as dispatch terms so it’s more visible for the customer. | For avoid misunderstanding regarding freight cost. | 4 | MP | 6 | 360 | YES |  |  | SENT TO PROJECT OFFICE |  | Marcin to prepare mockup and send to Anette. Accept if there is no huge developement and will be agreed by Anette. Mail sent 10.1.2019 Info from Kamil - it should be handled within Nordic project |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWmMZWuuWA5Po5DYTD4VjVEBT3cA4NBgVXXlMygL3i34KQ?e=1x34Ti
10.1.2019 | J. Steffen/E. Zhang |  |  |  | HL Display Suzhou Co. ltd |  | R19.8 Aug | QV | External sales from co 1180 (SZH) have in some cases exceptions that are manually mapped to correct salesmarkets in Qlikview. The mapping needs to be made on the lowest level where QV should show sales, Orders received, backlog etc values to sales market “United states” if Customer ID is 8748 and jeeves productaccount = 3800. If productaccount is not “3800” then current sales market “Other production” Should remain. | 1. This saves time for finance team, if we do not have this adaption they need to manually split sales during financial reporting. 2. Target and Bonuses are made by sales coming from Qlikview, if this is not Changed then if can have a negative impact on paid bonus to employees (US). | 4 | MP | 2 | 120 | YES | 16/04/2019 |  | IMPLEMENTED | 7490 | Important! This functionali could be implemented AFTER point 38 from IT CAB. 8.2.2019 - no final decision from IT CAB 27.2.2019 Marcin: Asked Julia to push this point during IT Pre-CAB (28.2.2019) 15.3.2019 - IT part of feature assigned to sprint 181. To be implemented in July. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EW3C27INb75CooO1YGPJvBIBSf3s7j3iFhIZ2F2DRQYsIg?e=C1Hi3D
10.1.2109 | B. Rasinski | Barys Rasinski | Emilia Hermio |  | HL Display OOO (Russia) |  | R19.2 Feb | CJ | Data table we get from Jeeves (the table part of the document) does not contain all the necessary lines of data. update your program that fetches data from SQL server and uploads xmls to our ftp with the following updated request for QV_Sales | To provide proper data for external finance system | 5 | MP | 4 | 240 | YES |  | 15-2-2019 | IMPLEMENTED | 7329 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYPePUaW9vBPnQUzay4yxFkBdqoyVVqTpOIAh9P-2xMtVw?e=hfqY85
11.1.2019 | D. Bonior |  | Emilia Hermio |  |  |  | R19.2 Feb | 1J | Please change registration number (PL and PL-EN footers) in companies 1810 and 1190 according to goverment decision | Legal demand | 5 | MP | 4 | 240 | YES |  | 15-2-2019 | IMPLEMENTED | 7336 | Costs should be divided between HUB (1810) and factory (1190) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcKnVZ0RVy5KvRKszxPIg9IBHxYrMtxtk19ZAKV2AH_-ZQ?e=NFAcOX
11.1.2019 | S. Tulasne |  |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | When we generate a pdf file in Crystal report for an invoice, or a customer quote, the name looks like: “rfaktsf2_18-12-28” & “q_hl_quot_nordic2v3”, which is absolutely not customer oriented. We’d like: • Invoice to be named with its number : ex= 9264521 • Customer quote to be named ”HL-+its number” : ex= HL-565223-2 | Time saving for sales assistants, who must rename this each time + no consistence between various files name | 3 | MP | 8 | 480 |  |  |  | REJECTED |  | 7-2-2019 Laurence will discuss it with Seraphie - back to this point in March 12-03-2019 Stephanie will check with Seraphie 16-04-2019 Stephanie will check with Seraphie 21-05-2019 Waiting for Seraphie to be back in the office 16.09.2019 Marcin sent mail to Jeeves (no #190917-000011). Answer - we don't have such possibility 11-02-2019 We already have a workaround. No answer from FR team for a long time. this point could be re-open based on request. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQ6Lou1WCztCtv5nwRbJMyMB9G6EIDROgvTS-y1QvWatDg?e=nMDp9D
06-05-2020 | S. Lucy | [6 empty] | 1J | Automation of sending invoices in Jeeves | As soon as an order is in status ”released for invoice” Jeeves should automatically send out invoices by mail / EDI |  | sonkur | 8 | 480 |  |  |  | SPECIFIED | 7989 | 07-05-2020 Initial discussion with Kamil and developers. A feature for investigation is needed 25-05-2020 Feature 7989 added, not in sprint yet |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BB8AF23B7-956B-4531-AE17-F352CF0E7E39%7D&file=RFC%20-%20Invoicing%20-%20HL%20Display.docx&action=default&mobileredirect=true
15.1.2019 | K. Philips | [6 empty] | 1J | Upload orders to order1 from customer portals / pdf. Currently process 10k orders manually which are downloaded as pdf’s from customers portals (Tesco C2O, CPW, DSG) | Reduces user error Free up % of time for CSO to concentrate on excellent customer service Speed of order to delivery for customer Customer retainment | 4 | MP |  | 0 |  |  |  | SENT TO PROJECT OFFICE |  | Marcin: From my point of view new small project will be needed E-comerce - to contact Magnus Ronn to cover these requestes within project. 7-2-2019 - Magnus will take responsibility of this point |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeGDCSJFz1hAm0CuU9sP2F8BroFKWYQaLwDPkgAk75TVZw?e=ezysdi https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcYEh-LA8O1BmmdRdyfbdiQByGsoz67sczy1lqHnPKfJ3Q?e=6EEI00
15.1.2019 | E. Dufkova | Vojtech Motl | Emilia Hermio |  | HL Display Ceská republika s.r.o |  | R19.3 Mar | 1J | Taric code is needed on collective invoices CZ and SK | Customers request. To meet CZ law | 5 | MP | 4 | 240 | YES | 08/02/2019 | 15/3/2019 | IMPLEMENTED | 7373 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ed04-FX86PpMgM15VxYxTO4Bwbs1MHoDm-og1x-QU6cwDg?e=57ZWFr
18.1.2019 | E. Lardic | Stephane Jacob | Emilia Hermio |  | HL Display France SAS (+ SASU DESIGN) |  | R19.4 Apr | EDI | Need of small investigation work in order to check if the new AUCHAN worldwide pricelist way of handling require a modificatin in the Integration between ARIBA & HL Display IT System (1Jeeves) It may appear during the investigation process that the validation of AUCHAN orders require adjustment (remove the price verification) | 7425 | 5 |  | 16 | 960 | YES |  |  | IMPLEMENTED | 7339 7408 | EL 01/03/2019 : Mail sent by ErLa to Stephane Jacob to inform that second feature 7408 (for 8h, invoiced to HL France) is created to process more test orders (within feature 7339, Auchan succeeded to send only one single test order with one single row which is not enough to fully approve the solution) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXlByFmmdHxLji5Av8h5NuUBekIeXVq7CD0NdCqJDXJOLA?e=ZOpU03
13.12.2018 | Tomi Yrjonen | Rasmus Michelsson |  |  | HL Display Suomi Oy |  |  | EDI | Field “Customer reference” in Jeeves is visible in normal printed invoices. That field is not visible in e-invoices. Because it is visible in printed invoices, it needs to be visible in e-invoices as well. | Better customer communication. Customer-required information on invoices can be handled much better. | 4 | MP | 12 | 720 | YES | 08/02/2019 |  | SENT TO PROJECT OFFICE | 7375 | Project Nordic/Salmon |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWlj60-6VcxPjOj5L9OlSkoB-teBWtuvZXOnNrTjpwLZAA?e=IM0McL | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWlj60-6VcxPjOj5L9OlSkoB-teBWtuvZXOnNrTjpwLZAA?e=IM0McL
23.1.2019 | J. Sundh | Anders Lautmann |  |  | HL Display Sverige AB |  |  | 1J | Update of assignment customer - sales person: All customers connected to: a) sales market SE b) financial groups groups: ICA, Coop, Axfood, Bergendahls These customers should be divided between Martin Lindgren and Malin Jonsson according to zip codes by proper assignment on customer level | Essential to follow new salesperson - orders and results | 5 | MP | 4 | 240 | NO |  |  | REJECTED |  | New sales person will not start work at HL, so request is cancled. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbuH7O_fSb9PhFK1aaCueqUBsSD_EGnEkfEgqAfKEHy9Mg?e=cek1dK https://hldisplay.sharepoint.com/:x:/s/itdocumentationrepository/EUidFGd8LxNFpu2De2loL74Bl1i2rSMZwMhA2iEDuLwO5A?e=RixkgE
28.1.2019 | M. Grzywacz |  | Emilia Hermio |  | HL Display AB - Sales |  | R19.3 Mar | QV | Adding field "Project Id" in QV report "New sales report" | Reduction of time needed to prepare reports regarding specific type of sale (Candy King) | 4 | MP | 2 | 120 | YES | 08/02/2019 | 03/2019 | IMPLEMENTED | 7377 | To check with Kinga if it should be a part of HUB 2 HUB project. And discuss with Emilia if project id is a proper field |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbLimkaVo1lArxh9IXFjDLsBxWCV1Jryv4FIvB4jVPBuZA?e=XwGhLc
1.2.2019 | S. Lucy | [6 empty] | 1J | 1) Tick box "Freight cost" should be unticked when there is order type = "sample" 2) The same when sales type = "free replacement" | Reduce possibilities of errors | 3 | MP | 8 | 480 | NO |  |  | REJECTED |  | 1) It is already in the system 2) Sales type is not connected with any logic currently |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EayUkC5puhpFiQvKVeZs32YBneltmxX3WY7FNbhOxvJ7IA?e=SVcXnx
1.2.2019 | S. Lucy |  |  |  | HL Display Schweiz |  | R19.12 Dec | 1J | Our biggest customer here in Switzerland forces us to send our invoices in “ZUGFeRD” format. Under the following link you find all information: https://www.dropbox.com/sh/pu27ghibl2mi0ti/AADfGiPT5oeYjEgA0bRuWbMPa/english?dl=0&subfolder_nav_tracking=1 |  | 5 | MP | 40 | 2400 | YES |  |  | IMPLEMENTED | 7538, 7539, 7559 | Feature is needed for investigation and start of developement. Sarah to contact with service provider (how about using standard format, for example EDI Fakt/XML) - costs and rules of cooperationd and handling formats. 40h ONLY when we use provider implementation of format = 120h 12.03.19: We decided to go with provider "DATA UNIT AG". Implementation Costs: CHF 1500.- Costs / Invoice: CHF 0.42 Needed Format: XML / Communication through SFTP or HTTP REST Testportal: Available What are next steps? When is it possible to implement in production? We need to give appr. timeplan to Coop.// salu 12-3-2019 Marcin asked Sarah to get technical specification form Data Unit. then we will be able to start analyze and (next) implementation. 21-05-2019 Marcin will discuss with Mariusz about possibilities to proceed and come back to Sarah. 23-05-2019 Mariusz sent email to Sarah |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Edjt1vo99ldNpw0J1gC0d6QBJbBQYeKTfqPDxMeIOFrIcA?e=kEbyie
1.2.2019 | J. Zagler |  | Emilia Hermio |  | HL Display Österreich GmbH |  | R19.4 Apr | 1J | Possible to add in Order1 in the row field (columns) these information: - Taric Code - Country of Origin. We will save lots of time by the Intrastat (we create a Excel-File) Form for the customer. Open the SO and only copy and paste thing. (Excel File enclosed in the e-mail) | Save time, reduce possibilities of errors | 3 | MP | 2 | 120 | YES |  |  | IMPLEMENTED | 7432 | 7-2-2019 Sarah to check QV Intrastat report. If it will bo not OK, then contact with Kay Marcin to provide access to report 12-2-2019 - Cost per license in QV 150 SEK / month for each user. More expensive than adding 2 new fields. I'm checking possibility from Kay now. / salu 14-2-2019 - UK solution is not working for Austria. They work with queries and VLOOKUP. Too complicated and time consuming. Austria wants to spend EUR 120.00 and implement these 2 fields into order1. I strongly support this decision. It's the easiest, cheapest and fastest solution. / salu |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXUoRFrF44BDpuyHYbVl1VUB_w23HDp3AHi7ehy73PONbg?e=PKz4YX
1.2.2019 | S. Lucy | [6 empty] | 1J | Preparation day should be added into planning list | Less unnecessary e-mails between SU | 4 | MP | 1 | 60 | NO |  |  | REJECTED |  | Long discussion, should be checked with logistic and purchasing departments 7-2-2019 Sarah will discuss with all countries within 1810, to be done after switching of Norway |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeiU5CXEHhNNpIEXgGM_3VgBL0JN7L9Vllq1bcRP1hjC7g?e=18MTpF
11.2.2019 | C. Becker |  | Emilia Hermio |  | HL Display Deutschland GmbH |  |  | 1J | Advance invoice is needed for German sales unit |  | 5 | MP | 8 | 480 | YES |  |  | IMPLEMENTED | 7435 | 12.3.2019 -> Waiting for German translation, Cordula is working on it |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Eek1O4kMSIVIuLy1tBBGclQB53q9MpR4hEAnd897YTISmQ?e=5SAKVJ
14.2.2019 | G. Wright |  | Emilia Hermio |  | HL Display (UK) Ltd |  |  | QV | Qlikview reports for Sales has dropped 2014 and 2015 and there is no other way to view this data. 2010 to 2013 are visible in a separate report so perhaps 2014 & 2015 can be added to this report. | Be able to view 2014 & 2015 Sales data | 4 | MP | 4 | 240 | YES | 16/04/2019 |  | IMPLEMENTED | 7465 | Idea is to have 5 last years in main report. And next 5 in a historical one 12.3.2019 - OK, BUT if 1710 will pay for it. 11.4.2019 - Reminder sent to G. Wright with information about possibilities of developement (if it will be paid) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERNB_Zh9l6tEnoeZIKKOFqQB5y6jjWmvWbpRB03YLdfsvg?e=hE0oW9
14.2.2019 | S. Juwarahawong |  | Emilia Hermio |  | HL Display Thailand Ltd |  | R19.4 Apr | CJ | The customer TAX ID is missing from Collective Invoice which is very serious for our customer regarding to Thai Tax Regulation. Customer will automatically rejects all the collective invoices which their Tax ID is missing and will not proceed the payment to HL Thailand. | No double work for manually adding the customer Tax ID on collective invoice and no excuse from customer to hold the payment. | 5 | MP | 4 | 240 | YES |  |  | IMPLEMENTED | 7428 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUBTAxfj5F1LsFUir13q9pIBeWvN2ahpriZWsUSFxm3HAg?e=fTtaBH
15.2.2019 | S. Lucy |  | Emilia Hermio |  | HL Display Schweiz |  | R19.4 Apr | 1J | Reprints of invoices & credits in company 2400 should only be printed once. Right now it is printed twice by default. We are talking about reprints in program: order1 and orderfu. We are only talking about reprints! First prints of invoice and credits still need to be printed out twice. | Less paper | 4 | MP | 1 | 60 | YES |  |  | IMPLEMENTED | 7426 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EV4gc5Xcs_NAgPxQT0JC60YBhxmht_CsdJU99VwWdFOaoA?e=Yyo7Vc
28.2.2019 | R. Huber |  | Emilia Hermio |  | HL Display Österreich GmbH |  | R19.4 Apr | 1J | VAT text "VAT exempt under Article 138 (1) of Directive 2006/112/EC" should be printed on the template without using option "order scecific text" | The invoice does not comply with tax laws | 4 | MP | 4 | 240 | YES |  |  | IMPLEMENTED | 7427 | We should uset VATTX program to prepare dynamic description. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EfhDukXVZMNCssYe_81U1joBx9EXVGk7gBXnimbOTzJM1Q?e=aVoRJW
4.3.2019 | E.Hermiö |  | Emilia Hermio |  | Costs info in comment |  | R19.4 Apr | 1J | Sales support report - work in progress, but it will cover only existing functionality. RFC is needed to add remaining parts. Mateusz estimated additional changes in sales suport report for 20h. |  | 5 | MP | 20 | 1200 | YES |  |  | IMPLEMENTED | 7429 | Please divide costs: - Area Central - Area NE - Area West - Area UK |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQczU5k-C7tDvhHeq8Y0WNgBocRPP1YvES--6UM9PvOJ1A?e=et1wYx
4.3.2019 | M.Pianka |  | Emilia Hermio |  | HL Display AB - IT |  | R19.4 Apr | EDI | Integration with Intergamma | Just to have entry in file | 5 | MP |  | 0 |  |  |  | IMPLEMENTED | 6942 7308 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeIqMWUDCW5HqtOd_SE6mk0BaBqoLoPd1sfkhVPb_cPvtA?e=uSj3h3
4.3.2019 | J. Steffen |  |  |  | HL Display Sundsvall AB |  | R19.8 Aug | QV | In co 1140 we have sales that currently displays at sales to market “Other”, but it should be counted as market “US” (Unites States), this is sales for US customer Siffron. We need to update mappingfile for Qlikview where sales from company 1140 to following customers should be mapped to sales market US. 5038,8748,50422 | 1. This saves time for finance team, if we do not have this adaption they need to manually split sales during financial reporting. 2. Target and Bonuses are made by sales coming from Qlikview, if this is not Changed then if can have a negative impact on paid bonus to employees (US). | 5 | MP | 2 | 120 | YES | 16/04/2019 |  | IMPLEMENTED | 7490 | It is similar to point 96. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ETFKaRL9Z25Oj_lyjZJzZ58BW2Le46TYGQc8m6vm_Z7eeg?e=T6a3Mr
7.3.2019 | D.Danescu | [6 empty] | 1J | Upload order from Excel - add order type and VAT rate |  | 4 | MP | 8 | 480 |  |  |  | REJECTED |  | 12-03-2019 Marcin to ask Dan about number of such orders/rows (keep Sarah in CC). 6.11.2019 Marcin sent email to check with Romainan team |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERJg3c0rAWVDid4xZRB6NGoBVbZi2lJ1SCnekk_SstpD5A?e=jgiVod
7.3.2019 | D.Danescu | [6 empty] | 1J | VAT texts should appear automatically |  | 4 | MP | 6 | 360 |  |  |  | REJECTED |  | Discussion with user - financial deprtmen in Poland and Romania have to check it (connected with point 119 - the same request) 6.11.2019 Marcin sent email to check with Romainan team |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERJg3c0rAWVDid4xZRB6NGoBVbZi2lJ1SCnekk_SstpD5A?e=jgiVod
12.03.2019 | S. Lucy |  | Emilia Hermio |  |  | Central | R19.6 Jun | 1J | Introduction for Advanced Payment Flow for Area Central (1810 + 3901) - templates for Poland, Austria, Czech and Slovakia |  | 4 | SL | 16 | 960 | YES | 28/03/2019 |  | IMPLEMENTED | 7466 | 12-03-2019 Sarah to contact with units and financial department - we already have PL and EN versions in 1810 and advance payment template in 3901 15-04-2019 Get templates for Czech and Slovakia, need to adjust Poland and Austria 21-05-2019 Still we don't have translations Part 1 will be implemented in June | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERYvxeQBa_pHsYlQOtA3OEwB9U01uCWXUSuK92D_lSqZHg?e=rIDyLi
07-05-2020 | S. Lucy |  |  |  | HL Display Schweiz |  |  | 1J | Payment slip Switzerland | All invoices in Switzerland will be digitilized, payment slip needs to be updated with QR-code | 5 | sonkur | 8 | 480 | YES | 27/05/2020 |  | INVESTIGATION | 8015 | 07-05-2020 Meeting on 27th of May |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B11E55818-7745-454A-9EB0-C297B0147BD0%7D&file=RFC%20-%20New%20payment%20slip%20Switzerland%20-%20HL%20Display.docx&action=default&mobileredirect=true
26.03.2019 | L. Lakafia |  | Emilia Hermio |  | Costs info in comment |  |  | 1J | During creation order from offer system should take email details from customer level. Currently functionallity works only for order created in order1. | 1- The invoice will be sent right away to the Customer for payment 2- No need to check or to register it manually 3- Less mistake 4- Cost saving (Postage costs) 5- DSO impact | 5 | MP | 8 | 480 | YES | 16/04/2019 |  | IMPLEMENTED | 7467 | Paid by all 1J Areas: North, West, Central and UK |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQHKNWEhRXlPjTXDfTPRkv0BIUkTHi7jaEmb3G905hRIoQ?e=PDfwNE
29.03.2019 | E. Serkina |  | Emilia Hermio |  | HL Display OOO (Russia) |  | R19.4 Apr | CJ | New address of RU sales office. | All templates have to be adjusted. | 5 | MP | 16 | 960 | YES | 28/03/2019 | 2019-04-19 | IMPLEMENTED | 7450 | BTP |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYh_fG7JygBEg8V7dgOMppYBZ_vbE5CRc973NCMs5bw_wA?e=nUIdql
03.04.2019 | K. Philips |  | Emilia Hermio |  | HL Display (UK) Ltd |  | R19.4 Apr | 1J | Tesco have changed their Purchase Order system. We quote and invoice up to 500 lines per order, we then invoice using an EDI package called Tungsten. The PO from Tesco comes in as 1 or 2 lines. Since the system changed in January none of our invoices have been approved as they now need us to add the PO line number to the invoice. We already have the field for this, we just need this field adding to the Upload excel big order template | Get our invoices paid | 5 | MP | 8 | 480 |  |  |  | IMPLEMENTED | 7456 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWW3EuYIfMpKl1a4OLLgj84B8B7oP5uA59epV09qnsuboA?e=PZXJ1p
05.04.2019 | E. Lardic |  | Emilia Hermio |  | HL Display France SAS (+ SASU DESIGN) |  | R19.4 Apr | 1J | The purpose of the Request is to investigate and implement following change: 1/ It is OK that ARIBA sends us prices with up to 4 decimals 2/ however, we need to make sure that when an order is converted from EDI (ohdedi) to Sales order (order1), the unit price is rounded down. | Send to customer correct invoices which will not cause any issue with fiscal organization | 5 | MP | 4 | 240 |  |  |  | IMPLEMENTED | 7461 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ET_qupdSridIvdHi9XxfamoBCRY3XqhwxRTvxSKWzHEkTQ?e=bij69D
|  |  | Emilia Hermio |  | HL Display Nordic |  | R19.4 Apr | 1J | Missing text in NO invoices EN: "Go to www.hl-display.no to see our terms and conditions of trading." NO: "Se www.hl-display.no for oppdatert versjon av våre standardbetingelser." | To increase customer service | 5 | MP | 8 | 480 | YES |  |  | IMPLEMENTED | 7444 |  |  | Part of 6284 project. Added here for invoicing purpose
|  |  | Emilia Hermio |  | HL Display Nordic |  | R19.4 Apr | 1J | Tieto - field "customer reference" and PODs in coll. invoices | To increase level of integration with Tieto (EDI invoicing) | 5 | MP | 10 | 600 | YES |  |  | IMPLEMENTED | 7375 |  |  | Part of 6284 project. Added here for invoicing purpose
|  |  | Emilia Hermio |  | HL Display Nordic |  | R19.4 Apr | 1J | Norway - go live support |  | 5 | MP | 12 | 720 | YES |  |  | IMPLEMENTED | 7350 |  |  | Part of 6284 project. Added here for invoicing purpose
11.04.2019 | M. Pianka |  |  |  | Costs info in comment |  | R19.7 Jun | 1J | Feature to be created to investigate what kind of pop-up messages we have in order1 and which funstionality is connected | Huge number of annoying pop-up messages makes work less efficient. We should discuss which are necessary and what could we remove. Workshop will be provided first to discuss all of them | 4 | MP | 16 | 960 | YES | 16/04/2019 |  | IMPLEMENTED | 7468 | Paid by all 1J Areas: North, West, Central and UK |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcCSest_VRpAkK-lWmPy-14BcZGUz-j4O8NF2vshqZFl3w?e=kl4qaU
30.04.2019 | E. Serkina |  | Emilia Hermio |  | HL Display OOO (Russia) |  | R19.6 Jun | CJ | There is a need to remove unnecessary parts from invoices. | Legal demand | 5 | MP | 6 | 360 | YES | 21/05/2019 |  | IMPLEMENTED | 7511 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWFBPK8EnrpEoMG-BqNYq88BtQz-6OsxIEYzNRsMLn6N1g?e=f5Sp0t
8.5.2019 | B. Tu |  | Emilia Hermio |  | HL Display Suzhou Co. ltd |  | R19.5 May | CJ | The footer in the format of invoicing or collect invoicing are not correct in suzhou Jeeves, as we have several accounts. So please help just remove bank details,just show our company name and address,tel No# | To avoid customer arrange payment to the wrong account | 5 | MP | 6 | 360 | YES | 13/05/2019 |  | IMPLEMENTED | 7500 | Point has been sent also to financial Pre-CAB to have an agreement. Info from Kinga - we have financial approval |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUX9VjS1TvZDkwI5KdYPuB8BzT2-ARO5pV_7MB4APSmAHQ?e=PVm6GA
20.5.2019 | G. Mayer |  |  |  | HL Display Deutschland GmbH |  | R19.8 Aug | 1J | Please add field ILN during creation of POD in Jeeves | Data accuracy. Time saving. Correct basic data. No issues with documents on which ILN is missing. | 4 | MP | 10 | 600 | YES | 11/06/2019 |  | IMPLEMENTED | 7551 | 21-05-2019 Marcin will send info to Gerhard if they will accept cost. To be discused in June 27-05-2019 Mail sent to Gerhard |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbZhf4stI2JDocfQLdljdxkB7gVg_eYVzPqkthvaKEFtOQ?e=LSDKZu
20.05.2019 | Jerry Frowde |  |  |  | HL Display (UK) Ltd |  | R19.6 Jun | 1J | 7580 | The benefit is that we will have confidence that we have the latest drawing. If the feature is not implemented, we may manufacture incorrect products for the customer. If there is a chance that information provided by the feature is incorrect we cannot use this feature. | 5 | pano | 5 | 300 |  |  |  | IMPLEMENTED | 7245 | 21-05-2019 Marcin will speak with Erwan and Jerry about this point 27-05-2019 Mail sent. Waiting for feedback 21.8.2019 - Marcin will check with Paweł the status |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQUt83dGKp1ArWq_VvrEkmUB7UiK2I0vMU7jpSWd5ziYDA?e=lxNWs5
21.5.2019 | E. Hermiö |  |  |  | Costs info in comment |  | R19.7 Jun | 1J | Microsoft App for sales to see stock availability - pre-work | Increasing customer service efficiency | 5 | EH | 24 | 1440 | YES | 21/05/2019 |  | IMPLEMENTED | 7512 | 21-05-2019 Emilia will check how to split costs of this solution 21-05-2019 Paid by all 1J Areas: North, West, Central and UK (accepted by B. Borgman) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUizCC9FneRPiOJ2gzIZhrQBpyydAmF_E-68lyB_7nf4dw?e=B3lM5V
24.05.2019 | A. Karlson |  | Emilia Hermiö |  | HL Display Sverige AB |  | R19.7 Jun | 1J | To be corrected contact details in SE footers (email and phone address) | Currently reception gets all phones and emails | 5 | MP | 6 | 360 | YES |  |  | IMPLEMENTED | 7534 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdGhyK--8LdJj9gYx-vKLRkBrCy9WbHpRifro9yyYAyeGw?e=emf1s8
27.05.2019 | E. Dufkova/ J. Steffen | Lars Simonsson | Emilia Hermio |  |  | Central | R19.6 Jun | 1J | Trade policy doesn't cover situations, where customer has defined different currency then sales market. In this case we have wrong values on order level | It is not possible to implemet functionality of trade policy in 1810 without this option | 5 | MP | 8 | 480 | YES | 27/05/2019 |  | IMPLEMENTED | 7522 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EY_z9PbIiRdKq7I4fmP8kNoB8BvIftn84Bo_2yZcHGCkCA?e=DqeqgN https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Eap9vK481xFKg8-OxP_FLTMB17XfG0AYk0OcZm97UStzIA?e=qkalrV
30.05.2019 | Kamil Saczka | [6 empty] | CJ | Pre-Study Jeeves Upgrade for Asian Sales Units - Thaliand, Hong Kong, Korea | Current ERP system is obsolete and most of the modules are not supported. Global HL development is more expensive because of the old architecture, sometimes some installations are not possible to be deployed. | 5 | KS | 40 | 2400 |  |  |  | SENT TO PROJECT OFFICE |  | This is not an implementation of the project. This is just a start (pre-study) in order to review the current setup, estimate and recommend different alternatives to management. -Costs should go to IT. //Bjorn Borgman Marcin: I will discuss it with Kamil if we should move this request to IT Pre-CAB meeting. Moved to IT Pre-CAB. |  | Cost Estimate: https://hldisplay.sharepoint.com/:x:/r/sites/hlabitprojectoffice/_layouts/15/Doc.aspx?sourcedoc={f5a550a4-e6c0-48d2-b2cf-7cc261b8290b}&action=editnew
10.06.2019 | Laura Rouru |  | Emilia Hermiö |  | HL Display Nordic |  | R19.8 Aug | 1J | Can we please have the "inventory management class" added as a column to the ‘shortage check’ program we use in Order1 | - adding efficiency - no need to go behind article to check the inv mgt class to choose the next step - diminishing errors in order registration, especially in cases with forecasted items (FI) and customer agreement items (CA) | 4 | MP | 2 | 120 | YES | 11/06/2019 |  | IMPLEMENTED | 7550 | Emilia come back with details 11/6 Details sent to Marcin |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EStE1hyAT35KjTsi6xYIPx8BQQ6LT8bSeMmTUUp-dCE0gw?e=NuzP6p
13.06.2019 | Amy Mo |  | Emilia Hermio |  |  |  | R19.6 Jun | CJ | Due to change of office by Honkong team, it is needed to update also templates | It is necessary to provide business | 5 | MP | 6 | 360 | YES | 13/06/2019 |  | IMPLEMENTED | 7553 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcsiZD32fI9FiPRWyIL4KHoBo8oyG_DTLCHYUBmGudD8pQ?e=k3yNXB
24.06.2019 | J. Aigner |  |  |  | HL Display Schweiz |  | R19.8 Aug | 1J | Change “Rabatt” to “Rabais” in FR templates in 2400 |  | 4 | MP | 2 | 120 | YES | 09/07/2019 |  | IMPLEMENTED | 7580 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQSEeBwmZhBJuff-Pbj4OaAB1svCBYPqQ5f39sbM5BlOGQ?e=OnRgSi
25.06.2019 | M. Reiterer | [6 empty] | QV | The following fields we’d like to have added to the dimensions in the New Sales Process.qvw report in sheet “Custom Report”: - Company ID - Company name - Company address: Combination of fields Street address/box + Postal address - Point of delivery, co. ID - Point of delivery, name - Point of delivery address: Combination of fields Street address/box + ZIP/Post code | KAMs can easier follow-up on deliveries and store opening implementation. Today, KAMs rely on back-office info, provided by email or verbal, which is very inefficient. Having these fields in QV would enable them to run reports on their own and can take decisions on sales/future deliveries more efficiently. | 4 | MP | 40 | 2400 |  |  |  | REJECTED | 7632 | 9.7.2019 - Sarah will check costs with Markus and ask for approval 21.08.2019 - Marcin will check with Paweł Kardas if we could use PowerApps instead. 30.08.2019 - Paweł estimated for 16 hours. To be decide if we will go with developement. 10.09.2019 - Emilia will check details and costs with Markus 11.10.2019 - Reinhard will investigate the need in Area Central and come back to Emilia 12.11.2019 - requirement is changed - small number of fields are needed/ Emilia will send info/ Marcin will check with dev team 27.11.2019 New RFC with new estimation |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESuGiHrSohlJrVUSFf9robMB_ivvwuwcTT4qOnZ80YfAjg?e=TDbnUb
1.7.2019 | K. Philips |  |  |  | HL Display (UK) Ltd |  | R19.9 Sep | 1J | Remove "Item specification" from customer's document | There are lots of internal information. It will also make our prints more customer friendly | 4 | MP | 6 | 360 | YES | 09/07/2019 |  | IMPLEMENTED | 7581 | To be released in September 2019. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Eev7XBNzryVLk_f1ZdA1njoB44Hmi_Mx-1ZPTmT3s6QsEw?e=9AKZVf
2.7.2019 | E. Hermio |  |  |  |  | North East | R19.9 Sep | 1J | Limited access of 1210 users to company 1810 | To avoid errors, users should have read mode access only (which is necessary to get data from years 2016-2019) | 5 | MP | 4 | 240 | YES | 09/07/2019 |  | IMPLEMENTED | 7583 | Marcin: No developement is needed - we could use security manager 09.07.2019 - Marcin will check with Kamil about estimation and let know |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYqqR3Mr96dEvDrLHEwmykwB9Ko0UE42YwYZmUSiK7IG9Q?e=CeIdB6
3.7.2019 | J. Holdorf |  |  |  | HL Display Norge A/S |  | R19.9 Sep | 1J | New address of HL office in Norway starting from 1.9.2019. Templates should be updated. Both 1210 and 1300 | Not needed | 5 | MP | 6 | 360 | YES | 09/07/2019 |  | IMPLEMENTED | 7579 | 9/7/2019 - Marcin will check with Mariusz and Kamil if there is possibility to deploy during weekend 30.8.2019-1.9.2019 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdUquYstTclJgYn3Wu7awNEBeEXJQhFm7qnQKeI_lRcAUQ?e=txOVUs
09-03-2020 | A.Cieloch | [6 empty] | QV | 1) Now data in program qov must be entered manually, for each order. It is necessary to have the possibility to import list of orders with required % assigned to sales market from Excel. 2) Now adjustments from program qov are visible only in “New – Sales Process […]” reports. Adjusted Sales Markets should be visible in all reports related to sales like: Aaro Customer specification 3) Now in QV, despite rows with reassigned sales market there is visible also the line with originally assigned sales market, with added “*”. It is necessary to create the button in QV which would hide the rows with originally assigned sales market, if it is replaced by the data from qov. 4) As a further change we would like to have the possibility to automatically change assigned sales markets on orders from Financial Group “Schwarz Group” and original Sales Market “Germany”. | Clearer and more useful reports in QV, easier data analysis. Reduction of manual work at the closing of the month (this method will enable replacing the manual division of Sales Markets outside the system). It will also eliminate discrepancies between QV and Aaro. | 4 | MP | 40 | 2400 |  |  |  | ON HOLD |  | 10.03.2020 Marcin will continue discussion with A. Cieloch to get a full scope of requirement. Existing program qov 12.03.2020 Reminder sent to A. Cieloch. We should have a final decision. Meeting planned: 16:03.2020 23.04.2020 Sonia will check with Hania and Mariusz the estimated hours 05-05-2020 Discussed with Markus Reiterer: three propositions, Markus agreed on the third one: button in QV to show sales before and after the split, funcionality to automatically divide the orders in program QOV based on rules (36-40h) 14-05-2020 Markus put this on hold. Need discussionabout splitting the cost sales and finance or moving this to finance |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESFhAoeemfJGtNyb5tBuVOoBYDdGbl3oVKYNpWCkUIXtIw?e=HFu3Hl
10.7.2019 | C. Zhou |  |  |  | HL Display Shanghai Co Ltd |  | R19.9 Sep | 1J | System calculates VAT based on field "VAT tax rate". Field "New VAT tax rate" is not taken ito calculation | It is confusing for customers. 1.4.2019 China changed VAT from 16 to 13%. Invoices are ok, but not OC | 4 | MP | 6 | 360 | YES | 21/08/2019 |  | IMPLEMENTED | 7618 | Marcin will check estimation with Kamil. If it will be above 6hr, then we should discuss with Emilia |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdtppIzxh1dHsfZCL81bk4AB3WlCiMZFWR9r8rOMhb7SpA?e=DNBVI1
10.02.2020 | O. Pedroncini |  |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | Claims - return of agreement. Change of layout | Only printing one page and more understandable by the customer | 4 | MP | 6 | 360 | YES | 11/02/2020 |  | SPECIFIED | 7845 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Eey1Djke2HZIk4BEP9G5tR0Bl9b5OD_gaDU4uHBxLjsVWg?e=tvvZSg
11.7.2019 | S. Lucy |  |  |  | HL Display Schweiz |  | R19.10 Oct | 1J | New GTC should be added into 2400 (French and German) |  | 5 | MP | 4 | 240 | YES | 21/08/2019 |  | IMPLEMENTED | 7617 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWSX9-9LAN1Jh9cjOpGDAbwB0opgaq14hZ_lKdyuotpZ-w?e=jhYqAD
18.7.2019 | O. Pedroncini |  |  |  | HL Display France SAS (+ SASU DESIGN) |  | R19.10 Oct | 1J | New invoice template with Swedish VAT number is needed |  | 5 | MP | 6 | 360 | YES | 21/08/2019 |  | IMPLEMENTED | 7616 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdBSCKBB1Q5EiWW3Fe1FhLEBs4WsNmTgKs2AL7AaVTZjGQ?e=tgV1L8
10.06.2019 | Marcin Pianka | [6 empty] | 1J | Uploading order details - Excel, csv, pdf, web services, others. To discussed current solutions |  |  | MP |  | 0 |  |  |  | IMPLEMENTED |  | Just discussion/ it should be discussed internally within areas
09/08/2019 | Boguslaw Kuczynski | Małgorzata Stasierska |  |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | Customer Own delivery after Place order Every day we are closing the orders. Some of these orders require singed ‘customer delivers’. Those documents are added by SU on order1 as attached. When we are closing this kind of orders (always on olhucorl) we should to receive this extra needed delivery directly from the printer after pressing ‘place order’ button. Now ‘customer delivers’ are not visible as attached on olhucorl level and to be sure that all this kind of orders will be processed as final customer requires we have to receive an email from SU example: “Please be sure that order….. with dispatch date next week require signed (his) delivery note attached in order1”< this is bad way and we would like to be sure that we will receive this delivery directly from the printer and give to the truck driver. | At this moment we have to remember the email form ~3days ago otherwise we don’t have any field/information on picking list that order require customer deliver doc. | 3 | pano | 16 | 960 | investigation | 14/08/2019 |  | IMPLEMENTED |  | 14/08 pano: please check on preCab Sales unit flow on Polish market and check if PL SU would like share cost 21.08.2019 - Marcin will organize meeting with Emilia, Kay and Paweł. Is it connected with certain customers? Or general solution for Poland? 23.8.2019 - Meeting planned for 27.8.2019 27.8.2019 Marcin. We analysed solution implemented in 1710. Paweł will check if we could it also in 1810 (in 1210 maybe also). Futher discussion is needed. Point should be back to logistic Pre-CAB. 14.01.2020 - Closed. Implemented, based on info from Emilia |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EV5EcN_ypmxPp-i0EhtThJ0BJmkalHGfAIoj35mqqHRA5A?e=JVyCH5
19.08.2019 | Marcin Pianka | [6 empty] | 1J | Point to discuss - costs of services - how you receive them from external suppliers? Invoices? Kind of agreement? 2) And how you would like to see them in QV report? |  | 4 | MP |  | 0 |  |  |  | IMPLEMENTED
19.08.2019 | S. Lucy |  |  |  | Costs info in comment |  | R19.10 Oct | 1J | As discussed during meeting “reducing pop-ups” we need an adjustment on the function “Adjust order for deliveries”. Today it overwrites text in “external text” on the row with PoD. In the future it should not overwrite, but ADD the PoD in the external text field on the row. After the change it should say: “Point of delivery data for the following order rows will be added on the external text: 10 20 30 40” | More efficient as we do not need to write in again information from external text. | 4 | MP | 12 | 720 | YES | 21/08/2019 |  | IMPLEMENTED | 7615 | Costs: Area West, North-East, UK, Central and 2400. To be checked if China also |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERBh6U9B2iNLpHSzXkEhiPUBf-vLapxjNd7OPDDpfbZiiA?e=7y9LWf
27.08.2019 | L. Sohn |  |  |  | HL Display Korea Co Ltd |  | R19.9 Sep | CJ | Financial Group Mapping is set incorrect for LOHB’s & Nestle Korea, so Qlikview cannot retrieve the correct financial group information | Will get the correct view on Qlikview Sales report with the financial group. | 5 | MP | 2 | 120 | YES | 27/08/2019 |  | IMPLEMENTED | 7624 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EboMElSxhHRGg8ZcA3Su-pQBRaUVCkbw3XQM_3aF_5I1JA?e=KN1TIn
29.08.2019 | M.Pianka |  |  |  | HL Display AB - IT |  | R19.10 Oct | CRM | Additional columns should be handled during synch dictionary values from Jeeves to CRM. | To provide a proper message. Feature is based on feedback form production installation. | 5 | MP | 10 | 600 | YES | 30/08/2019 |  | IMPLEMENTED | 7629 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeMkVWXd2TJJjcPsnD1xIqMBMZzWC7jKsDa7bbO3_GfsFg?e=hlNfex
30.08.2019 | M. Ostrowska |  |  |  | HL Display Distribution Center Europe sp zoo |  | R19.11 Nov | QV | MTO report shows changes on SO If any row on SO is cancelled sheet "row status has been changed" shows that information, but we need to know exact qty which was canceled (row qty before cancellation). There is another sheet “row qty has been changed” there can be reported canceled rows as qty decreased from number which was on the row before cancellation to 0 | It helps us to recognize which SO owner is responsible that we have placed PO to factory and than SO have been cancelled. | 4 | MP | 6 | 360 | YES | 10/09/2019 |  | IMPLEMENTED | 7642 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUXvl8xe3W1EvGGcKKeTZJcBx5sPMGBy5czXu7re_mxJjw?e=k27zWw
10.09.2019 | E. Hermio | [6 empty] | 1J | Button “Set rows to Active” in Estimator changes the status on all rows. If customer orders only part of the offer, we need to update all rows manually one by one. Could we add a pop-up behind the button to choose: -Change all rows to active -Change following rows to active -Which status and reason should be set for the rest of the rows (dropdown menu) | Improves efficiency in CS. | 4 | MP | 16 | 960 |  |  |  | REJECTED |  | 9.10.2019 - Marcin will check why in 1710 it is not needed to use button "set rows to active" comparing to other units. Maybe developement will be not needed. 6.11.2019 - Mail sent to dev team. We should take a look at the case during next Pre-CAB meeting 12.11.2019 - To check with Kay in December and get a final decission 14.01.2020 - Marcin will check if there are some parameters to implement rules from 1710 also to other units, like 1210. 11-02-2020 Marcin will send info before March's meeting to have full overview on settings. 09-03-2020 Marcin: I made several tests and there is no differences using 1710 or 1600 parameters. It will be good to have a separate meeting to check togerher such cases 10-03-2020 Marcin will invite CAB team for a separate meeting. Sonia will check if there is a defect logged for this action. 23.04.2020 Sonia will schedule a meeting to compare flows from UK and Switzerland and Nordic 07-05-2020 Scheduled meeting on 20th of May |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbPgOiIq5bNEpVFQT9pxEacBUj_2vCLYIDHcDMebonxDuA?e=RMG5h6
09.09.2019 | E. Hermio | [6 empty] | 1J | Today charge for customers exist only for EUR pallets. If field “other pallet” is used, no charge will be added on customer invoice. We need a solution to add charge also behind ”other pallet”. If we charge customer or not, we need to be able to decide that on customer level, same way as EUR pallet charge. Algorithm should consider tick box ”Charge freight cost” same way as for EUR pallets. Values for the charges will be informed later for every country (NO, SE, FI). Marking the tick box for customers need to be handled with mass upload by IT (detailed information to be provided from SU’s). |  | 5 | MP | 18 | 1080 |  |  |  | REJECTED |  | 10.9.2019 - Emilia needs to revise request with new requirements. Expected to back to this point in October. 11.10.2019 - Under investigation in Area NE 12.11.2019 - Still no final decission 22.11.2019 - Rejected. Emilia sent new RFC |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EU5HezN8jjlFlpuZQ8lYmHcBiMwldiTdidcjGGc_9IP_aw?e=TJzdZo
10.09.2019 | C. Sahlen |  |  |  | HL Display Sundsvall AB |  | R19.10 Oct | QV | To be able to filter QV report on claims we need to add “Project” as a dimension in QV New Sales process report. Project can be valuable to filter on for other units as well, not to select claims but to see sales based on a special customer project (which field is used for in other Jeeves co´s). Add dimension “Project” in “Other” box in the tab “Overview” It also needs to be selectable as a column | Today claims are effecting the margin on HL partners, this would allow us to filter claim orders in Sundsvall where we have the biggest issues at the moment. By being able to filter Claims, the Finance dept will be able adjust the financial reporting in AARO in an easy non time consuming way. This is also beneficia for Sales managers who will be able to exclude claims from their total sales/bc figures in QV. | 5 | MP | 4 | 240 | YES | 10/09/2019 |  | IMPLEMENTED | 7641 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbrdS8zbp6ZIkzUfLHvw0pABlUWdvdONXGUBqcseGeIzGQ?e=ME3Yxw
10.09.2019 | B. Johansson | [6 empty] | 1J | Just investigation - how much time it will take to wrap all of item descriptions in one template. Check number of templates. |  |  |  |  | 0 |  |  |  | REJECTED |  | 10.09.2019 - Marcin will check it and back with results 10.09.2019 - 0,5-1h for 1 template. Around 450 templates in 1J. 11.10.2019 - Cost is too high, separate meeting to be booked to test and investigate alternative options 12.11.2019 - Closed. Trying to fin alternative solution using rules for item names
10.7.2019 | E. Hermio |  |  |  | Costs info in comment |  |  | 1J | Following additions to the existing solution of Stock Availability Tool: 1. More options during searching e.g. possibilty to use % 2. Long items names to be divided to two rows 3. Visibility of PO acknowledged - possibly OA-date 4. Sales qty and Supply MOQ visible in the item page 5. Visibility of forecasted items for 1810 (field stock owner) Additional option: 6. Function “copy to mail” from the item page | Increases CS efficiency and customer focus when sales have more accurate information available | 4 | MP | 8 | 480 | YES |  |  | INVESTIGATION |  | It will be discussed during in September. Kamil estimates it for 8-16hrs. Details will be set when developer will be back. 10.09.2019 We will back to this point in October 12.11.2019 - Point will be discussed in December (taking feedback from other countries) 14.01.2020 Emilia will discuss with Kay and Laurence if all points are needed. Maybe just 2 of them? Or the new request? 11-02-2019 It should wait for full feedback. 10.03.2020 - it will be discussed in April 23.04.2020 Waiting for the feedback from France. Emilia will contact Laurence 14-05-2020 Stephanie will contact Laurence about the PowerApp 17-06-2020 Sonia will talk with Pawel K. about the picture in Stock Availibility Power App 13/08/2020 Sonia will check the 5 point with Pawel 13/08/2020 Costs will be divided between all Areas |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVxUpxUxEP1Fh-kle1usG8YB-3itwicskinuWn822dN_QA?e=LJIVIj
01.10.2019 | E. Hermio |  |  |  | HL Display AB - Sales | Headquarter | R20.01 Jan | 1J | We want to start charging customers for paper invoices. We need a tick box on customer level to mark if an automatic fee for paper invoice should be added. Feel also free to suggest an alternative option. | We want to push customers towards digitalized invoicing by charging for paper invoices | 4 | MP | 32 | 1920 | YES | 14/10/2019 | 20-12-2019 | IMPLEMENTED | 7672 7734 7773 | 9-10-2019 Marcin to check with Kamil other options - just warning message for sales unit, that fee should be added manually. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ETraUuUgkK1OpyApewkM-AABjHSExkO-4wsmPnH40jPo5Q?e=kjfacM
10.10.2019 | M. Ronn |  |  |  | HL Display France SAS (+ SASU DESIGN) |  | R19.11 Nov | CRM | Prepared integration Jeeves->CRM in sales market France | The same information in Jeeves and CRM | 5 | MP | 12 | 720 | YES | 14/10/2019 |  | IMPLEMENTED | 7669 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYxKkY_C3FlAjzYQQ9uNEmMBU5ekgUde4nGIU0MXcijQ7Q?e=nTkvwt
14.10.2019 | M. Ronn | [6 empty] | E-Store (online sales) | Sales portal improvement |  | 5 | MP | 10 | 600 |  |  |  | IMPLEMENTED |  | Marcin to ask Kamil/Magnus - who will pay for the changes?? Magnus - already implemented, outside HL IT |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EaJu4XdP7TNPotCA1OOFcz4BydEiPrqgwe7uqKmwmZHSkQ?e=Njadx3
21.10.2019 | M.Pianka | [5 empty] | R19.10 Oct | CRM | QV CRM report should contain information about problems with sync. | If there is no proper mapping, accounts are in CRM, but users are not able to see them | 5 | MP | 10 | 600 |  |  |  | IMPLEMENTED | 7622 |  |  | Moved from CRM project
24.10.2019 | O. Pedroncini |  |  |  | HL Display France SAS (+ SASU DESIGN) |  | R19.12 Dec | 1J | New office of French team. Changes should be needed on all templates (also for BE and NL). Deployment 11.12.2019 | Legal demand | 5 | MP | 40 | 2400 | YES | 24/10/2019 |  | IMPLEMENTED | 7686 7687 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESPnoZGEjC1KgsnxMXkDZyIB3Zqxw39EnuOfrof0nDdOew?e=KkDHDm
30.10.2019 | M. Ronn |  |  |  | Costs info in comment |  |  | 1J | Please change logic of setting promised dispatch/delivery date based on estimated dates. | To provide a proper handling of sales orders from Sales Portal | 4 | MP | 20 | 1200 | YES | 12/11/2019 |  | REJECTED | 7719 | Please divide costs between Nordic and West 17.12.2019 - rejected based on Magnus email |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EaLQBRTLKIBJoA_wSSfMmMgBtYguXYJeY53hXY2UcLWCwA?e=fcNksP
30.10.2019 | M. Ronn |  |  |  | Costs info in comment |  | R19.12 Dec | Sales Portal | Connect Sales Portal with CRM Dynamics | Efficiency and better knowledge about the business | 5 | MP | 28 | 1680 | YES | 12/11/2019 |  | IMPLEMENTED | 7702 7703 | Please divide costs between Nordic and West |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ef7cl3tth8hBp6hMzqdI8WgBOKxuIFh3tsqCXJpkw3sH-Q?e=DB6dTc https://hldisplay.sharepoint.com/:p:/s/itdocumentationrepository/ETYMB0gdd8tLlyN4HBpqH-QBa9Yb3X4ocSRbmstz6cyn1A?e=DLMWGK
12.03.2019 | S. Lucy |  |  |  |  | Central |  | 1J | Introduction for Advanced Payment Flow for Area Central (1810 + 3901) - copy of point 121 - templates for Romania and Hungary |  | 4 | SL | 12 | 720 | YES |  |  | SPECIFIED | 7632 | 12-03-2019 Sarah to contact with units and financial department - we already have PL and EN versions in 1810 and advance payment template in 3901 15-04-2019 Get templates for Czech and Slovakia, need to adjust Poland and Austria 21-05-2019/11-06-2019/21.8.2019 Still we don't have translations 12.11.2019 - Marcin will check if we have all translations 13.11.2019 - Slovenian translation is still missing. Last mail from September 2019. 15.01.2020 - Marcin sent last info to Emilia 11-02-2020 - Sarah should be in the next meeting. Input from finance (Kinga) is needed. 10-03-2020 Sarah will contact Marcin 24.04.2020 Marcin will contact Sarah regarding the slovenian translation 11.05.2020 After Sarah and Joe email it was decided to work with English template instead of Slovenian. When the Slovenian template will be needed in the future it will be added with a new feature. 14-05-2020 Sonia will check the translation and double check with the finance department and with dev team about the estimation | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERYvxeQBa_pHsYlQOtA3OEwB9U01uCWXUSuK92D_lSqZHg?e=rIDyLi
7.11.2019 | A. Tarabuła |  |  |  | HL Display Gliwice Sp z.o.o |  | R20.01 Jan | 1J | New invoice for 1190 + changes in the footer | requested by customer | 5 | MP | 6 | 360 | YES | 10/12/2019 |  | IMPLEMENTED | 7732 | Investigation (together with Gliwice finance team) in progress. Kasia will establish a meeting to discuss and have a final decision. 15.11.2019 - Spec done and accepted by Gliwice finance |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERpf9jmUMq5BuEMha5AtFA4BkY6dlg-QgnUxCqqWjjXmtw?e=5644da
12.11.2019 | E. Hermio |  |  |  | Costs info in comment |  |  | 1J | Trade policy: questions about adding fees should appear only during changing to status "Entered" For discussion in Pre-CAB | Improves efficiency in CS when unnecessary pop-ups don’t appear | 4 | MP | 8 | 480 | YES |  |  | SPECIFIED |  | 10.12.2019: To be checked with Kay and Laurence in January 2020. 11-02-2020 To be discussed in March 10-03-2020 To be discussed in April 23.04.2020 Sonia will investigate how Trade Policy works in France 13-05-2020 Trade Policy is added on the level of Supergroup and on that level on Sales Market - fees are added in status Entry in progress 14-05-2020 Sonia will check the estimation 09-06-2020 Estimation is correct 09-07-2020 Parameter to be added - check the estimation of dev hours 13/08/2020 Cost will be split between Nordic and Central |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EctoHZ9cWgpCpK9bBnByxykB5k0N18pC0jVeqW_t6kjUYw?e=PoEm96
14.11.2019 | L. Rouru |  |  |  | HL Display Nordic |  | R20.02 Feb | 1J | Price list: Inventory mgt class should be visible in PRH, place it between item group and text. | Improves efficiency for customer service with yearly price updates | 4 | MP | 2 | 120 | YES | 10/12/2019 |  | IMPLEMENTED | 7754 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EctoHZ9cWgpCpK9bBnByxykBeSjLAeCivEXnUY7jiwRs6Q?e=RmlxZb
19.11.2019 | E. De Winter |  |  |  | HL Display Nederland BV |  | R20.01 Jan | 1J | New office in Netherlands. All templates should be corrected. | Legal demand | 5 | MP | 12 | 720 | YES | 22/11/2019 |  | IMPLEMENTED | 7745 7746 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EZOHgYkGjQ1EvcJM9czA17wBNkO5G1aMhrIVvaTY37-Ymw?e=baRC6J
22.11.2019 | E. Hermio |  |  |  | HL Display Nordic |  |  | 1J | Remove all descriptions "euro" from all 1210 invoices | We are misleading our customers to think we use EUR-pallets when we actually are not | 4 | MP | 6 | 360 | YES | 10/12/2019 |  | IMPLEMENTED | 7764 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EU38jPjnUOtHvko-zlCK6qYBV3dP6Y19FXTFiLwyVZe6dw?e=B1fiD2
22.11.2019 | M. Ronn |  |  |  | Costs info in comment |  | R20.02 Feb | CRM | Integrate Jeeves with CRM for Belgium and Netherlands |  | 5 | MP | 12 | 720 | YES | 14/01/2020 |  | IMPLEMENTED | 7766 | Investigation phase - we have doubled records for sales persons in Jeeves. Issue is analyzed by financial team ============================== Payment: split between BE and BL. Marcin will confirm it. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYF8mqWUjllNrAjibeSmWtYBZ9yvJdw1ufMo9n9tt_7kjg?e=0Hooer
26.11.2019 | R. Rollet |  |  |  | HL Display Österreich GmbH |  | R20.01 Jan | QV | We need to add the fields “point of delivery, name” and the “city of delivery” to be visible in QV: | Improves sales forecast and follow-up | 5 | MP | 20 | 1200 | YES | 10/12/2019 |  | IMPLEMENTED | 7748 | Paid in advance (Release R19.11) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ed5AF14McoNPkdQ_pj3HBiMBg1d2bNQMVjt6VNlCh7qGAg?e=8Ambig
28.09.2019 | M.Pianka |  |  |  | HL Display AB - IT |  | R19.11 Nov | QV | Handling of errors within CRM integration (customers/accounts) | Necessary to provided a proper information for support | 5 | MP | 2 | 120 | YES |  |  | IMPLEMENTED | 7676
10.07.2019 | S. Lucy |  |  |  | HL Display Deutschland GmbH |  | R20.01 Jan | 1J | Limitation access for German team to company 1600. Only Gerhard Mayer and Anke Bergner should have full access. The rest of the team -> read-only mode | Security role | 4 | MP | 2 | 120 | YES | 10/12/2019 |  | IMPLEMENTED | 7755 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Efo4AL4MhR5NstW-ZLmhRJEBPoUkwIDjgm_LO-sdyxSUaA?e=rPpKXi
10-04-2020 | A. Mamińska |  | Emilia Hermiö |  | HL Display Romania |  |  | 1J | Due to change of bank account concerning RON currency we need to adjust the footer of Romanian invoice templates. | Customers should receive invoices with proper bank account number so that they pay accordingly and company 1810 will receive money. Customer should start receiving invoices with new bank data and start paying to the new bank account number before the old one is closed to avoid any payment delays. | 5 | sonkur | 2 | 120 | YES | 14/04/2020 |  | IMPLEMENTED | 7955 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B923B0F56-DAD9-4160-824B-050314133237%7D&file=RFC%20-%20RO%20invoice%20templates.docx&action=default&mobileredirect=true
11.12.2019 | T. Yrjonen |  |  |  | HL Display Suomi Oy |  | R20.02 Feb | EDI | Please change bank details to IBAN to SE65 5000 0000 0569 6822 4712 on e-invoices and SWIFT to the following: ESSESESS. This IBAN is currently visible in order confirmations, but on e-invoices there is currently FI72 3301 0001 1282 30. | Correct IBAN&SWIFT will be visible for e-invoices | 4 | MP | 4 | 240 | YES | 14/01/2020 |  | IMPLEMENTED | 7798 | 12/12/2019 KIPA: approved by finance - Margareta Karlsson 11/12/2019 Info to: Karin Wennerstal |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUfQX39819xMli-lN5Sn7N4BpRRPkmoXizsHztFsd54vUA?e=RYGNaB
17.12.2019 | K. Leśniewska | [6 empty] | 1J | Just discussion - handling of claims (sending of items, partly return, partly invoiced) |  |  | MP |  | 0 |  |  |  | REJECTED
13.02.2020 | M. Lekstutis | [6 empty] | EDI | Norgesgruppen EDI handover from Evry to HL EDI solution | Improve reliability and maintenance of this integration and avoid constant issues with sending via Evry | 5 | ML | 40 | 2400 |  |  |  | ON HOLD |  | Marcin: to check if costs will go to Nordic/Norway or IT (Kamil?) - Anders Lautman to discuss. If yes, then we could switch to YES. 17-03-2020 Marcin sent question to Kamil
13-6-2018 | S. Keller |  | Emilia Hermio |  |  |  |  | 1J | "Multiselection"/"Change dates" buttons in order1 -> there should be option to add category to these rows. | This will avoid to have to assign “manually” the category particularly in case of Austria / Slovenia where such orders can be quite important with 100 to 150 rows. It will also allow to easily identify such orders Approx 80 such orders are handled by the warehouse 1810 per month. | 3 | MP | 16 | 960 |  |  |  | ON HOLD |  | wait for point 47 |  | RFC: https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ef5wg5ImJB5BrhycmkZn0yUBkQd-Yk1mhLegUQiozhwwYQ?e=aHcNC3
9.1.2020 | E. De WInter | Emilia Hermiö |  |  | HL Display Nederland BV |  | R20.01 Jan | 1J | Change phone number on NL templates to +31762300300. Fax should be removed | Office movement | 5 | MP | 4 | 240 | YES | 14/01/2020 |  | IMPLEMENTED | 7782 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EZvfr0teeE9Ei3QOtZryRzUBnCq9fEZKrSGAN28gQbEvOg?e=qMhAxc
14.1.2019 | I. Santos |  |  |  | HL Display Middle East FZCO |  |  | 1J | Change way of calculation total amount in local currency (all invoices) | To avoid complaint from customers that invoice does not match with their PO | 5 | MP | 12 | 720 | YES |  |  | ON HOLD | 7335 | Feature has to be put on hold due to discussion between Kinga and finance auditor in Dubai due to legal demands and roundings in the system. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERO9O3L9DP5LoQWhVs351vgBOM01tXja4nSJyY1WhdLNvA?e=gZTI0t https://hldisplay.sharepoint.com/:x:/s/itdocumentationrepository/EUZM9FPQObROr2NkW8VW_qcBrGwCttc6IFizIWUg2HSa0g?e=ff4nkF
17.1.2020 | A. Bergner |  |  |  | HL Display Deutschland GmbH |  | R20.03 Mar | 1J | New GTC for Germany 2020 + additional text on the invoices | Legal demand, customer satisfaction improvements | 5 | MP | 8 | 480 | YES | 11/02/2020 |  | IMPLEMENTED | 7848 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYxBzIUPQUxJghW614rAygAB9CJew3JowdmXyg3ShWIrKw?e=vyEZx1
23.01.2020 | M. Lekstutis |  |  |  | HL Display (UK) Ltd |  |  | EDI | New orders-change-confirmation integration (invoice later) for UK Tesco via Marrakech portal | Will allow us to gain new business – without it the business will not happen. Allows us to to business better. | 5 | ML | 36 | 2160 |  |  |  | SENT TO PROJECT OFFICE |  | Three features created: 7814 - investigation - 4h 7815 - orders handling - 16h 7816 - confirmations handling - 16h Marcin: Should it ba a part of project or the maintenance? Marcin to contact with Magnus and Mariusz. Info from Kamil: we will do it within project 8055: order and invoice efficiency
23.01.2020 | J. Steffen |  |  |  | HL Display Sverige AB |  | R20.03 Mar | QV | Customers 5040 and 5050 in CJ Suzhou should be mapped within super and financial group "Ikea" | This will simplify to search for IKEA sales | 4 | MP | 2 | 120 | YES | 12/02/2020 |  | IMPLEMENTED | 7852 | 11-02-2020 Marcin will check with Jesscia to make sure, that costs goes to HL Finance (not Suzhou) 12-02-2020 Mail sent to Jesica. Jessica: HL Sweden AB |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EStdoRj97WZPrEKTRkyaieYBIXM1bH1wio-fZkYZPhWuiA?e=5Scn0r
16.1.2020 | G. Wright |  |  |  | HL Display (UK) Ltd |  |  | EDI | Our customer Kellogg ( 37071) will only does business via Tunsten ( OB10 )I and therefore needs to be set up | Will allow us to gain new business – without it the business will not happen. Allows us to to business better. | 5 | MP | 32 | 1920 | YES | 12/02/2020 |  | SPECIFIED | 7882 | 11-02-2020 Marcin will send request to Howard (if he will accept the costs). Just after approval from business Marcin will change status to "accepted" 12-02-2020 Marcin sent email to Howard. Waiting for response. 13-02-2020 Answer: It is ok, but 32 is maximum. They expect a lower price. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EblTf0gYihBMrYlpmJvsi1kBTKtMUgXWogLM2C0JM_EA-w?e=cRECfs
16-04-2020 | S. Roinard |  |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | Issue on item description. The field used for detailed description is the field used ont the web portal as the title/name of the item. We do not have any field to have detailed description populated on commercial document (offer ...) | Having clear and detailed description for our customer (on web portal AND on commercial document from Jeeves) | 4 | sonkur | 1 | 60 | YES |  |  | IMPLEMENTED | 8058 | 23.04.2020 Seperate discussion about the global solution how to handle item description in Web Portal and on commercial documents 07-07-2020 Meeting scheduled on 13th of May 14-05-2020 Discussion with Magnus and Marketing 13/08/2020 Solved by increasing character length in arb-program
18.12.2016 | G. Wright |  |  |  | HL Display (UK) Ltd |  |  | EDI | Our new customer Nisa requires us to do business via EDI and therefore needs to be set up | Will allow us to gain new business – without it the business will not happen. Allows us to to business better. | 5 | MP | 32 | 1920 | YES | 14/01/2020 |  | IN PROGRESS | 7801.7833 | 15-01-2020 Marcin sent email to Graham nad Kay if they will accept the costs. Accepted by 1710 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeH0iI0dXq5Pq0XJJMk8PEABzREjI--4P_GmMsgrj9tquA?e=eUCA0A
18/12/2019 | Emilia Hermio |  |  |  | Costs info in comment |  |  | 1J | Remove and adjust pop-ups during order update process after picking list is printed – today we have too many pop-ups and they appear when the order update is not relevant for WH. | Improve efficiency in CS and reduce frustration | 4 | pano | 16 | 960 | YES | 11/02/2020 |  | SPECIFIED | 7871 | 28/01/2020 moved from PreCab Supply Chain ,cost supposed to be taken by Sales Costs divided between 1710, 1600, 2400, 1810, 1210 11-02-2020 Marcin will contact with Paweł to get a full information about the final effect. 20-02-2020 Spec is ready based on previous decission |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ETGPE385-MFHh_uinO1T5DwB8oirlSm5-A4MAcaWQltlVA?e=dY2woa
31.01.2019 | O. Pedroncini |  | Emilia Hermiö |  | HL Display France SAS (+ SASU DESIGN) |  | R20.03 Mar | 1J | New invoice template is needed - EN version with Polish VAT | To be able to apply the international rules on VAT | 5 | MP | 4 | 240 | YES | 11/02/2020 |  | IMPLEMENTED | 7846 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESHJUhPL-t9Pir2Rhj--TJEBUhtW2niS_vAuyV1tE9rPoQ?e=83OKm5
19/11/2019 | Jeannine Stutz | Emilia Hermiö |  |  | HL Display Schweiz |  |  | 1J | It does not accept the PoD address into the proforma invoice. (program “be) On the proforma invoice there is always the customers address for the delivery address and not the specific PoD address. | Correct proforma invoice, so we do not have to correct it manually. | 5 | pano | 8 | 480 | YES | 14/01/2020 |  | SPECIFIED | 7797 | 17/12 moved to Sales PreCab Planned for sprint 205 17.03.2020 - it has to wait due to long queue in maintenance and Sundsvall project |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdEO-bZRtZhCqMX-ew42hygBXWy4LhencHcnfQkKmllJ_w?e=vpZvSR
10.02.2020 | M. Ronn |  | Kamil Saczka |  |  | North East | R20.02 Feb | Sales Portal | Catching of orders from Sales portal and passing to CRM |  | 5 | MP | 2 | 120 | YES | 12/02/2020 |  | IMPLEMENTED | 7842 | 11-02-2020 Marcin will discuss with Magnus - who should pay for the changes. 12-02-2020 Marcin sent a proper email. Answer: costs should go to Area North East
20/06/2018 | Nordic HUB AL43 |  | Emilia Hermio |  | Costs info in comment |  |  | 1J | Order1 program : in the embedded list, the "Allocated qty" field is showing informations regarding booked qty of the order row Purpose is to have a way to know if the allocated qty comes from "Stock available" or from "Purchase Order" (booking against PO) |  | 3 | PANO | 8 | 480 | YES | 14-05-2020 |  | SPECIFIED | 7996 | Such information are available in corx table. similar dvpt hasd already been done in planning and can perhaps be re-used by focusing only on corx table 10-7-2018 - sales support report should be fixed instead 14-01-2020 Marcin to discuss with Paweł Nowak 11-02-2020 Marcin to discuss with Paweł Nowak 10.03.2020 Marcin will check with Kamil development hours and send instruction to Kay. 17.03.2020 Mail sent to Kay (instruction) and to Paweł and Kamil (estimation) 15.04.2020 Email do Kamil and Paweł about the estimation (40h) 23.04.2020 Check with Pawel how many hours if the develoment would require only colouring the order row 07.05.2020 If we want to only colour the line in yellow for information if the order row is allocated from PO it would be 8h, more if we would also want to add a column from which PO it is booked - similar to the planning list 14-05-2020 Cost can be split to Nordic, West and Central |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYAGgkm9O3lHjvlc5yTkLGQBeThuZ0cumWPolopwB0Dh4Q?e=AgxKne
20-04-2020 | S. Lucy |  |  |  | Costs info in comment |  |  | 1J | Adjusting the bank account on offer templates (German, French and English) | Correct bank information | 5 | sonkur | 2 | 120 | YES | 23.04.2020 |  | IMPLEMENTED | 7961 | The cost is split to Central and IT |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B3FCF814E-2817-4382-BEB2-DD0A9E4C881D%7D&file=RFC%20-%20Offer%20HL%20Switzerland.docx&action=default&mobileredirect=true
24.02.2020 | M.Pianka |  |  |  | HL Display AB - IT |  |  | EDI | Integration with Edeka (Germany) | Remaining parts of EDI Rollout project | 5 | MP | 12 | 720 | YES | 10/03/2020 |  | IN PROGRESS | 7753
24.02.2020 | M.Pianka |  |  |  | HL Display AB - IT |  |  | EDI | Integration with EHF Portal (Norway) | Remaining parts of EDI Rollout project | 5 | MP | 12 | 720 | YES | 10/03/2020 |  | IN PROGRESS | 7677 | 23.04.2020 Marcin and Sonia wil lschedule a meeting how to resolve the payer address problem 12-05-2020 We received a clear information how to handle the payer address - need small investigation on developer side what needs to be change
25.02.2020 | O. Pedroncini |  |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | Incoterm is needed on invoices (standard, advance, credit) | No special benefit needed for export principally | 5 | MP | 8 | 480 | YES | 10/03/2020 |  | SPECIFIED | 7921 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQ9NZsz20OBMhi9WabRGqmEBrAtkcwJCiVglt5EZstRwPQ?e=R8w87h
26.02.2020 | O. Pedroncini |  |  |  | Costs info in comment | West |  | 1J | Part 4: Order modification when order is blocked. When we unblock an order and CSO change date or other information, this block again the order. We should have the possibility to modify information on the order and this will not block again this one. If we change the total amount only this should block the order. | Improving communiaction between sales- finance and logitics. | 4 | MP | 6 | 360 | YES |  |  | INVESTIGATION |  | Marcin: Should we treat it as a defect? 10.03.2020 - We should involve a full CAB team to discuss this point 12.03.2020 - Inc. 14883 to analyze if it is a defect or feature is needed. 14-05-2020 Need discussion with Kinga and Pawel 07.09.2020 - Cost split between area West and UK |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ebk4BzymKf5FkFnCTN5sIPoBr_pGWGCTLeKwktpiFMuY6g?e=Lkwj2O
26.02.2020 | O. Pedroncini |  |  |  |  | West |  | 1J | Part 5: Email when modification on field kus.rabklass1. When field kus.rabklass1 =”Investigation execute” an email should be sent to the CSO | Improving communiaction between sales- finance and logitics. | 4 | MP | 8 | 480 | YES |  |  | INVESTIGATION |  | 10.03.2020 - Marcin will check with Olivier and Laurence why it is necessary 12.03.2020 - Mail sent 14-05-2020 Need discussion with Kinga |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Eb-G_aKKsEJHjGkKyswmhgUBEfP09E2g3NWe3GY9rNndKQ?e=Bdvjjq
26.02.2020 | O. Pedroncini | [6 empty] | 1J | Part 6: Bug need to be fixed on field. Last point: On order1 field VKUSKUNDSALDO is not working. Check this one to have the right information on the system. | Improving communiaction between sales- finance and logitics. | 4 | MP |  | 0 |  |  |  | ON HOLD |  | 10.03.2020 Marcin will ask Olivier (and Laurence) for a details/ 12.03.2020 - Mail sent 14-05-2020 Sonia will check this bug |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXuypDSb9jNImvXK68N9fSYB87Fce2LExI7MmnN9VP2yTQ?e=J7Dr1l
26.02.2020 | O. Pedroncini |  |  |  | Costs info in comment |  |  | 1J | Part 1: Development purpose: Possible to print advance payment invoice with status Entry in progress. Today order should be on entered to be able to print the advance invoice. When invoice is paid with a payment (not matched with a credit note), and we have a voucher number, only in this case the order should be unblock automatically and as we have status unblock an email should be sent to sales assistant. | Improving communiaction between sales- finance and logitics. | 4 | MP | 6 | 360 | YES | 17-06-2020 |  | SPECIFIED | 8025 | 10.03.2020 - We should involve a full CAB team to discuss this point (moved to April) 14-05-2020 Sonia will check with Kay if they are using the advance payment flow 25-05-2020 UK is not using Advance Payment flow, but agress that it should be able to print it in the Entry in Progress status 17-06-2020 Cost divided into West, Central and North |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWyE6BompxpEmgzerZHTYwUB8hc9U86EpKkW9VTfelie6g?e=GPBZV3
26.02.2020 | O. Pedroncini |  |  |  | Costs info in comment |  |  | 1J | Part 2 Development purpose: Automatic credit limit unblock. When customer is over the credit limit all news, orders are automatically blocked. But we should have a functionality when the customer is again under the credit limit ( due to invoice payment for example), the order should be unblock, but automatically, in this case email should be sent to sales assistant and logistic( only if the picklist was printed) | Improving communiaction between sales- finance and logitics. | 4 | MP | 24 | 1440 | YES |  |  | INVESTIGATION |  | Marcin: how about orders blocked based on other limit than credit limit? Should we discuss with finance? 10.03.2020 - We should involve a full CAB team to discuss this point (moved to April) 14-05-2020 Sonia will contact Kinga if this should be moved to the finance 9-7-2020 Costs shared between West, UK finance & North finance |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ERLiaUVarhZEiP8Wnzh7rSoB0HLSyUuPxaon3hTUPx_RWQ?e=AKwfph
26.02.2020 | O. Pedroncini |  |  |  | Costs info in comment |  |  | 1J | Part 3: Development purpose: Email when customer blocked manually When a customer is blocked manually by the accounting department such information should be sent automatically to sales assistant and logistics (only when pick list is printed), same for manual unblock. | Improving communiaction between sales- finance and logitics. | 4 | MP | 8 | 480 | YES |  |  | INVESTIGATION |  | 10.03.2020 - We should involve a full CAB team to discuss this point (moved to April) 14-05-2020 Sonia will discuss this with Kinga and Pawel 9-7-2020 Costs shared between West & UK finance |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQiDYSEM2zdGmQK5k99C-vcBY8eeixWxGfRDCYA_mLzS2w?e=HPdcle
04.03.2020 | M. Lekstutis | [6 empty] | 1J | Adjust automatic currency update functionality for different dates | Improvement after automatic currency update failure related to INC-12562 | 6 | ML |  | 0 |  |  |  | IMPLEMENTED | 7813
27.01.2020 | M. Ronn |  |  |  |  | North East |  | CRM | Integrate Sales portal with CRM (through Jeeves) to send info about meetings | Improved sales and communication with customers for Field Sales | 5 | MP | 32 | 1920 | YES | 12/02/2020 |  | IN PROGRESS | 7849, 8014 | 11-02-2020 Marcin will check with Magnus who should pay for the development (and for the future - how about project - it could resolve this issue) 12-02-2020 Marcin sent a proper email. Answer: Area North East 17-03-2020 Waiting for confirmation from Gung, that they are ready 21.04.2020 There will be a startup meeting on 29th of april 11-05-2020 Feature added to the 212 sprint |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EZIOM_Oxqa5MmAAzAGY9-JQBbQbtuXzh4SZMuRSFVTFgbw?e=4n1tla
27.01.2020 | M. Ronn |  |  |  |  | West |  | CRM | Connection between sales portal and CRM (through Jeeves) in company 1600 | Improved tracking of opportunities | 5 | MP | 8 | 480 | YES | 12/02/2020 |  | INVESTIGATION | 7850 | 11-02-2020 Marcin will check with Magnus who should pay for the development (and for the future - how about project - it could resolve this issue) 12-02-2020 Marcin sent a proper email. Answer: Area West 17-03-2020 Waiting for confirmation from Gung, that they are ready |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYE7fl3-xetDmGvabMd1v6YBH6i4KurQ2Z4JK1ApLLe0nA?e=ASV3Qi
27.02.2020 | E. Hermio |  |  |  | Costs info in comment |  |  | 1J | Adjust the Capacity control Tool in a way that the first ”orange” pop-up can be locally turned off. | “Orange” pop-up appears too early for Nordic which in turn causes CS not to follow the guidelines of Capacity control | 4 | MP | 4 | 240 | YES |  |  | SPECIFIED | 8013 | Marcin: How about change this functionality to make it more flexible, depending on the unit? To be discussed during March CAB meeting Kamil: 10 hours in order to fix it, 24 hrs in order to fix and prepare the flexible solution 10.03.2020 Marcin will check with Kamil and Paweł why in the previous estimation there was 2 hours. And check who is using. 23.04.2020 Sarah will check with Gliwice RDC how they are using the Capacity Control Tool 12-05-2020 4h estimation 14-05-2020 Cost will be divided to North and Central |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Eax7F5dsSBxMvZ0EfpOCqpoBdB_TXy2JCwHpZATc1NYktA?e=TmSv2E
27-04-2020 | A. Mamińska |  |  |  | HL Display Romania |  |  | 1J | Due to the change of the bank account number on Romanian invoice templates, there is a need to also have invoice templates with the old bank account | Legal demand | 5 | sonkur | 8 | 480 | YES |  |  | SPECIFIED | 7963
24-03-2020 | J. Steffen |  |  |  | HL Display AB - Finance |  |  | QV | Sales market Russia to be moved from area North-East to area Central (historical data as well). This is for all reports where area is an option. Also ensure that the Daily sales reports sent on April 8 and later will show Russia in area central instead of North-East | This is a necessity for our area managers, controllers and group functions where we analyze and make decisions based on our area structure. Without this change it would take a lot of extra time to manually adjust figures between areas. | 5 | sonkur | 4 | 0 | YES | 24-03-2020 | 08-04-2020 | IMPLEMENTED | 7922 | Need following to be done in Qlikview on April 8 (not earlier). Jessica Steffen and HL AB accepted the costs. |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B216FB7DB-C0F6-41A6-AEC3-7606F720BEBB%7D&file=RFC%20-%20Change%20area%20for%20Russia%20in%20QV.docx&action=default&mobileredirect=true
27-6-2018 | M. Stasierska |  | Emilia Hermio |  |  |  |  | 1J | We would need to have a change in the algorithm based on which “sales date” on invoice is generated. For now that date is the same as date when Warehouse staff put the sales order into status “dispatch started”. However from Accounting perspective the “sales date” should be equal to the date when sales order is put by the WH staff into status “Released for invoicing”. This is fundamental especially at the end of month when WH staff is putting on 31/05 SO into status “dispatch started” and is releasing for invoicing only on 01/06 and on the invoice we should have 01/06 and not 31/05 as a sales date. | This is to secure that we respect accounting rules in organization and avoid tax issues | 4 | MP | 32 | 1920 |  |  |  | ON HOLD |  | Marcin: Back to this point with finance and warehouse (how often?) Marcin: Reminder sent 10-7-2018. There is issue with different names for the same field. And it is also connected with releasing date (logistic area). Marcin: Contact with Jeeves - they will check with developers if such case could be fixed (release date is not overwriten during partial shipment). Jeeves took it as proposition of developement. 2018-12-11 Discussion is still in progress. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWymXuEm-K5JtAQj65ZlemgBwobFhuVQ0p_Otg4B6QQ53A?e=FQnJcM
28.01.2019 | E. Hermio |  |  |  |  | North East |  | 1J | We would need a solution that based on the OD-classification an automatic text would appear (OA, OC, invoices) under the items | With this solution we reduce the number of “wrong” returns of non-stocked items | 4 | MP | 12 | 720 |  |  |  | ON HOLD | 7847 | EH 14/02: Supply Chain will change the Item classification system - we need to wait for that to be clarified first |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EfDFxkjAbQVLgc_Sh6teCkYBoaAOwEB4-5drlRyqJFNIbA?e=fxu4tg
28-02-2020 | O. Pedroncini | [6 empty] | QV | QV report with KIT information |  | 4 | MP |  | 0 |  |  |  | INVESTIGATION |  | 10.03.2020 - Marcin to contact with Olivier if we could ues existing report (order statistics and details). If not, then we expect a mockup. He should also chect this requirement with other area controllers 12.03.2020 - Mail sent to Olivier 23.04.2020 Sonia will send an reminder to Oliver 14-05-2020 Sonia will check with Hanna and Oliver 13/08/2020 Sonia will schedule a meeting with Olivier and Laurence |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ETZ3LrdCS1VDg_WvQcdu7CIB8Z6gXl4ey-19m5thQFvXSg?e=HIDHkB
4.11.2019 | E. Hermio |  |  |  | Costs info in comment |  |  | 1J | Upload quotation rows in estimator (similar like it is in order1). | Increases efficiency in CS | 4 | MP | 24 | 1440 | YES | 23.04.2020 |  | INVESTIGATION |  | To be discussed with Kay and Laurence in December 10.12.2019 Point will be discussed in January 2020 11-02-2020 Waiting for full aproval to divide costs 10-03-2020 Waiting for full aproval to divide costs 23.04.2020 Costs will be divied to all four Areas |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUs6ighjay1GhSY038bANq8BDHwN5iAzo-I2j4JV4utXBA?e=15vNXJ
30.08.2019 | M. Pianka | [6 empty] | 1J | Presentation - functionality to check minimum BC and BC margin on item level (based on value from item group) |  | 4 | MP |  | 0 |  |  |  | REJECTED |  | 10.9.2019 - Marcin will check with dev team details of this functionality and back to sales team 17.9.2019 - Case passed to dev team. Waiting for response. 11-02-2020 Marcin will check with dev team. 23.04.2020 Sonia will conract dev team to check this 12-05-2020 Investigation from developer: fucnionality compares fields q_hl_margin_bcu and q_hl_margin_procent from Item Group with margins that are calculated by Jeeves on order row (Row margin BCU and Row margin %). The block message appear when: order_margin_bc is smaller that vg_margin_bcu and order_margin_percent is smaller than vg_margin_percent. It works only for Price type = Manually and for order type that are not Credit order, Price adjustment and Sample
8.7.2019 | S. Lucy | [6 empty] | 1J | Please make analyze and find a solution to avoid invoicing (by mistake) orders by people from other units. There should be also option to assign more then 1`sales market to the user | Currently it works only for button "invoice" - not for printing from menu | 5 | MP | 8 | 480 |  |  |  | ON HOLD |  | Kamil: HL Sales market in Jeeves is the customized development. Standard printing is not deisgned to handle the sales markets. Development possibilities are limited. There is an option to create a button and to hide the reports from the menu - this must be investigated first. If we use button only, we can assign users to sales markets and limit the scope of the Jeeves Templates report. Development 40-60 hours, must be investigated first. 8 hours needed in order to investigate first. 9.7.2019 Marcin will check if we could use similar solution to existing one (checking freight for orders). Sarah will accept costs about 10hr. Marcin: Kamil suggested to contact directly with Jeeves if they could develop any solution to cotrol invoicing process - question asked 29.8.2019 (inc number #190829-000003) Jeeves: developement sugestion (id: 29543) Answer from Jeeves to be waited |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ET7Fj7ng3U1LrgbgAJ4bjwIBivo-fRug_uL4EdrBd5Du5A?e=1C1Pz6
15-06-2020 | I. Cupina |  |  |  | HL Display Nordic |  |  | 1J | Credit limit field in program kus as mandatory field in 1210 | All new customers will have credit limit, will avoid issues with 0 credit limits | 4 | sonkur | 2 | 120 | YES | 17-06-2020 |  | SPECIFIED | 8026 | 15-06-2020 The cost will be taken by HL Display Nordic AB |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BB07C3324-8D17-47C9-AFFE-156A698A4A30%7D&file=Request%20for%20Change%20-%20HL%20Display%20Nordic%20Ab%20Field%20credit%20limit.docx&action=default&mobileredirect=true
09-06-2020 | J. Holdorf |  |  |  | HL Display Norge A/S |  |  | 1J | Norwegian translation in templates | Re-mapping of fields to be shown on OA, OC, delivery note and Invoice. We need to show field from item desc. Language, not item descr. 2 as it is today. | 4 | sonkur | 8 | 480 | YES | 17-06-2020 |  | SPECIFIED | 8027 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B28EECB13-732B-489B-8C95-C041D30EDA54%7D&file=Request%20for%20Change%20-%20Template%20-%20HL%20Display.docx&action=default&mobileredirect=true
19-05-2020 | E. Hermio |  |  |  | Costs info in comment |  |  | 1J | Improving the claim statistics | Improves CS and WH efficiency, improves statistics and follow up of an important part of the sales process – claims | 5 | sonkur | 36 | 2160 | YES |  |  | OPEN |  | 09-07-2020 8h development to make claim reasons locally (costs to all 4 areas), the rest Area Nordic
25-06-2020 | S. Lucy | [6 empty] | 1J | Popup message from item in a different colour | In Area Central we use the text field in item program for important information during entering process of the order. With the tick “Show edit at order” the information pops-up during entering process. if it is possible to have this pop-up in a different color? Orange or red or something? We have so many pop-ups that the risk is high that the pop-up will not be read. With having it in a different color, it would make almost “impossible” to not read it. | 4 | sonkur | [5 empty] | REJECTED |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B3EEC9A91-B035-424F-B2FA-5E8D20A5404F%7D&file=Request%20for%20Change%20-%20Item%20Information%20Pop-Up%20in%20different%20color%20-%20HL%20Display.docx&action=default&mobileredirect=true
01-07-2020 | S. Lucy |  |  |  | Costs info in comment |  |  | 1J | Popup message in Estimator | Customer Internal Text popup message when creating a new offer | 4 | sonkur | 8 | 480 | YES |  |  | OPEN |  | 09-07-2020 cost divided to all areas; Sonia will check the estimation with checkbox in kus
03-07-2020 | E. Sporrenhjelm |  |  |  | Costs info in comment |  |  | SHAREPOINT | Sharepoint Dynamics | We are going to create a reflection from SharePoint to Dynamics so the users don´t need to go true SharePoint to see the documents that are related to a specific post in CRM. | 4 | sonkur |  | 5 hours * Sirocco hourly rate ~ 5 * 1200 SEK = 6000 SEK | YES |  |  | OPEN |  | 08-07-2020 The best is indeed to split between the HL Sales Areas: Central, UK, Nordic and WEST
27-07-2020 | S. Lucy |  |  |  | HL Display Österreich GmbH |  |  | 1J | New GTC Austrian SU | Austria has new GTC starting from 1st August 2020. Therefor GTC in ofhestimator for Sales Market Austria needs to be adjusted | 5 | sonkur | 4 | 240 | YES |  |  | OPEN |  |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BEF65A592-6B7D-4A5B-9695-F2B9EBA861A8%7D&file=Request%20for%20Change%20-%20New%20GTC%20Austria%20%20-%20HL%20Display.docx&action=default&mobileredirect=true
27-07-2020 | S. Kurtz |  |  |  | HL Display Middle East FZCO |  |  | 1J | Collective invoice template | One of the Dubai's clients requested a collective invoice. Currently there is no proper tax invoice for collective invoicing. | 5 | sonkur | 10 | 600 | YES |  |  | OPEN |  | 13/08/2020 needs approval from Andrej regarding the cost
01-09-2020 | S. Kurtz |  |  |  | HL Display Romania |  |  | 1J | New HL Display Romania address - updateting the address on Jeeves templates | Legal demand | 5 | sonkur | 2 | 120 | YES |  |  | OPEN |  |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B849EB9DC-5E47-41D9-9F5F-885054D2C120%7D&file=RFC%20-%20New%20HL%20Display%20Romania%20address.docx&action=default&mobileredirect=true
14-09-2020 | T. Yrjonen |  |  |  | HL Display Suomi Oy |  |  | EDI | Advance payment e-invoice in Tieto EDI flow | More countries are using advance payment flow, we need to implement advance payment flow in the EDI system | 4 | sonkur | 4 | 240 | YES | 08-10-2020 |  | OPEN |  | To be checked the general need of Advance payment in all EDI connections before development |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BF2E6D378-714E-4B77-A4CD-3791323D50DC%7D&file=IT%20Request%20for%20Change%20INC-20094%20Advance%20payment%20e-invoice.docx&action=default&mobileredirect=true
14-09-2020 | T. Yrjonen |  |  |  | HL Display Suomi Oy |  |  | EDI | Missing info between e-invoice vs paper invoice (country of origin) | Legal demand: country of origin, commodity code and weight are required to be displayed on invoices, e-invoice is missing country of origin in comparison with Jeeves template of invoice | 5 | sonkur | 4 | 240 |  | YES |  | SPECIFIED |  |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B3ECACC01-3539-46AD-AFDD-BD539061E7EE%7D&file=IT%20Request%20for%20Change%20INC-23745%20Missing%20info%20between%20e-invoice%20vs%20paper%20invoice.docx&action=default&mobileredirect=true
18-09-2020 | S. Kurtz | [6 empty] | 1J | Our reference or other field with Customer Service Officer on the planning list intead of created by | More and more automatically created orders are in Jeeves, in the planning list in the column Created by we see hlit2 or kongun, Customer Service Officers has extra work to determine which order belongs to who | 4 | sonkur
08-10-2020 | E. Lardic |  |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | Upload portal improvement | Avoid mistakes due to currently conversion factor done manually. End up in wrong qties delivered to customer, wrong price. Ends up with need to proceed with Credit Order, Returns. Secure the quality & service level offered to our customer | 4 | sonkur | 12 | 720 |  |  |  | OPEN |  |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B00A77422-12A8-400D-9735-DEFA3B77D9C4%7D&file=Request%20for%20Change%20-%20Upload%20portal%20improvement%20(Conversion%20Factor)%20v2.docx&action=default&mobileredirect=true
08-10-2020 | M. Ronn |  |  |  | Costs info in comment |  |  | CRM | Sales Portal integration towards CRM | All opportunities to be created and added on the fake sales person CRM Admin. This so we can remove users from CRM. Implemented for all countries using the Sales Portal: Sweden, Norway, Finland, France, Germany, Benelux | 4 | sonkur | 2 | 120 | YES | 08-10-2020 |  | OPEN |  | 08-10-2020 Cost splited into all (?) areas (?)
08-10-2020 | O. Pedroncini |  |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | VAT number of the POD appearing on the invoice | We are able to fill a point of delivery on the order program. On invoice template we need to have the VAT number of the point of delivery. If there is no VAT number on point of delivery we have to take tha acual vat number taken in consideration on invoice template | 4 | sonkur | 8 | 480 | YES | 08-10-2020 |  | OPEN |  |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BB8109AA8-2B54-4648-A0F0-103B186843D5%7D&file=RFC%20Vat%20number%20point%20of%20delivery.docx&action=default&mobileredirect=true
13.10.2020 | E. Sporrenhjelm |  |  |  | Costs info in comment |  |  | HL WEB | Generate leads from the reports on the homepage that creates leads in CRM |  | 4 | sonkur | 16 | 960 |  |  |  | OPEN |  | 13-10-2020 cost splitted into all sales areas
Note on F88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed to HL AB Sales after review with Erwan
Note on O219: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Investigation only!

## HR
|  | Process Leader |  | Annika Haaker
|  | Business Coordinator |  | Kamil Saczka
Date | Requested By | Authorized By | Approved By | HL Unit | HL Area | Business Consultant | Release | Product | Description | Justification | Prio | Added By | Est Dev (hrs) | Est Cost (EUR) | Decision | Decision date | Est Deliv Date | Status | Feature ID | Comment | Cust notified | RFC Link
16/11/2018 | Marika Westrin |  | Annika Haaker | HL Display AB - HR | Central |  |  | TALENTSOFT | Talentsoft - Sync end-date for users to AD | We will be able to remove accounts in a much secure way. Also, we will comply much better with GDPR-regulation. For security this is also an improvement. Ex-employees will not be able to log on to the HL-accounts. |  | KASC | 6 | 400 |  | 2019-03-28 |  | OPEN |  | Kamil to talk to Anna. 2019/01/24 Mail Sent to Anna C, to be moved to HR pre-CAB 2019/02/11 Audit to secure the process, remark that we have users that are still able to logon. 2019-04-05. Approved by Annika Haaker. Marika will take action with GDM to implement this. Aslo to update Philippe if any instructions for managers needs to be updated. |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B845DEF06-4628-499A-91F6-93ABF3940495%7D&file=INC000000795958-RFC-%20Talentsoft%20-%20Sync%20end-date%20for%20users%20to%20AD.DOCX&action=default&mobileredirect=true
03/12/2018 | Dawid Wybierek | [6 empty] | SHAREPOINT | HL Sharepoint Calendar or Jorani | As an HL Employee I want to quickly add vacation/sick leave dates to some webapp and see how many days i can use to spend more time productively and relieve the HR department from repetitive manual activities As a manager I want to see calendar with marked vacations/sick leave from all my subordinates all in 1 clear view To better plan projects in our organizationAs a tester/developer/BC | 3 | KASC |  | 0 | NO |  |  | OPEN |  | 24/1 To be discussed with HR. DevCore has a solution for it. |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/New/calendar%20RFC.docx?d=w752655f9ed224dd7a813a66b75fecbf1&csf=1&e=BonaVk
29/09/2020 | Anna Ericsson | Annika Haaker | Annika Haaker | HL Display AB - HR |  |  |  | HL WEB | HL HighLight Survey tool for improvements | We need to build a solution for HR and for HL managers to coordinate the action plan of highlight survey improvement |  | KaSc |  | 0 | Yes |  | 1/11/2020 | IN PROGRESS
| Marika Westrin |  |  | HL Display AB - HR | Central |  |  |  | Look into Onboarding Process. If we can start using IT´s tool a bit better | To be able to get a user onboard faster. With accounts, access and equipment |  | maws |  | 0 |  |  |  | INVESTIGATION |  | At the moment, we just started to look into this. No cost so far. More info will come. Marika and Mikael G are working on this with Anna Ericsson.
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN

## Finance
Process Leader |  | Kinga Leśniewska
Business Coordinator |  | Kinga Leśniewska
Date | Requested By | Authorized By | Approved By | Business Consultant | HL Unit | HL Area | Release | Product | Description | Justification | Prio | Added By | Est Dev (hrs) | Est Cost (EUR) | Decision | Decision date | Est Deliv Date | Status | Feature ID | Comment | Cust notified | RFC Link | Approved Date
| Valentina Semenova Rem = 414856 date 17/11/2015 | [6 empty] | Current Russia | In Jeeves Prod Rus need to check debts. There should be Invoice No(RU) and Invoice No., go together. | We want to have a list of the unpaid invoices with invoice no.(ru) | 5 |  |  | 0 | NO |  |  | REJECTED |  |  | 19/11 work around shown - retrive data from fh program 25/11 waiting for feedbak if work around is ok 01/12 still not respons from Russia 01/12 data can be retrive from fh to excel - no need of new report - confirmed by Valentina
| Jessica Ljunggren - RFC directly to BC | [6 empty] | One Jeeves | We would like to use the xakon function but since this is set as a global program today we cannot use this. We will save time and have a more effective way of work if we can use xakon locally. | save time - be able to create auto postings and allocaltion rules licaly | 4 |  |  | 0 | YES |  |  | IMPLEMENTED | 4887 | 4887 | 1/12 feature in sprint 96 | https://docs.google.com/document/d/1-2EG3q3bRukXyc0psjXYY8glHFzhReAgJ7IOTsKFOXY/edit# https://docs.google.com/document/d/1Avte4pyddVnBHLGC3E7xCNeQFeI1HgrffcVim64TW3U/edit
| Katarzyna Klopotowska - RFC directly to BC | [6 empty] | One Jeeves | Activete job moving EDi invoices from EDFH to supplivcs for 1810 | Reducing the time of registered invoices, reducing possible mistakes | 5 |  |  | 0 | Yes (this job is active in all compamnies in1J which are using EDI) |  |  | IMPLEMENTED | 4918 | 4918 | 09/12/2015 feature in sprint 97 | https://drive.google.com/a/hl-display.com/file/d/0B6hrQ4ninuBTT0VuRnZjMWpEbVk/view?usp=sharing
| Jessica Ljunggren - RFC directly to BC | [6 empty] | One Jeeves | We´d like to add field Pipe in form, program xkvr | Pipe is standard dimention that need to be visible | 4 |  |  | 0 | YES |  |  | IMPLEMENTED | 4924 | 4924 | 11/12/2015 feature in sprint 97 | https://drive.google.com/open?id=0B6hrQ4ninuBTdGVtU1I0VDJ5OGc
| One Jeeves Support/BC | [6 empty] | One Jeeves | missing fields in VALT program | To ba able to chceck which journal was not posted user needs to see all journals in standard tab | 4 |  |  | 0 | YES |  |  | IMPLEMENTED | 4958 | 4958 | 2016/01/07 feature in sprint 99 | https://drive.google.com/a/hl-display.com/file/d/0B6hrQ4ninuBTTXhENV9ZRVhWaFE/view?usp=sharing
| Baris Rasinski | [6 empty] | Curret Jeeves | Change of Query | Need to create a report, change will make it nuch easier and quicker | 5 |  |  | 0 | YES |  |  | REJECTED | 5001 | 5001 | YES IN Business TEST
| IT dev/BC | [6 empty] | ONE Jeeves | missing fields in program BANK | In program BANk part of the standard fields is not visible - due to that users can not insert data corectly. Data from this program are used for EDi cominucation that is why request coming from IT/BC | 5 |  |  | 0 | YES |  |  | IMPLEMENTED | 5029 | 5029 | 2016/01/27 feature in sprint 100 | https://drive.google.com/open?id=0B6hrQ4ninuBTY3RYc2xRRFdDMjQ
| Caroline Xu | [6 empty] | ONE Jeeves | inventory location in vfaktst | possiblity to easy differentiate sales doen by HUB and sales unit. Can also be helpfull for other countries to differentiate different sales flows such as customer own goods, traded ect | 4 |  |  | 0 | YES |  |  | IMPLEMENTED | 5030 | 5030 | 2016/01/27 feature in sprint 101 2016/03/02 CFT | https://drive.google.com/a/hl-display.com/file/d/0B6hrQ4ninuBTUFBwMnBOemZ0TEE/view?usp=sharing
| Sandra Malczyk/ Magda Kruk | [6 empty] | One Jeeves | Adding local account to program Nobi iin tabs : customer invoices and suppier invoices to bea bale to poste bank statement more efficienlty | to be able to poste bank statement more efficiently | 5 |  |  | 0 | YES (project 8020) |  |  | IMPLEMENTED | 5359 | 5359
| Magda Kruk (Czerwińska) | [6 empty] | One Jeeves | Picture of printed invoice safed in fh | Legal demand to show exacly the same copy of the invoice as orginal sent to customer if tax office will required data. additionaly control function for fiance - to be able to follow if corect templaets are used for printout of corective invoices comind from credit order and price adjustment | 5 |  |  | 0 | YES ( project 8020) |  |  | IMPLEMENTED | 5353 | 5353 | sprint 109 | https://docs.google.com/document/d/1Dc-jABl6Y0Iq4mFDNNr11c6_XICv3ltzXgChcUTZGFw/edit
| Jessica Ljunggren | [6 empty] | Curent Jeeves Hong Kong | update of alternative suppliers in Hong Kong - nessesery for implementation for new BC solution |  | 5 |  |  | 0 | YES |  |  | IMPLEMENTED | 5474 | 5474 | sprint 111
| Imee Santos | [6 empty] | One Jeeves | bank charges in in currency in INB - field need to be moved from all fields to HL Standard | for accounts restricted just for currency standard field avaliable at the moment can not be used - user need to see fileds for currency - at the moment only manula posting of bank charges can be used as workaround - additional workload | 5 |  |  | 0 | Yes (project 6263) |  |  | IMPLEMENTED | 5471 | 5471 | 5471 sprint 111 | https://docs.google.com/document/d/1Sniuv-ue98sXYhWTaj40WSKvCtmaHcCyd6kJpam-6Mw/edit#
| Kinga Leśniewska | [6 empty] | One Jeeves | exchange rate in vfaktst - the wrong exchange rate is shown at the moment - it is order rate insted of invoice rate |  | 4 | KL |  | 0 | YES |  |  | IMPLEMENTED | 5473 | 5473 | sprint 111
| Jenny Hedberg | [6 empty] | Current Jeeves HFS | macro updating OCR number for HFS - nessesery for finalyng implementation of sepa functionality |  | 5 | KL |  | 0 | Yes (Sepa project) |  |  | IMPLEMENTED | 5497 | Go through SEPA project - plan time for release 112? Rough est 16-24 h 5497 sprint 112 | 5497 sprint 112
| Kinga Leśniewska | [6 empty] | One Jeeves | VAt rate on the item - should be local filed as all Vat releated fields - now is global | no possiblity to use Vat on item level due to fact that field is global | 4 | KL |  | 0 | YES |  |  | IMPLEMENTED | 5477 | 5477
24-05-2017 | Bożena Paszkowska | [6 empty] | One Jeeves | files in GDPDU_EXPORT. The file is mandatory element of reporting to the Tax Office about VAT. Right now it’s impossible to generate a file in correction version. | legal purposes | 4 | BETR |  | 0 |  |  |  | IMPLEMENTED
15.02.2018 | Kinga Lesniewska/ Julia Homik | [6 empty] | One Jeeves | add log of changes on TF fileds | to make analises possible | 4 | KL |  | 0 | YES |  |  | MOVED/DUPLICATED |  | KIPA: added to biger development conected with automatic TF handling - line 87
15.02.2018 | Kinga Leśniewska | [6 empty] | One Jeeves | design in programs conected with journals | a lot of fileds are missing in journals programs in HL standard tabs - due to that fact users are not able analise data by themselves | 4 | KL |  | 0 | YES |  |  | IMPLEMENTED | 6786 | 6786
15.02.2018 | Susann Radestrom | [6 empty] | Current Jeeves | auto update of currency rate from web to Jeeves | easier to operate and control | 4 | KL |  | 0 | YES |  |  | IMPLEMENTED | 6821 | 6821
07/03/2018 | Kinga Lesniewska / Jessica Steffen | [6 empty] | One Jeeves | block possiblity to add new records localy in posting templates programs | Posting templates are global and should not be modified localy | 5 | KL |  | 0 | YES |  |  | INVESTIGATION |  | KIPA: part of the bigger change concerning replication rules - moved in time due to more urgent projects and Kinga's long sick leave
2017 | Olivier Pedroncini | [6 empty] | OneJeeves | Possiblity to send payment teminders by mail directly from Jeeves | simplification of the proces, time saving, cost cutting ( no paper vertion) | 4 | KL |  | 0 | YES - agreed in West project |  |  | IMPLEMENTED | 6849 | 6849 (easy Send)
16/03/2018 | Anna Gancarz/West fiance team | [6 empty] | OneJeeves | possiblity to send invoice by mail directly from Jeeves | simplification of the proces, time saving, cost cutting ( no paper vertion) | 5 | KL |  | 0 | YES - disscused on CAB 15/03 |  |  | IMPLEMENTED | 6851 | 6851 ( Easy send)
27/03/2018 | Markus Reiterer | [6 empty] | 1J | reminder letters for PL market in 1810 | at the moment reminders to customers are handled manualy in excel/world - for time saving and bettre control it would be bettre to use Jeeves standard function for this | 4 | KL |  | 0 | YES |  |  | IMPLEMENTED |  | all templates are on place - only setup is required - done on prod; kinga need to create manual for users
12/04/2018 | Olivier Pedroncini | [6 empty] | 1J | VAt and order specific text - fields to be moved from all fields tab | fields need to be visible for users | 4 | KL |  | 0 | YES |  |  | IMPLEMENTED | 6908 | 6908
12/04/2018 | Elena Zhang | [6 empty] | CJ | China facotry sales calculation to be done on PC5 and not BC asles | Calculation in SZV is not ok according to the BC model set by the Group | 5 | JH |  | 0 | YES |  |  | DUPLICATED |  | KIPA: should be handled by Andreas as a part of production area 7/9: Moved to Production
09/05/2018 | Kinga Lesniwska | [6 empty] | 1J | VAT setup for 3901 | Starting from 01/01/2018 Dubai started to operate with VAT tax. Due to this fact VAT setup need to be done in the system. Basic setup for counting VAT on transaction level was done at the beginning of year. Unfortunately, due to missing information final processing of the setup become possible in May 2018 | 5 | Kl |  | 0 | YES |  |  | IMPLEMENTED | 6938 | 6938
09/05/2018 | Kinga Lesniwska | [6 empty] | 1J | extending function of sending invoices by mail for 1190 - program ffhlevp |  | 4 | Kl |  | 0 | YES |  |  | IMPLEMENTED | 6955 | 6955
15/05/2018 | Olivier Pedroncini / jessica Steffen/Aleksandra Cieloch | [6 empty] | 1J | adding fileds to list view in supplinvcs | to analize supplier invoices fro goods in transit, VAt, monthly recon ect several fileds should be added to list view in supplinvcs program: PO No VAt/tax curr supplier ref lr.vbfaktmoms (FCU) lr.levingmoms (BCU) lr.redovisnar lr.period lr.ktonrresksaldo (request from 1810) - Pmt date (now we have to click on “All pmts on invoice” to get it) - Internal VAT/tax specification status – it would be great if there was information on the list if there is internal invoice already created or not Net, currency Net, BCU Accounting Date Arrival Date | 4 | KL | 6 | 360 | YES |  |  | IMPLEMENTED | 7026 | discussed Pre CAB meeting 22/05/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Kamila Saczka, Kinga Lesniewska). Decision - feature will be created by Kinga 19/06/2018 KIPA: feature 7026 27/08/2018 KIPA: 7026 implemented on prod 24/08/2018; info sent to FCs 28/08/2018 | 7026
15/05/2018 | Joanna Skiba | [6 empty] | 1J | adding sales person filed to Hl standard tab in bkus and xkfhk | in 1810 payment reminders will be issued by sales support staff. Each prson would like to woprk only with cown customers and issue reminders only for own customers - that is why they want to have possiblity to chose customers by sales persone in bkus program | 4 | KL | 2 | 120 | YES |  |  | IMPLEMENTED | 7026 | discussed Pre CAB meeting 22/05/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Kamila Saczka, Kinga Lesniewska). Decision - feature will be created by Kinga 19/06/2018 KIPA: feature 7026 27/08/2018 KIPA: 7026 implemented on prod 24/08/2018; info sent to FCs 28/08/2018 | 7026
15/05/2018 | Kinga Lesniewska | [6 empty] | 1J | acces to xkfhk for customer support roles | possiblity to run payment reminders flow for customer support staff in 1810 | 5 | KL | 0 | 0 | YES |  |  | IMPLEMENTED |  | discussed Pre CAB meeting 22/05/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Kamila Saczka, Kinga Lesniewska). Decision - yes for adding program to Sales support role - Kinga will mange change with 1J Support - no feature needed; request confirmed to Support 23/05/2018
16/05/2018 | Kinga Lesniewska | [6 empty] | 1J | area and sales market in XRB on Ap and Ar reports to be moved - part of cleaning project | Ar and AP reports are used only by some countries and in limited way. most of countries is using quesries, Qv reports or retrive date from fh to excel manualy. Due to that fact and also due to fact that split betwen areas and markets need to be maitain manualy in this report my proposal is to clean area and sales market from reports and leav only general ones in xrb - detailed are avaliable in QV | 4 | KL | 12 | 720 | YES |  |  | IMPLEMENTED | 7057 | discussed Pre CAB meeting 22/05/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Kamila Saczka, Kinga Lesniewska). Decision - feature will be created by Kinga 05/07/2018 KIPA: feature 7057 created 27/08/2018 KIPA: feature on internal tests. Should be released second half of September 21/09/2018 KIPA: changes on prod; released 21/09/2018 | 7057
16/05/2018 | West | [6 empty] | 1J | layout in fh | change of the order of columns | 3 | KL | 2 | 120 | no |  |  | REJECTED |  | discussed Pre CAB meeting 22/05/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Kamila Saczka, Kinga Lesniewska). Decision - request rejected - layout can be easly adjusted in excel or by moving column in One Jeeves; info send to users 23/05/2018
16/05/2018 | Olivier Pedroncini | [7 empty] | changes in F02 | goods from location customer own goods should be shown on the report with value 0 not with carrent cost price as it is now. In spite of the fact thta ther is possiblity of creating report without customer own stock 1600 would like to change as described above. | 4 | KL | 10 | 600 | no |  |  | REJECTED |  | discussed Pre CAB meeting 22/05/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Kamila Saczka, Kinga Lesniewska). Decision: request rejected - there is possiblity to print report without customer own stock. As alternative Kinga will check reports avaliable is xarla program KIPA 25/05/2018 Olivier was inform by decission; xarla program can be used as alternative for F02 - this was also sent to Olivier
17/05/2018 | Olivier Pedroncini | [6 empty] | QV | split of stock provision by the pipe | Stock transaction (deliveries) are not connected to sales market so there is no possibility to split stock by the PIPE but in spite of that WEST is pushing to have this kind of split - final solution needed - rule or development |  |  | 40 | 2400 | to be discussed further |  |  | ON HOLD |  | discussed Pre CAB meeting 22/05/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Kamila Saczka, Kinga Lesniewska). Decision: Eva will continue disscusion on the Group level. Group decision (rule) needed before any developments will be decided KIPA 25/05/2018 - Olivier informed about the status KIPA 14/06/2018 - still open - waiting for Eva KIPA 05/07/2018 - provisin should be split but rules for this split will be given by the Group. Rules are disscused. Report will be rebuilt when rules of the split will be comunicated by the Group KIPA 28/08/2018 - disscusion on a Group level is ongoing (project in supply chain) - decision expected till the end of 09/2018 KIPA 05/11/2018 - due to Eva's leave questions in this are should be directed to Martin Saldenius KIPA 20/05/2019 - questiona sent to Jessica Steffen where we are KIPA 16/9/2019 - question about status of Gropu decision sent to Jessica KIPA 23/09/2019 - Grup disscusion will be taken week 39-40; Jessica will come back with conclusions KIPA 24/09/2019 - Martin Saldenius will incorporate this into the Eazystock project. Till it will be ready RFC remain on hold
18/05/2018 | Kinga Lesniewska | [6 empty] | 1J/QV | move of report customer invoices from XRB to QV | One Jeeves cleaning - report is not often used | 3 | KL | 16 | 960 | to be discussed further |  | 12/2018 | INVESTIGATION |  | discussed Pre CAB meeting 22/05/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Kamila Saczka, Kinga Lesniewska). Decision: Kinga will check possiblity of use of dinamic report function 27/08/2018 KIPA: action still open due to holidays period. Should be process till the edn of 2018 20/05/2019 KIPA: Kinga will come back to this during 05-06/2019 16/09/2019 KIPA: report is used by UK. It can be moved to QV but the final decision and cost owner should be disscusde during CAB 17/09/2019
18/05/2018 | Kinga Lesniewska | [6 empty] | QV | AR info send by mail form Ar aged report in QV | to limit use of queries, limit use of Ar report in 1J , make analizing of Ar easier (collection); fulfill request conected with acces to FH program; save time for finace who is distributing this info manualy to customer service | 3 | KL | 12 | 720 | investigated more |  | 12/2018 | INVESTIGATION |  | discussed Pre CAB meeting 22/05/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Kamila Saczka, Kinga Lesniewska). Decision: Kinga will investigate benefits of this solution - remove o licences, how many user is interested ect 27/08/2018 KIPA: action still open due to holidays period. Should be process till the end of 2018 20/05/2019 KIPA: most of user is working with AR report - they are interested in this function but as additional feature not replacing acces to QV. Kinga will continue disscusion with fiance departments
18/05/2018 | Olivier Pedroncini | [6 empty] | QV | Report for spliting additional cost by PIPE | When additional cost are added by factory in ICT drop shipment flow they are posted in HUb under supplier invoice as a cost. 1600 team want to split the cost to markets by the PIPE - to do this they need to have report showing conection of Supplier invoice with CO | 4 | KL | 20 | 1200 | YES |  |  | ON HOLD |  | discussed Pre CAB meeting 22/05/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Kamila Saczka, Kinga Lesniewska). Decision: Eva will discus this further to check if those cost should be split by the markets or shoud stay on a HUB level KIPA 25/05/2018 Olivier was informed by the progress KIPA 04/07/2018 YES from CAB metting - feature need to be created 27/08/2018 KIPA: request put on hold due to point 56. According to Kinga if point 56 will be approved report will not be needed. Question sent to Olivier.
18/05/2018 | Olivier Pedroncini | Reinhard Rollett | Eva Wennborg |  |  | Headquarter | R20.02 Feb | QV /1J | split of sales by sales market on the order row level - chang logic in 1j and in Qv; consistency of date betwenn Qv and GL (PIPE/sales market) | consistency of date betwenn Qv and GL (PIPE/sales market); possiblity to split project sales betwenn markets | 4 | KL | 48 | 2880 | YES |  | 12/2018 | IMPLEMENTED | 7299, 7403 | discussed Pre CAB meeting 22/05/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Kamila Saczka, Kinga Lesniewska). Decision: split of sales by sales market on the order row level will no give expected result: to have sales split 50% each arket two rows with the same goods will be needed - probably not accepted by customer; Implementation of already develped solution - sales market taken from invoice level insted of KUS need to bee disscused on the next pre CAb meeting KIPA 24/05/2018 Olivier and other requestors were informed by decision by mail KIPA 28/08/2018 meeting will be set to see what is really needed from bussines point of view - meeting set to 07/09/2018 KIPA 18/09/2018 possible sollution disscused with Olivier, Erwan, Julia, Jessica and Łukasz: additional tabel in Jeeves wher user will be able to add spit of ceratin orders betwenn sales markets. Tabel will be conected with DW and will send data to sales report. In Qv in sales report ther will be possiblity to see sales with and without split starting from order level. Development extimated for 48h (24h Jeeves;24h changes in QV - all reports conected with sales). Solution should be presented by Erwan on CAB sales KIPA 22/10/2018 - still waiting for Erwan's feedback from sales CAB EL 12/11/2018 : Has been presented to Pre-Cab Sales & Quotation. OK generally speaking with one remark : How will be the behavior on item level ? (just to be sure it goes to item detail level). Might be needed that we need to enter the split on order row level instead of order header 07/12/2018 KIPA: agreed that solution should be simple and spit should remine o order header level. Reminder sent to Marcin whith question when this can be process. It should be process by Marcin due to fact ta it is strictly conected with sales ( less with finance) 18/12/2018 KIPA: Marcin P will create nessesry features - agreed on the meeting 13/12/2018 20/05/2019 KIPA: feature 7299 is ready, feature 7403 is in progres. Development is managed by Marcin Pianka 16/09/2019 KIPA: 7299 implemented, 7403 ready for CFT week 38 - case drivenn by Marcin Pianka BC sales
14/06/2018 | Jessica Steffen | Kinga Leśniewska | Eva Wennborg |  |  | Headquarter |  | QV /1J | changes needs to be made in Qlikview basecost follow up report (currently in “sales process with calculation version”) | at the moment system takes incorect fields for caclulation so output is not as required | 4 | KL | 12 | 720 | YES |  |  | IMPLEMENTED | 7070 | discussed Pre CAB meeting 14/06/2018 (Eva Wennborg, Kamila Saczka, Kinga Lesniewska) KIPA 12/07/2018: first two points will be covered by defect - replacing invoice quanity with order quanity. point 3 from RFC covered with feature 7070 27/08/2018 KIPA: NOK on CFT week 34, feature is back to developer 22/10/2018 KIPA: implemented on prod | 7070 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20BC%20follow%20up%20report.docx?d=w3b7091da5fc441a7afe2b881643029e8&csf=1&e=cvfiys Spec : https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/Development%20Documentation/7070%20-%20Avg%20purchase%20quantity%20%E2%80%93%20change%20in%20logic.docx?d=w77d11957cbb34ca5a08d95163f643ebe&csf=1&e=yY9Xh2
14/06/2018 | Olivier Pedroncini | Philippe D'autume | Eva Wennborg |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | easy send improvments - add field in xkfhk which will allow to select (modyfy if needed) which payment reminder should be send by mail and which printed on paper | at the moment system is not sending mail for customer wher mail addres is not defined. Each such customer couse separate popup window apearing diuring sendin reminders - difficult towork with and to control. France is a pilot in implementing easy send functionality fr sending payment reminders - it is plan to implement it for all companies working with payment reminders | 4 | KL | 16 | 960 | YES |  |  | IMPLEMENTED | 7026 | discussed Pre CAB meeting 14/06/2018 (Eva Wennborg, Kamila Saczka, Kinga Lesniewska) 19/06/2018 KIPA: feature 7026 27/08/2018 KIPA: fetaure implemented on prod 24/08/2018, info sent to users 27/08/2018 | 7026
14/06/2018 | Olivier Pedroncini | Philippe D'autume | Eva Wennborg |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | setup in 1600 possiblity of import bank files with incoming and outgoing payments | speed up the proces of registration of bank ststements | 4 | KL |  | 0 | YES |  | 12/2018 | IN PROGRESS |  | discussed Pre CAB meeting 14/06/2018 (Eva Wennborg, Kamila Saczka, Kinga Lesniewska) 19/06/2018 KIPA: Kinga asked Olivier to contact bank and check if they are able to deliver file in MT940 format - standard used by Jeeves. 20/05/2019 KIPA: delay due to Kinga's sick leave and priority of ongoing projects
15/06/2018 | Olivier Pedroncini | Philippe D'autume | Eva Wennborg |  |  | Headquarter |  | QV | changes with QV stock provision report |  | 4 | KL |  | 0 | YES/NO |  | 12/2018 | INVESTIGATION |  | 19/06/2018 KIPA: disscusion started on a Group level - to be disscused in details on next CAb meeting (Olivier should participate) KIPA 05/07/2018; only one chenge from the RFC was approved on the CAB 04/07/2018 - the one conected with adding the date whan goods can be scraped; olivier will create separet RFC with details for that change 20/05/2019 KIPA: Kinga will disscus this with Olivier - idf this is still needed 16/09/2019 KIPA: feedbak from Olivier needed - question sent |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20%20stock%20depreciation%20V2.docx?d=w044adae2c6ec453c87b7dbf20b2c1ba7&csf=1&e=hB1cbM
21/06/2018 | Aleksandra Cieloch | Bożena Paszkowska | Eva Wennborg |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | possiblity of creation invoices in UOH with use import from Excel | In Pl it is legal demand to create credit invoice for all cash discounts. this is done with use of manual invoices - to fulfil legal demend and not involve customers. 300-400 of manual invoices is created each month in this flow - upload from excel would alow to save many working hours | 5 | KL | 24 | 1440 | YES |  |  | IMPLEMENTED | 7060 | discussed Pre CAB meeting 04/07/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Olivier Pedroncini, Alicja Mamińska, Julia Homik, Kinga Lesniewska). 05/07/2018 KIPA:feature 7060 27/08/2018 KIPA: fetaure implemented on prod 24/08/2018, info sent to users 27/08/2018 | 7060 | RFC: https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%201810%20import%20to%20uoh.docx?d=wce995a00c3104e208edef2d73eb3196e&csf=1&e=754AJH
21/06/2018 | Aleksandra Cieloch | Bożena Paszkowska |  |  | HL Display Gliwice Sp z.o.o |  |  | 1J | activation of job moving invoices from EDFH to supplinvcs in 1190 | time saving 1H per month, work with standard flow used by all 1J companies | 3 | KL | 4 | 240 | NO |  |  | REJECTED |  | discussed Pre CAB meeting 04/07/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Olivier Pedroncini, Alicja Mamińska, Julia Homik, Kinga Lesniewska) - rejected (mail from Eva 10/07/2018 - reason - number of 1140 invoices is not very large and SDl will be moved to another data base at the begining of 2019 and EDi will be replaced with ICT |  | RFC https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%201190%20EDI%20ICT%20import.docx?d=w2f1d317ff3d64cbdba2567adc5a7953d&csf=1&e=3bysyq
28/06/2018 | Aleksandra Cieloch | Bożena Paszkowska | Eva Wennborg |  | HL Display Gliwice Sp z.o.o |  |  | 1J | payment reminders templates for 1190 - PL and EN (development only for templates - rest is a matter of settings) | more efficient and standard way of woring in AR collection area - time saving 3h per month. At the moment payment reminders are not send very often - usualy once a month due to fact that creating payment reminders manualy is time consuming | 4 | KL | 6 | 360 | YES |  |  | IMPLEMENTED | 7071 | discussed Pre CAB meeting 04/07/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Olivier Pedroncini, Alicja Mamińska, Julia Homik, Kinga Lesniewska) - finall approval mail from Eva 10/07/2018; 12/07/2018 KIPA: feature 7071 created 27/08/2018 KIPA: fetaure implemented on prod 24/08/2018, info sent to users 27/08/2018 | 7071 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%201190%20Payment%20Reminders.docx?d=w6e1ad1e33bc247c681c60d498b3a9832&csf=1&e=wXvEQo https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/Development%20Documentation/7071%20-%20Payment%20reminder%20templates%20for%201190.docx?d=wbae4f33f8ef64309b922bfe75e5aafbb&csf=1&e=cYX47Y
28/06/2018 | Aleksandra Cieloch | Bożena Paszkowska | Eva Wennborg |  |  | Headquarter |  | 1J | acces to program ARASOF fo FC and AA | possiblity of different analizing of AR - just a setup - no development needed | 3 | KL |  | 0 | YES |  |  | IMPLEMENTED |  | discussed Pre CAB meeting 04/07/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Olivier Pedroncini, Alicja Mamińska, Julia Homik, Kinga Lesniewska) - finall approval mail from Eva 10/07/2018; 12/07/2018 KIPA: request sent to One Jeeves Support 17/09/2018 KIPA: should be on prod 21/09/2018
28/06/2018 | Aleksandra Cieloch | Bożena Paszkowska | Eva Wennborg |  |  |  |  | QV | report showing details nessesry for tax caclulation - income statement accounts with details | time saving and work with standard flow. Presten way of working is based on queries and due to huge nuber of lines taken from the systme working with excel files is not efficient esspetialy in second half of the year | 4 | KL | 16 | 960 | YES |  |  | IMPLEMENTED | 7129 | discussed Pre CAB meeting 04/07/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Olivier Pedroncini, Alicja Mamińska, Julia Homik, Kinga Lesniewska). 10/09/2018 KIPA feature 7129 17/09/2018 KIPA: 7129 on bussines test - waiting for Ola to be back from holidays 22/10/2018 KIPA: implemented on prod |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%201810,%201190,%201800%20detailed%20Income%20Statement%20in%20QV.docx?d=w8f1a5ad74a7f439fa9cda55efed1ed2b&csf=1&e=32bz5e https://hldisplay.sharepoint.com/:x:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20details%201810,%201190,%201800%20detailed%20Income%20Statement%20in%20QV.xlsx?d=wc58a6a07f8e447119a7f5bcaa7b2f0c1&csf=1&e=1olDcv
28/06/2018 | Alicja Mamińska | Bożena Paszkowska | Eva Wennborg |  |  | Headquarter |  | 1J | design in vouchre row registration program - move fields conected with currency | time saving 1h per month, elimination of mistakes - change global for all 1J companies | 3 | KL | 4 | 240 | YES |  |  | IMPLEMENTED | 7072 | discussed Pre CAB meeting 04/07/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Olivier Pedroncini, Alicja Mamińska, Julia Homik, Kinga Lesniewska) - finall approval mail from Eva 10/07/2018 13/07/2018 KIPA: feature 7072 27/08/2018 KIPA: fetaure implemented on prod 24/08/2018, info sent to users 27/08/2018 | 7072 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20tab%20design%20change%20finalapproval%201810,1190,1800.dotx?d=wfb0137a814d54948908dd40c58556cf9&csf=1&e=hiSolE https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/Development%20Documentation/7072%20-%20Design%20on%20voucher%20row.docx?d=w66584dd9be6944deb507482bc4e49594&csf=1&e=19MmSf
28/06/2018 | Aleksandra Cieloch | Bożena Paszkowska | Eva Wennborg |  | 1800/1810/1190 |  |  | 1J | possiblity to print accounts statement for customers without open invoices in 1810,1800 and 1190 | legal demand - till now it was done manualy once a year - time saving 16h per year. | 4 | KL | 20 | 1200 |  |  |  | REJECTED |  | discussed Pre CAB meeting 04/07/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Olivier Pedroncini, Alicja Mamińska, Julia Homik, Kinga Lesniewska). 05/07/2018 KIPa : kinga will try to find anotther place in the system for generating "blanc" account statements and then new estimation will be done 28/08/2018 KIPA: no other possiblity to print blanc account statemen separately for each customer. Question sent to Ola if thsi is really needed due to fact that according to Ola last year auditors alowed not to sent account statements at all 29/08/2018 KIPA: user withdrew request due to issues mantioned above |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%201810,%201190%20-%20Account%20Statement%20for%200%20value.docx?d=w44015bbbfcf547e79827b2d7d830a5f8&csf=1&e=M7XVQb
28/06/2018 | Aleksandra Cieloch | Bożena Paszkowska | Eva Wennborg |  | 1800/1810/1190 |  |  | 1J | possiblity to import bank statements files into Jeeves (use NOBI if possible) for 1190,1810,1800 | simplification and time saving - 2h per day; probably no development needed - just a setup in the system | 4 | KL |  | 0 | YES |  | 12/2018 | OPEN |  | discussed Pre CAB meeting 04/07/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Olivier Pedroncini, Alicja Mamińska, Julia Homik, Kinga Lesniewska) - finall approval mail from Eva 10/07/2018 12/07/2018 KIPA: change will be prcess affter summer due to holiday period 22/10/2018 KIPA: delay in implementetion due to Salmon project 20/05/2019 KIPA: delay due to kinga's sick leave |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20%20import%20of%20bank%20statements%20to%20Jeeves%201810,%201190,%201800.docx?d=w8ece6982c2474008b13553ecd5136559&csf=1&e=FDrADv
28/06/2018 | Aleksandra Cieloch | Bożena Paszkowska | Eva Wennborg |  | 1800/1810/1190 |  | R19.3 Mar | QV | Report for VAt check purpose - customer and POD data | replacing querry with standard report - querry is not working perfectly fine at the momen | 4 | KL | 20 | 1200 | YES |  | 12/2018 | IMPLEMENTED | 7269 | discussed Pre CAB meeting 04/07/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Olivier Pedroncini, Alicja Mamińska, Julia Homik, Kinga Lesniewska). 05/07/2018 KIPa : report should be build in QV but it should be useful for all companies not only GLI - requirements should be gather from all other units 23/11/2018 KIPa: feature 7269 19/02/2019 KIPA feature BTP - planed release 19.3 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20%20VAT%20check%20-%20Point%20of%20Delivery%201810,%201190.docx?d=w5bb0bd74f5dd42b78639ae60514ab4c6&csf=1&e=nb3WHn
28/06/2018 | Aleksandra Cieloch | Bożena Paszkowska | Eva Wennborg |  | 1800/1810/1190 |  |  | 1J | change of the logic concerning generating payment files for PLN payments from 1J for 1800,1810,1190 | time saving (1h per day) and work with standard flow - at the moment Gliwice are using procedure created for them at the begining of CBM wich is not efficient any more | 4 | KL | 4 | 240 | YES |  | 12/2018 | IN PROGRESS | 8028 | discussed Pre CAB meeting 04/07/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Olivier Pedroncini, Alicja Mamińska, Julia Homik, Kinga Lesniewska) - finall approval mail from Eva 10/07/2018 12/07/2018 KIPA: change will be prcess affter summer due to holiday period 22/10/2018 KIPA: delay in implementetion due to Salmon project 20/05/2019 KIPA: delay due to kinga's sick leave |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20Payment%20Files%20in%20xjfbs%20for%20invoices%20in%20PLN%201190,1810,1800.docx?d=waa17ba3082e24208ace806d4f559d6be&csf=1&e=cjgl4T
04/07/2018 | Olivier Pedroncini | Philippe D'autume | Eva Wennborg |  |  |  |  | QV | change in aged Ap report conected with the way how advance supplier invoices are shown | correctnes of the report - at the moment invoices posted with posting template ADV are wrongli shown | 4 | KL | 12 | 720 | YES |  | 11/2018 | IN PROGRESS |  | just QV |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20QV%20report%20account%20payable.docx?d=wd32ae6ff44c64acab3ebf23dcdd432bb&csf=1&e=NXvIkx
04/07/2018 | Olivier Pedroncini | [6 empty] | 1J | additional costs should be added to PO automatycaly in ICt flow and splited between Po rows diuring delivery insted of posting directly to P&L trought supplier invoice | legale deamnd of adding this kind of cost to stock value - today it is handled manualy | 4 | KL | 48 | 2880 | ON HOLD |  |  | ON HOLD |  | discussed Pre CAB meeting 04/07/2018 (Eva Wennborg, Jessica Steffen, Erwan Lardic, Olivier Pedroncini, Alicja Mamińska, Julia Homik, Kinga Lesniewska) : put on hlod Olivier should deliver more info - what will be gain from this development and what are the amounts which are added to stock value ( relevance of amounts) - mail sent 12/07/2018 27/08/2018 KIPA: new RFC deliverd by Olivier but without amounts - Kinga ask Olivier for more details - mail 27/08/2018; should be disscused togethre with point 39 05/11/2018 KIPA: this issue is disscused paraler as a part of drop shipment changes project and changes in base cost handling. |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20extra%20costs%20treatment.docx?d=w0c5ea58c5f274aec919c2b4cbfd7d60b&csf=1&e=1VYXcu
04/07/2018 | Aleksandra Cieloch/Olivier Pedroncini | [6 empty] | 1J | handling of bank account on supplier and supplier invoice level - only finance department should be able to add and change bank details | control and security | 4 | KL | 0 | 0 | NO |  |  | REJECTED |  |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-authorization%20regarding%20bank%20account%20on%20supplier.docx?d=w09f27e7f44f1445faccecee5211b94ad&csf=1&e=WAegUC
04/07/2018 | Kinga Lesniewska / Susann Radestrom / Olivier Pedroncini | [6 empty] | 1J | payment terms on customer and customer order level - change of the way how is handled today | all users should be able to use any of existing paymen terms on customer and customer order level | 4 | KL | 12 | 720 | YES |  |  | IMPLEMENTED | 7160 | 24/09/2018 KIPA: 7160 22/10/2018 KIPA: implemented on prod
04/07/2018 | Kinga Lesniewska / Susann Radestrom / Olivier Pedroncini | Kinga Leśniewska | Eva Wennborg |  |  | Headquarter |  | 1J | acces to credit limit and cerdit limit block fields on customer and customer order level | credit limit should be avaliabe to be set by sales support at the time of creting of customer but later only fiance users should be able to change credit limit on customer level and all fileds wich are conacted with credit limit blocks | 4 | KL | 4 | 240 | YES |  |  | IMPLEMENTED | 7160 7161 | 28/08/2018 KIPA: Kinga will send details of the solution agreed with Susann to Eva 10/09/2018 KIPA: proposal of the solution sent to Eva 20/09/2018 KIPA: proposal of the solution approved by mail by Eva after disscusion on a Group level. Changes will be process with use of security manager settings that is why estimation was changed from 24h to 4h 26/09/2018 KIPA: feature 7160, 7161 22/10/2018 KIPA: implemented on prod
31/07/2018 | Susann Rådeström/Lucia Villagi |  | Eva Wennborg |  |  | Headquarter |  | QV | disconnect company 1900 HL Display Österreich GmbH from QV report Cash Management, folder OPUS CAPITA: Account Receivable and AP accounts Payable? Pls. see previous email from Susann Rådeström 25/6 | Incorrect information uploaded in CFF and causes forecast risking being incorrect. Reporting to the management will be wrong information if the company isn’t able to correct their own information manually. As for the moment the company has informed “no capacity”. (Mrs Rådeström has an ongoing discussion with Mr Reiterer.) | 4 | JH | 4 | 240 | YES |  |  | IMPLEMENTED
08/08/2018 | Erwan Lardic | [7 empty] | Extra cost on POs. Check point nr 52 from Logisitcs Cab list |  | 5 | EL |  | 0 | duplicate |  |  | REJECTED |  | 27/08/2018 KIPA: copy of point 56 and 39; comunication with Pawel, Erwan and Olivier sent 27/08/2018
27/08/2018 | Kinga Lesniewska/ Jessica Steffen | Jessica Steffen | Eva Wennborg |  |  | Headquarter |  | 1J | replication rules for payment reminder text program - xfhkt | - correctnes of system settings and the flow - avoiding of mistakes | 4 | KL | 8 | 480 | YES |  | 30/09/2018 | IMPLEMENTED | 7119 | 7119 22/10/2018 KIPA: implemented on prod |  | RFC: https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20xfhkt%20settings.docx?d=w588ad75e881d4c908f410a498fea466d&csf=1&e=vSQEum spec: https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B2F985709-8E01-4190-9638-C63AD194CBCA%7D&file=Document50.docx&action=default&mobileredirect=true
31/08/2018 | Aleksandra Cieloch | Bożena Paszkowska | Eva Wennborg |  | 1800/1810/1190 |  |  | 1j | additional file in supplier invoice program for original invoice No | easier possiblity to search and match original invoice and credit. matching is required for VAt purposes and also makes easier hendling of payments | 3 | KL | 2 | 120 | YES |  | 16/11/2018 | IMPLEMENTED | 7168 | REMARK: insted of adding I wouldsugest use of existing filed Reference No. (ReferensNr) A general reference number used in several applications. For example, the field exists on customer and supplier invoices but has no logic connected to it; it can be used as desired. A reference number can also be defined as desired when converting external vouchers for the general ledger. 7168 22/10/2018 KIPA: feature in progress plan to be released 16/11/2018 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%201810,%201190,%201800%20Field%20Original%20Invoice%20Numer%20in%20supplinvcs.docx?d=w7dfdb1f5ae984f61be473d4344e4f003&csf=1&e=fIV964
11/09/2018 | KInga Lesniewska | Kamil Saczka | Eva Wennborg |  | HL Display AB - Finance | Headquarter | R19.1 Jan | 1J | change companies 1090,1160, 2310 from active to archive in 1J | time saving - no nessesty of checking basic data replicated from master; system performance - turning of replication will have positive inpact of system performance; this is more IT issue then finace but should be approved by fiance - hours will be allocated to IT maitenence | 4 | KL | 8 | 480 | YES |  | 12/2018 | IMPLEMENTED | 7169 | 7169 22/10/2018 KIPA: feature planed for sprint 172 - planed release 16/11/2018 17/12/2018 KIPA: correction in development needed - feature on BT
14/09/2018 | Kinga Lesniewska |  | Eva Wennborg |  |  | Headquarter |  | 1J/QV | Balance sheet report - move from xrb to QV | move all fin reports to QV - continuation of project started 2 years ago by Marcin Minkina flexiblity - QV gives possiblity to dril down to transaction level, easier export to excel ect | 3 | KL | 16 | 960 | YES |  | Q4/2019 | OPEN |  | Details: structure of the report is ready in XRB in Jeeves; date will be taken from GL and group according to accounts and CC 22/10/2018 KIPA: specification need to be done and consulted with super users - Kinga's task
14/09/2018 | Kinga Lesniewska |  | Eva Wennborg |  |  | Headquarter |  | 1J/QV | Income statement report - move from xrb to QV | move all fin reports to QV - continuation of project started 2 years ago by Marcin Minkina flexiblity - QV gives possiblity to dril down to transaction level,easier export to excel ect | 3 | KL | 16 | 960 | YES |  | Q4/2019 | OPEN |  | Details: structure of the report is ready in XRB in Jeeves; date will be taken from GL and group according to accounts and CC 22/10/2018 KIPA: specification need to be done and consulted with super users - Kinga's task
14/09/2018 | Kinga Lesniewska |  | Eva Wennborg |  |  | Headquarter |  | 1J/QV | Opex report - move from xrb to QV | move all fin reports to QV - continuation of project started 2 years ago by Marcin Minkina flexiblity - QV gives possiblity to dril down to transaction level, easier export to excel ect | 3 | KL | 8 | 480 | YES |  | Q4/2019 | OPEN |  | Details: structure of the report is ready in XRB in Jeeves; date will be taken from GL and group according to accounts and CC 22/10/2018 KIPA: specification need to be done and consulted with super users - Kinga's task
24/09/2018 | Michaela Franke | Olivier Pedroncini | Eva Wennborg |  | HL Display Deutschland GmbH |  |  | 1J | Change in reminder templat - GE (1600) | move addres to the left side - justification - fit to the envelopes | 3 | KL | 2 | 120 | YES |  | 16/11/2018 | IMPLEMENTED |  | 22/10/2018 KIPA: feature 7203 - planned to be delivered 07/11 |  | RFC link: https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20GE%20reminder%20templat.docx?d=w312b060a2c1b4097aea4eccdeaefb1c1&csf=1&e=3r0Ivs dev doc https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/Development%20Documentation/7203%20-%20Payment%20reminder%20template%20in%201600%20%E2%80%93%20change%20of%20the%20layout%20for%20GE.docx?d=w500ddbb6219f4027b73438edefac8290&csf=1&e=AnqNaS
24/09/2018 | Irina Cupina |  |  |  | HL Display Nordic |  | R19.1 Jan | 1J | Ar report for 1210 - adjustment in existing Jeeves report in FH + additional templates for 3 markets ( language and footer) | customer needs - at the moment info about customer account is created manualy. Reporta was avaliable in old 1210 Jeeves but was never moved to One Jeeves | 4 | KL | 16 | 960 | YES |  | 12/2018 | IMPLEMENTED | 7310 | 27/09/2018 KIPA: to be checked in only one language vertion will be enough - EN vertion 05/11/2018 KIPA question sent to Irina and Janicke - waiting for feedback 05/11/2018 KIPA: according to Jannicke all documents sent to customers in NO should be in local language - legal demand 21/12/2018 KIPA: due to fact that this report is required only be Nordic ( Norway) it was decided to move it from maitenence to Salmon project 19/02/2019 KIPA: implemnted on prod in January |  | RFC link: https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20AR%20report%20for%201210.docx?d=wf48978624d544fea86a85efefd47c0a6&csf=1&e=OEbuaH
24/09/2018 | Imee Santos |  | Eva Wennborg |  | HL Display Middle East FZCO |  | R19.2 Feb | Qv | VAT report | gather and present all data nessesry fo VAt reporting | 5 | KL | 12 | 720 | YES |  | 12/2018 | IMPLEMENTED | 7267 | 22/10/2018 KIPA: waiting for details from Imee 23/11/2018 KIPA: feature 7267 19/02/2019 KIPA: implemented 15/02/2019 |  | https://hldisplay.sharepoint.com/:b:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Approved/Finance/7267%20RFC%20VAT%20report%20for%203901%20.pdf?csf=1&e=a8ouib
2018-11-01 | Olivier Pedroncini | Lars Simonsson | Eva Wennborg |  |  | Headquarter | R19.10 Oct | 1J | Report of MO Differences | Indespensible and rationalizing. Manufacturing in HUB's currently have huge impact on the HUB pipe. This would improve the P&L accuracy. | 5 | AEL | 32 | 1920 | YES | 21/05/2019 | 12/2018 | IMPLEMENTED | 7543 | 1/11: Added to production and finance CAB /AEL 19/02/2019 KIPA: before report in QV will be creted existing report in Jeeves should be corected - def 2095 - internal tests 20/05/2019 KIPA: on a base of investigation done by Lars and Jessica heading to improvments in value added flow in HUB's it was decided thta QV report should be created. Specification sent by Jessica; RFC was in investigation phase 11/2018-05/2019. Final decision was taken CAB 21/05/2019 | 24/06/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B97652F5D-1B83-4414-9D7C-C4E4D968AC4E%7D&file=RFC%20-%20Report%20for%20MO%20difference%20justification%20-%20Olivier%20Pedroncini.docx&action=default&mobileredirect=true
05/11/2018 | Graham Wright/Jessica Steffen | Jessica Steffen | Kinga Leśniewska |  | HL Display (UK) Ltd |  | R5.14 Dec | 1J | Changes in XRB factoring report for UK | change in the way how final value of the report is cacluated. Without this change it is not possible to use the report to reconcile account One jeeves account 15999 hence it will not show the correct amount if an invoice is partial paid. | 5 | KL | 8 | 480 | YES |  | 12/2018 | IMPLEMENTED |  | 23/11/2018 KIPA: feature 7268 - it ws decided to move report to QV and make nessesry corection the same time |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20Change%20in%20Factoring%20XRB%20report.docx?d=w56d5326961584c3697b6d3a3dbd28162&csf=1&e=AM6NhG
05/11/2018 | Jessica Steffen/Anna Wellin |  |  |  | HL Display Sundsvall AB |  | R5.14 Dec | SDL | change in invoice ststistics - BC shoud be 0 for price adjustmet order type | adjusting to the logic implemented in other companies | 5 | KL | 12 | 720 | YES |  | 12/2018 | IMPLEMENTED | 7256 | 16/11/2018 KIPA: feature 7256 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20SDL%20invoice%20ststistics%20changes.docx?d=w2118b078f064462dbf03137170351d19&csf=1&e=Kxodap
09/11/2018 | Alicja Mamińska | Bożena Paszkowska | Benno Eliasson |  | 1800/1810/1190 |  | R19.1 Jan | 1J | design in LE and supplinvsc - VAT No and VAT EU No should be visible | easier way of controling data | 3 | KL | 2 | 120 | YES |  | 01/2019 | IMPLEMENTED | 7304 | 17/12/2018 KIPA: change for all PL companies 1800,1810,1190 19/12/2018 KIPA: feature added to sprint 176 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20VAT%20no.%20from%20FR%20to%20LE%20and%20supplinvcs.docx?d=wf9d6969b327c44258ade4531c11622c8&csf=1&e=wMUAXE | 18/12/2018
26/11/2018 | Olivier Pedroncini |  | Benno Eliasson |  | HL Display France SAS (+ SASU DESIGN) |  | R19.2 Feb | 1J | automatical update of daily exchange rates in 1J in XX from web for 1600 | time saving, data accuracy, improvments in the proces ( sales do not need to wait for updated rates) | 4 | KL | 16 | 960 | YES |  | 02/2019 | IMPLEMENTED | 7326 | 30/11/2018 KIPA: similar uploads are already done in other companies: 1810,1190,1210,1140 20/12/2018 KIPA: Kinga is still waiting for approval of cost from Olivier 04/01/2019 KIPA: cost approved, feature created 19/02/2019 KIPA: implemeted 15/02/2019 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Approved/Finance/7326%20RFC%20-%20Automatic%20update%20XX%20program.docx?d=wb4d6390833df4daba07f9135e38ae68c&csf=1&e=5nxR0D | 18/12/2018
08/11/2019 | Anne Bergstrome | Kinga Leśniewska |  |  | HFS |  |  | CJ | change of the paymen file format according to new rules | legal requirements - change of international standards | 5 | KIPA | 16 | 960 | yes |  | 12/2018 | IMPLEMENTED | 7233 | KIPA: feature 7233 created on base of Support incident: [#SRX19630] Incident INC000000788593. Change was plan to be delivered till the end of 2018 so ther is no cost allocation to unit. Delay in delivery was coused by problems in comunication beteen IT/HFS and bank
15/11/2018 | Kinga Lesniewska |  |  |  | HL Display AB - Finance |  | R19.2 Feb | QV | Upload of budget rates fro 2019 | standard maitenance conected with createing of new year in the system | 5 | KIPA | 2 | 120 | YES |  | 31/12/2018 | IMPLEMENTED | 7254 | 24/1 To be released in Ferbuary and to be moved to Finance 19/02/2019 KIPA: implemented on prod in release 15/02/2019
15/11/2018 | Kinga Lesniewska |  |  |  | HL Display AB - Finance |  |  | CDB | Upload of budget rates fro 2019 | standard maitenance conected with createing of new year in the system | 5 | KIPA | 2 | 120 | YES |  | 31/12/2018 | IMPLEMENTED | 7255 | 24/1 To be released in Ferbuary and to be moved to Finance 19/02/2019 KIPA: feature is staus BTP ready to be moved to prod in neares release. Delay in releasing coused by developer absence
30/01/2019 | Carita Saat | Jessica Steffen | Kinga Leśniewska |  | HL Display AB - Finance |  |  | 1J | activete night job for posting of journals in 1010 | time saving, security, standarisation | 4 | KIPA | 4 | 240 | YES | 19/02/2019 | 04/2019 | IMPLEMENTED | 6376 | 22/02/2019 Old feature for activation of this job was activated and added to sprint 181 (week 10/11) | 22/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/IT%20Change%20Request%20-%20Activate%20nightjob%20invoicejrnls%20co%201010.docx?d=wa98e607b99c9478b9f551a93b21b3cd8&csf=1&e=6jgfIW
05/02/2019 | Olivier Pedroncini |  |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | Additional mail recipients in functionality from feature 6267 - payment of advance invoice notification | time saving, less mail conversations | 3 | KIPA | 12 | 720 |  |  |  | REJECTED |  | 19/02/2019 decision was not taken due to additional questions from Benno. Jessica will take this with Benno again wen Olivier will sent more details he was asked for 25/02/2019 KIPA Olivier will disscus with sales what would be more efficient: additional mail receivers as requested in this RFC or functionality automatycaly unblocking order when advance invoice is paid. Till the decision will be taken request is put on hold. Jessica is informed 20/05/2019 KIPA: No final decision from Olivier; reminder sent by Kinga to Olivier 20/05/2019 KIPA: rejected on a base of user decision - mial from Oliver dated 20/05/2019 | 22/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open%20and%20New/RFC%20-%20Add%20email%20address%20for%20advance%20payment%20information.docx?d=w2a49a430c8604938a31e7e8e9ddfc404&csf=1&e=xFjX04
05/02/2019 | Olivier Pedroncini | Kinga Leśniewska |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | e-approval implementaton in 1600 | time saving, standarisation | 5 | KIPA | 40 | 2400 | YES | 19/02/2019 |  | INVESTIGATION |  | 19/02/2019 KIPA: should be treated as a samll project and hendling separately - KInga will disscus this with Kamil how to handled this from formal point of view 22/02/2019 KIPA: disscusion with Kamil started. Kinga sent info to Olivier about the cost. Further moves will be taken when local units will accept cost 25/02/2019 KIPA: short meeting with Olivier. e-approval functionalities described, scaning solutions presented. Olivier will investigate cost of scaning solution and will come back with final decision 20/05/2019 KIPA: No final desicion from Olivier; Kinga sent reminder 20/05/2019 KIPA: input from Olivier: development will be process further but final green light will be given after finding supplier for scaning - Kinga is waiting for final approval from Olivier | 22/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open%20and%20New/RFC%20-%20eapproval%20implementation.docx?d=we791776c57c345e1a10ae823d7e472e0&csf=1&e=qO3hZN
05/02/2019 | Olivier Pedroncini | Kinga Leśniewska |  |  | HL Display Belgium N.V |  |  | 1J | e-approval implementaton in 1510 | time saving, standarisation | 4 | KIPA | 24 | 1440 | YES | 19/02/2019 |  | INVESTIGATION |  | 19/02/2019 KIPA: should be treated as a samll project and hendling separately - KInga will disscus this with Kamil how to handled this from formal point of view 22/02/2019 KIPA: disscusion with Kamil started. Kinga sent info to Olivier about the cost. Further moves will be taken when local units will accept cost 25/02/2019 KIPA: short meeting with Olivier. e-approval functionalities described, scaning solutions presented. Olivier will investigate cost of scaning solution and will come back with final decision 20/05/2019 KIPA: No final desicion from Olivier; Kinga sent reminder 20/05/2019 KIPA: input from Olivier: development will be process further but final green light will be given after finding supplier for scaning - Kinga is waiting for final approval from Olivier | 22/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open%20and%20New/RFC%20-%20eapproval%20implementation.docx?d=we791776c57c345e1a10ae823d7e472e0&csf=1&e=qO3hZN
05/02/2019 | Olivier Pedroncini | Kinga Leśniewska |  |  | HL Display Nederland BV |  |  | 1J | e-approval implementaton in 1530 | time saving, standarisation | 4 | KIPA | 24 | 1440 | YES | 19/02/2019 |  | INVESTIGATION |  | 19/02/2019 KIPA: should be treated as a samll project and hendling separately - KInga will disscus this with Kamil how to handled this from formal point of view 22/02/2019 KIPA: disscusion with Kamil started. Kinga sent info to Olivier about the cost. Further moves will be taken when local units will accept cost 25/02/2019 KIPA: short meeting with Olivier. e-approval functionalities described, scaning solutions presented. Olivier will investigate cost of scaning solution and will come back with final decision 20/05/2019 KIPA: No final desicion from Olivier; Kinga sent reminder 20/05/2019 KIPA: input from Olivier: development will be process further but final green light will be given after finding supplier for scaning - Kinga is waiting for final approval from Olivier | 22/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open%20and%20New/RFC%20-%20eapproval%20implementation.docx?d=we791776c57c345e1a10ae823d7e472e0&csf=1&e=qO3hZN
05/02/2019 | Olivier Pedroncini |  |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | QV | report showing historical values of BC from factories on a base of log of changes in Jeeves. Development should be slited between 2 parts: - log of changes on BC fields in 1j (8h) - log of changes on BC fields in current jeeves 1140 and 1180 (16H) - QV report taking data from creted log of changes (16h) | possiblity to follow BC changes | 4 | KIPA | 40 | 2400 |  | 19/02/2019 |  | REJECTED |  | 19/02/2019 KIPA: there is open feature for BC follow up report in QV. Lars S is testing it and it should be avaliable soon. This report will show BC history and compare it with acculat values and sales. 22/02/2019 KIPA feedback sent to Olivier 20/05/2019 KIPA: Olivier was asked to disscus this issue with Lars S and chack if another report which was in test phase could not be used insted of requested one - Kinga ask Olivier for feedback if any acctions were taken 20/05/2019 KIPA: rejected on Olivier's request | 22/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open%20and%20New/RFC%20-%20store%20historical%20value%20for%20base%20cost%20unit%20and%20base%20cost%20start.docx?d=wf3b869b05cbe41b18d96ffb2bed44421&csf=1&e=S6V0zf
05/02/2019 | Karin Wennerstål | Jessica Steffen | Benno Eliasson |  | HL Display AB - Finance |  | R19.4 Apr | QV | Recaclulation to SEk according to budget rate in reports: - AP Ledger - AR ledger | reduction of manula recaclulation in proces of creating cash flow reports on a Group level | 4 | KIPA | 8 | 480 | YES | 19/02/2019 | 04/2019 | IMPLEMENTED | 7400 | 26/02/2019 KIPA: during cretion of specification to the feature some questions apeare. Questions sent to Jessica and Karin. Witing for final confirmation befor developemnt will be started | 26/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open%20and%20New/RFC%20-%20Add%20SEK%20values%20in%20QV%20Treasury%20reports.docx?d=w469071c221904eb6a5d3e92995ec60fa&csf=1&e=6xSr8g
05/02/2019 | Jessica Steffen | Lars Simonsson | Benno Eliasson |  | HL Display AB - Finance |  | R20.02 Feb | 1J | Automatic solution for transfer factor update in 1J - new program in master when TF will be updated by Gropu and sent to local comapnies (with log of changes). On a base of this sloultion TF in sy, Q_hl_sup_tf and on alt suppliers in local comanies should be updated | transparency of data and possiblity of following historical data. Elimination of discrepencies conected with the fact that different companies re changing TF in different dates what is cousing inconsistence of data | 5 | KIPA | 44 | 2640 | YES | 19/02/2019 | 05/2019 | IMPLEMENTED | 7712, 7739,7740 | 26/02/2019 KIPA: specification will be created when Kinga will be abck from sick leave. Confirmed and agreed with Jessica 16/09/2019 KIPA final scope and solution details are disscused with Jessica. Estimation changed from 40 to 44 due to additional point concerning TF handling on customer level (HUB2HUB) | 26/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open%20and%20New/RFC%20-%20Auto%20update%20of%20transfer%20factor.docx?d=wf2c75dff351b49bdb9da6d41e5d4a215&csf=1&e=sEXpGY
05/02/2019 | Jessica Steffen | Lars Simonsson | Kinga Leśniewska |  | HL Display AB - Finance |  | R19.3 Mar | 1J | additional fileds on list view in vfaktst program (invoice statistics) in 1J | possiblity to analise sales data more efficiently without need of retriving data by querry or asking It for help | 5 | KIPA | 4 | 240 | YES | 19/02/2019 | 04/2019 | IMPLEMENTED | 7398 | 25/02/2019 KIPA: feature added to sprint 181 (week 10-11) | 25/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open%20and%20New/RFC%20-%20Add%20fields%20to%20list%20vfaktst.docx?d=w1e658786b3084ecba12834c7216a8cc3&csf=1&e=Az2hrS
05/02/2019 | Olivier Pedroncini |  |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | 1J | possiblity to exclud certain invoice (mostly advance invoice) from reminder - checkbox in FH. | At the moment there is standard possibility to exclude invoice from reminder on reminder level. It need to be done reminder by reminder, and invoice by invoice. With new solution invoice with checkbox marked would be excluded from reminder once for all. Time saving and better control over invoices on reminders | 5 | KIPA | 14 | 840 | YES | 26/04/2019 | 05/2019 | IMPLEMENTED | 7487, 7488 | 19/02/2019 KIPA: check first how filed "reminder code" is working 25/02/2019 KIPA: field tested. It seems to work as desired. Befor final development user should confirm this. Request sent by Kinga to Support to make filed avaliable for users in test enviroment. Olivier will make testing when filed will be avaliable in tab visible for users in test enviroment. Further actions will be taken on a base of test results 26/04/2019 KIPA:"reminder code" chekbox is working as desired - field need to be moed from all fields to tabe avaliable for users - feature 7487. Next additional logic will be creted to give user possiblity to unmark this checkbox by defoult for certain type of invoices 20/05/2019 KIPA: features will be part of CFT testing week 21 30/05/2019 KIPA: relesed 24/05/2019 | 26/04/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open%20and%20New/RFC%20-%20%20reminder%20and%20advance%20invoice.docx?d=web0e4ee9c1a84498967ee5b65be316e9&csf=1&e=L80djb
18/02/2019 | Aleksandra Cieloch | Bożena Paszkowska |  |  | HL Display Gliwice Sp z.o.o |  |  | 1J | e-approvel implementation | time saving, standarisation | 5 | KIPA | 30 | 1800 | YES | 19/02/2019 | 11/2019 | IN PROGRESS | 7639 | "implementation of e-approval in PL units was recomended and approved by Susann Raderstrom and Eva Wenborg. It suppos to be done during Gliwice improvment proces project - it was postponed due to lack of recourcec - BC was on maternity leave, finace team in GLI was changed 19/02/2019 KIPA: should be treated as a samll project and hendling separately - KInga will disscus this with Kamil how to handled this from formal point of view 22/02/2019 KIPA info abot decision and cost was sent to Ola Cieloch. Further moves will be taken when cost will be approved by local unit" | 22/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/20.%20Approved/Finance/1190,%201810%20e-approval%20RFC%20-%20Template.docx?d=w46c102bbe874467e8184fba18cbfa5fe&csf=1&e=FSuAIj
18/02/2019 | Aleksandra Cieloch | Bożena Paszkowska |  |  | HL Display Distribution Center Europe sp zoo |  |  | 1J | e-approvel implementation | time saving, standarisation | 5 | KIPA | 30 | 1800 | YES | 19/02/2019 | 12/2019 | SPECIFIED | 7652 | implementation of e-approval in PL units was recomended and approved by Susann Raderstrom and Eva Wenborg. It suppos to be done during Gliwice improvment proces project - it was postponed due to lack of recourcec - BC was on maternity leave, finace team in GLI was changed 19/02/2019 KIPA: should be treated as a samll project and hendling separately - KInga will disscus this with Kamil how to handled this from formal point of view 22/02/2019 KIPA info abot decision and cost was sent to Ola Cieloch. Further moves will be taken when cost will be approved by local unit | 22/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/20.%20Approved/Finance/1190,%201810%20e-approval%20RFC%20-%20Template.docx?d=w46c102bbe874467e8184fba18cbfa5fe&csf=1&e=FSuAIj
18/02/2019 | Aleksandra Cieloch | Bożena Paszkowska |  |  | HL Display Polska SP.zo.o |  |  | 1J | e-approvel implementation | time saving, standarisation | 5 | KIPA | 20 | 1200 | YES | 19/02/2019 |  | ON HOLD |  | implementation of e-approval in PL units was recomended and approved by Susann Raderstrom and Eva Wenborg. It suppos to be done during Gliwice improvment proces project - it was postponed due to lack of recourcec - BC was on maternity leave, finace team in GLI was changed 19/02/2019 KIPA: should be treated as a samll project and hendling separately - KInga will disscus this with Kamil how to handled this from formal point of view 22/02/2019 KIPA info abot decision and cost was sent to Ola Cieloch. Further moves will be taken when cost will be approved by local unit 09/09/2019 KIPa: request stoped due to lack of cost approvemnt form Rafal Lewandowski. Bozena will continue disscusion with Rafal | 22/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/20.%20Approved/Finance/1800_%20e-approval%20RFC%20-%20Template.docx?d=w2ea4411bb1e14b24b0d5726ec412953f&csf=1&e=WBVdjh
23/04/2019 | Jessica Steffen | Lars Simonsson | Benno Eliasson |  | HL Display AB - Finance |  |  | 1J | Base Cost adjustemts in trading policy handling |  | 5 | KIPA | 16 | 960 | YES | 24/04/2019 | 05/2019 | IMPLEMENTED | 7486 | 26/04/2019 KIPA: due to fact that request was very urgent additional CAb disscusion was taken. Jessca S disscused request, cost ect with Benno E and lars S.. RFC was approved. Cost will be taken bo HL AB 20/05/2019 KIPA: feature will be part of CFT this week 30/05/2019 KIPA: feture 7486 implemented on prod 24/05/2019, second part concerning changes in QV is process on a base of feature 7520 - planned release date 06/2019 | 26/04/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/20.%20Approved/Finance/7486%20RFC%20-%20Basecost%20adj%20for%20trading%20policy%20items%20ver2.docx?d=w732d26b96e974038bbd831b20c40cc59&csf=1&e=KJwGhy
23/04/2019 | Irina Cupina | Margareta Karlsson | Kinga Leśniewska |  | HL Display Nordic |  | R19.6 Jun | 1J | VAT field modification in viewupdrows - change to show VAT from payer not from Customer | time saving, correctnes of VAT handling process | 4 | KIPA | 8 | 480 | YES | 21/05/2019 | 06/2019 | IMPLEMENTED | 7517 |  | 28/05/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/RFC%20-VAT%20field%20in%20viewupdrows.docx?d=w511027a285c14fef88ae3ed9346b986d&csf=1&e=5a5691
16/05/2019 | Carita Saat | Jessica Steffen |  |  | HL Display AB - Finance |  | R19.6 Jun | 1J | add field "display on WEB" in PRJ program (project) | this is essential for correct handling of e-approval process by users on WEB. At the moment users are not able to see and chosse project during approveing invoices on WEB | 4 | KIPA | 4 | 240 | YES | 21/05/2019 | 06/2019 | IMPLEMENTED | 7516 |  | 27/05/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/RFC%20-%20Add%20new%20field%20in%20prj.docx?d=wd7e910632b8d4ac0b91dd9734bcee7e8&csf=1&e=W0iErQ
2019-03-12 | Kinga Szyguła | Julia Homik |  |  | HL Display AB - Finance |  |  | 1J | Add field in XTI program (page HL Entry) showing current quantity from valid calculation. | Avoiding of MO diffrences, better control on MO | 4 | KIPA | 8 | 480 | YES | 21/05/2019 |  | MOVED / DUPLICATED |  | 20/05/2019 KIPA: this RFC concerns production area but should be disscused on CAB finace due to global investigation done by Lars S and Jessica heading to improvments in VAle added flow in HUB's 28/05/2019 KIPA: moved to PROD CAB - line 146 - Christer was informed | 28/05/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/RFC%20-%20calculation%20qty%20in%20xti.docx?d=w9f1b31d036034e9e970b5ce712c5896f&csf=1&e=QohfiV
2019-05-27 | Jessica Steffen | Lars Simonsson | Kinga Leśniewska |  | HL Display AB - Finance |  | R19.6 Jun | QV | Base Cost adjustemts in trading policy handling in QV | To be able to follow logic from feature 7486 from Jeeeves in QV | 5 | KIPA | 8 | 480 | YES | 28/05/2019 | 06/2019 | IMPLEMENTED | 7520 | 28/05/2019 KIPA: this development is conciderd as a second part of development requested and developed on a base of fature 7486. | 28/05/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B732D26B9-6E97-4038-BBD8-31B20C40CC59%7D&file=7486%20RFC%20-%20Basecost%20adj%20for%20trading%20policy%20items%20ver2.docx&action=default&mobileredirect=true
2019-06-13 | Kinga Lesniewska | Margareta Karlsson | Lennart Johansson |  | HL Display Nordic |  | R19.8 Aug | 1J | INTRUM - activation of the conection with Intrum allowing to sent info for reminders ect | to be able to proces reminders | 4 | KIPA | 4 | 240 | yes | 13/06/2019 | 07/2019 | IMPLEMENTED | 7163 | 13/06/2019 KIPA: feature was moved from Salmon project to maitenence. Feature was not finished within the project due to p
2019-06-13 | Graham Wright | Howard Williams | Kinga Leśniewska |  | HL Display (UK) Ltd |  | R19.8 Aug | 1J | Factoring checxbox in orderf | to make easier process of invoicing of factroring customers. To save time (1h week and avoid reprinting wrongly issued invoices) | 4 | KIPA | 2 | 120 | yes | 18/06/2019 | 07/2019 | IMPLEMENTED | 7562 |  | 24/06/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/RFC%20-%20factoring%20checkbox%20in%20orderf.docx?d=wf56058a001c64e47bae5083a52656b4f&csf=1&e=z8uK6E
2019-06-17 | Jessica Steffen | Lars Simonsson | Benno Eliasson |  | HL Display AB - Finance |  | R19.11 Nov | QV | Calulation details - report in QV | Avoiding of MO diffrences, better control on MO | 5 | KIPA | 16 | 960 | yes | 18/06/2019 | 07/2019 | IMPLEMENTED | 7560 | 24/06/2019 KIPA: approved by Benno Eliasson and lars Simmonson in the urgent CAB proces (separate handling of the issues conected with VA flow improvments) | 24/06/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BE02EAECD-DA37-440C-8FDD-9D1F676A2195%7D&file=7560%20RFC%20-%20Calulation%20report.docx&action=default&mobileredirect=true
2019-07-05 | Norman Tong | Jessica Steffen | Kinga Leśniewska |  |  |  | R19.10 Oct | CJ | Change in f11 RPT print report for Korea, Hong Konga, Thailand | report is not showing corect data if item was not scraped | 5 | KIPA | 12 | 720 | yes |  |  | IMPLEMENTED | 7574 | 07/07/2019 KIPA: approved by Bennoa Eliasson on a meeting with jessica Steffen (urgent CAB procedure due to holidays period). Cost should be splited between 3 Asian units: Korea, Hong Kong and Thailand equaly | 05/07/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/20.%20Approved/Finance/7574%20RFC%20-%20F11%20in%20RPT%20Print%20changes.docx?d=w4ed595564cd2434988d6537553468090&csf=1&e=G9hDJX
2019-07-05 | Jessica Steffen | Lars Simonsson | Benno Eliasson |  | HL Display AB - Finance |  | R19.11 Nov | 1J | Change of tha way how TF is handled on Value added items in HUB's | process improvments | 5 | KIPA | 36 | 2160 | yes | 05/07/2019 | 09/2019 | IMPLEMENTED | 7575.7576 | 05/07/2019 KIPA: approved on "urgent CABproces" as a part of value added flow improvments | 05/07/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B7F3BD9CE-515F-4A4D-8946-3814F63B1C07%7D&file=RFC%20Calculated%20Transfer%20factor%20in%20Jeeves%20VA%20pre-calculations%20190617%20ver%202.docx&action=default&mobileredirect=true&cid=dab9bf62-6264-431b-bf44-0f1227304bc7
2019-07-16 | Małgorzata Majewska | Bożena Paszkowska |  |  | HL Display Gliwice Sp z.o.o |  |  | 1J | In 1190 we would like to start using the order type price adjustment for issuing corrective invoices in situations when amendment invoice is not possible to issue or credit order is not necessary or possible due to any system limitations. Currently we use only amendment invoice or credit order type for corrective invoices . For both price adjustments and credit orders we would like to have the same series of numbering beginning with number 3 as it is in company 1810. Now in Jeeves for company 1190 price adjustment order type have the numbering beginning with the number 1. So please change the numbering for Price adjustment orders. | Price adjustment and Credit orders. Distinguishing the numbering of corrections which are not amendment invoices nor normal invoices. | 5 | MP |  | 0 | yes (to be discussed further after info from Jeeves) | 16/07/2019 |  | IMPLEMENTED | - - - | Marcin: No developement is needed. Point added to keep history of changes 26/08/2019 KIPA: changes implemented on prod without need of development - just change of settings. No additional cost to be invoiced | 26/08/2019 | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ec57a1Lk-FlEkwyNbP-WPMEBqKtzvrxQC8w5586kU-5tFQ?e=aVQvUv
2019-08-20 | Carita Saat | Jessica Steffen | Kinga Leśniewska |  | HL Display AB - Finance |  | R19.11 Nov | QV | Change log in supplier (le) - adjustments in existing report or move to QV. report suppose to show also suppliers newly added - not only changes on existing suppliers QV report solution choosen | auditors request | 5 | KIPA | 16 | 960 | yes | 17/09/2019 | 10/2019 | IMPLEMENTED | 7654 | 26/08/2019 KIPA: Kinga proposal was to move report from Jeeves to Qv - easier to change, develop, maitain. Waiting for estimation from Hania. Estimation for change of existing Crystal report in 1j: 12H 06/09/2019 KIPA: QV report wa estimated by Hania for 16H. USer decide to take this option - QV report | 25/09/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20change%20log%20on%20supplier%20-_.docx?d=w0c7d530693f147f09669046dcc8376f8&csf=1&e=EKPoJX
2019-08-20 | Jessica Steffen | Kinga Leśniewska | Benno Eliasson |  | HL Display AB - Finance |  | R19.10 Oct | 1J | design in MRVT, TIVT programs - add period field to tab and list view | It saves time for finance when searching for transaction within a specific period as today it is only possible to use Date/time field and search by intervalls | 4 | KIPA | 4 | 240 | yes | 17/09/2019 | 10/2019 | IMPLEMENTED | 7666 |  | 09/10/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20Add%20fields%20to%20program%20and%20lists.docx?d=w3134cb87526f47ecb7f08190bf4dbe6c&csf=1&e=Z0l5Iw
2019-08-22 | Mchaela Franke | Frank Liebrand | Kinga Leśniewska |  | HL Display Deutschland GmbH |  | R19.9 Sep | 1J | Changes on Edeka/Markant invoice list | new basic data: ILN, GLN | 5 | KIPA | 4 | 240 | yes | 29/08/2019 | 20/09/2019 | IMPLEMENTED | 7628 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20Edeka,%20Markant%20invoice%20list%20correction.docx?d=w8518998a92d0420893d7b7b18fb86805&csf=1&e=xhcBoq
26.06.2019 | Jessica Steffen | Kinga Leśniewska | Benno Eliasson |  | HL Display AB - Finance |  | R19.10 Oct | QV | This request is to add additional dimension ”Item origin” to tab "Custom report" | This makes it easier for some analysis such as calculation of MUP, Transfer factor when comparing Basecost to Cogs etc. | 4 | MP | 6 | 360 | yes | 17/09/2019 | 11/2019 | IMPLEMENTED | 7663 | 9.7.2019 It is not 100% connected with sales. Kasia will chceck if it is needed for her. If not, then we will move this request to finance CAB. 21.8.2019 - Marcin will send email to Jessica and Kinga (cc to Bożena Paszkowska) if this reqquest should be moved to finance Pre-CAB 23.8.2019 - Moved from sales Pre-CAB 17/09/2019 KIPA: approved on CAB 07/10/2019 KIPA: added to sprint 197 w.42-43 23/10/2019 KIPA: implemented 18/10/2019 | 07/10/2019 | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Eb0Gn-7rnY5Bj5TS4X_M0vUBHaQ6ZPoSBeUPaNrXURj_Ig?e=HIeSnw
10/09/2019 | Kinga Lesniewska/ Jessica Steffen | Kinga Leśniewska | Benno Eliasson |  | HL Display AB - Finance |  |  | CJ | Block BC fields on item level and add log of changes for BC fields on item and order level for Korea, Hong Kong and thailand | Data accuracy Combability with Group guidelines Possibility to follow changes Correct basic data Blocking possibility of user interference w system data Easier control over BC in Asia , | 5 | KIPA | 12 | 720 | yes | 17/09/2019 | 10/2019 | IMPLEMENTED | 7653 | 10/09/2019 KIPA: Torbjorn do not want to block fields - in his opinion education is needed. He approved log of cahnges but do not want to take this cost - to high for Asia. From IT and Group point of view those cahnegs are nessesry to be able keep control over BC values in Asia 25/09/2019 KIPA: on a base of disscusion with Support team oit was decided to split development on two separaet features: one for log of cahnges second for BC handling (block BC fields or stor BC on order level). Log of cahnges is estimated for 8h and will be done on a base of feature 7653 23/10/2019 KIPA: feature 7653 was implemented on prod 18/10/2019 - this is first part of the proces so RFC remain still in progress 25/11/2019 KIPA: log of changes helped in investigation what is cousing problems with BC in Korea. Due to that it was decided not to continue block of BC fileds. Decision might be changed in the future if new issues will apeare. |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20Block%20BC%20fileds%20in%20Asia.docx?d=w4eb59fb7a8c74dd3bb9404953a0f60ee&csf=1&e=L2gGMQ
16/09/2019 | KInga Lesniewska | Julia Homik | Benno Eliasson |  | HL Display AB - Finance |  | R19.11 Nov | 1J | Automatization of budge currency rate update on alt suppliers n one Jeeves | Data accuracy , autoatization of manual flow which need to be handled at the begining of the yeare in each local company separately | 4 | KIPA | 12 | 720 | yes | 17/09/2019 | 11/2019 | IMPLEMENTED | 7671
14/10/2019 | Kinga Lesniewska | Kamil Saczka | Benno Eliasson |  | HL Display AB - Finance |  | R19.12 Dec | 1J | Automatization of yearly base cost update in One Jeeves - investigation of the proces and proposed solution for automatization | Data accuracy , autoatization of manual flow which need to be handled at the begining of the yeare in each local company separately | 5 | KIPA | 8 | 480 | yes | 14/10/2019 | 12/2019 | IMPLEMENTED | 7682 | 14/10/2019 KIPA: approved in urgent CAB prosecc - mail from jessica Steffen 14/10/2019 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20price%20list%20update%20investigation.docx?d=wba256bfdae0d42699367d18db0e07e42&csf=1&e=9RSAc5
14/10/2019 | Vivian Li | Jessica Steffen | Torbjorn Magnusson |  | HL Display AB - IT |  |  | 1J | automatization of caclulation of due date for tax invoices in 2950 Customers in China pay invoices according to due date from tax invoice - not jeeves invoice. To be able to control AR all dat concerning tax invoices need to be set corectly. | Data accuracy, time saving | 4 | KIPA | 4 | 240 | yes | 09/10/2019 | 11/2019 | IMPLEMENTED | 5987, 6169 | 14/10/2019 KIPA: this is just finishing of development from Asia restructuring project
23/10/2019 | Anna Welin | Jessica Steffen | Kinga Leśniewska |  | HL Display Sundsvall AB |  | R20.02 Feb | CJ | change in product account setup in 1140 CJ | to ba able to differentati sales of HL prod and HL traded item on GL level and in QV | 4 | KIPA | 12 | 720 | yes | 19/11/2019 | 12/2019 | IMPLEMENTED | 7744 | 18/11/2019 KIPA: on a base of this RFC investigation of possible solution and estimation of the soultion should be done - thsi is RD+FC for investigation only |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%201140%20product%20account%20setup.docx?d=w0ab395794a9f409cb76f3ca9db3502aa&csf=1&e=Qc3KJh
23/10/2019 | Jessica Steffen | Kinga Leśniewska |  |  | Costs info in comment |  | R20.01 Jan | 1J | designa for e-approval and other fin design changes | To avoid having users assigning supplier invoice costs to account segments that should not be used. | 3 | KIPA | 6 | 360 | yes | 19/11/2019 | 01/2020 | IMPLEMENTED | 7743 | 05/11/2019 KIPA: add design in sysl, sycg: Cost should be splited between HL ab (5h) and 2950 (1h) |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20Add%20field%20Display%20on%20web%20in%20programs.docx?d=wdcd4604236c04bc98370a8a376da9ebd&csf=1&e=X1nUSv
23/10/2019 | Ida Moghid | Margareta Karlsson | Jenny Nobrand |  | HL Display Nordic |  | R19.11 Nov | 1J | querry to retrive data for Intarstat reporting for 1210 | Possibility to retrieve easily Intarstat data Possibility to correct previous reports Possibility to verify feature data and remove correctly RPT unit setup | 5 | KIPA | 8 | 480 | yes | 25/10/2019 | 11/2019 | IMPLEMENTED | 7692 | 25/10/2019 KIPA: approved in urgent CAb flow - mail from Jessica S 25/10/2019 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20Intrastat%20Querry%20for%201210.docx?d=wd2be1bad81464df491f7ea75c345d082&csf=1&e=4nirAE
04/11/2019 | Jessica Steffen | Kinga Leśniewska | Jenny Nobrand |  | HL Display AB - Finance |  |  | 1J | change of the logic for transfer factor postings in HUB2HUB flow in 1J | possiblity to differentiate TF for internal and external transactions in GL | 5 | KIPA |  | 0 |  |  |  | ON HOLD | 7544 | 04/11/2019 KIPA: feature moved from HUB2HUB pilot project due to closing of the project. Feature should be proces withing new HUB2HUB project but if new HUB2HUb will not be started will the end of 2019 disscusion need to be taken if changes should not be proces within maitenence. Till then fraure is on hold in CAB |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/Development%20Documentation/7544%20-%20HUB%202%20HUB%20-%20TF%20postings%20in%20GL.docx?d=weffce97bff4e49699d894d21dad71859&csf=1&e=psPMNr
05/11/2019 | Lars Simmonson | Jessica Steffen |  |  | HL Display AB - Finance |  |  | 1J | Change in TF caclulation in 1J for deliveries autside of 1J | consistence of data between seller and purchase | 5 | kipa | 20 | 1200 | yes | 12/02/2020 | 04/2020 | IN PROGRESS | 8104 | 06/11/2019 KIPA: approved in urgent CAB process. 04/02/2020 KIPA: development on hold till the moment when final decision about ICt with new SDL database will be taken. Question sent by Kinga to Kamil to confirm timeframe for ICt implementation in new SDL 04/02/2020 KIPA: there is no time frame for ICt implementation in SLD. Waiting for Benno's decision concerning this RFC. 12/02/2020 KIPA Benno approved this RFC on a base of the fact thta tere are no plans to change the way of comunication between 1140 and 1J. 05/03/2020 KIPA: issues conected with the way of caclulation of TF was discoverd |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20TF%20on%20deliveries%20from%20co%20outside%201J.docx?d=wf48a664e1a0c4191a0b8f96740eedf14&csf=1&e=ghGJl1
18/11/2019 | Alicja Maminska | Bożena Paszkowska | Kinga Leśniewska |  | 1800/1810/1190 |  |  | QV | Report showing log of changes of FR (company) in 1J | On FR level there are some data (VAT No) used later in the flow for tax caclulation (VAT) and paymen handling (split payment). Due to that strict control over change on those fields should be kept | 4 | KIPA | 4 | 240 | yes | 18/03/2020 |  | INVESTIGATION |  | 19/11/2019 KIPA: Kinga will asked other companies if they see a need of such retport. On that base further disscusion will be taken 25/11/2019 KIPA: question sent to all 1J controllers who would be interested in such report 05/03/2020 KIPA: due to lack of feedback from other units alternative solution was proposed: to use company log of cahnges tab in fr program - only design changes needed - Alicja feedback needed |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20log%20of%20changes%20FR.DOCX?d=w97a4c5dee31f4444b842a60fc8ce5395&csf=1&e=lu8vyv
18/11/2019 | Alicja Mamińska | Bożena Paszkowska | Kinga Leśniewska |  | 1800/1810/1190 |  |  | 1J | Changes in tax control file - VAT | legal requirement - tax authorities presented new requirements concerning VAT control files | 5 | KIPA | 50 | 3000 | yes | 26/02/2020 | 03/2020 | IMPLEMENTED | 7887 | 18/11/2019 KIPA: control files functionality was done by Jeeves as a part of customization for Polish market. IT will ask Jeeves to implement changes in those files Changes need to be impemented till 06/2019 Estimation will be given after consultance with Jeeves 19/11/2019 KIPA: Jeeves is goint to deliver solution but delivery date is not given yet. Another approval from CAB need to be given when final estimation of development will be known and will exceed 10h 09/01/2019 KIPA: Jeeves is going to develop necessary changes. Question sent to Product Manager when they plan to release those changes 20/02/2020 KIPA: details https://www.podatki.gov.pl/media/5833/broszura-informacyjna-jpk_vat-z-deklaracj%C4%85.pdf#jpk-vat 27/02/2020 KIP: 1190 need to have solution ready on prod till 01/04/2020. Jeves will not deliver solution till that time. It was decided to proces development with own resources |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20JPK%20VAT.DOCX?d=w198d18e588a649a080b529cedf17f067&csf=1&e=rLLkqh
18/11/2019 | Alicja Mamińska | Bożena Paszkowska | Kinga Leśniewska |  | 1800/1810/1190 |  |  | 1J | Changes in tax control file - sales invoices (FA) | legal requirement - tax authorities presented new requirements concerning sales control files | 5 | KIPA | 8 | 480 | yes | 25/03/2020 | 05/2020 | IMPLEMENTED | 7924.7967 | 18/11/2019 KIPA: control files functionality was done by Jeeves as a part of customization for Polish market. IT will ask Jeeves to implement changes in those files Changes need to be impemented till 06/2019 Estimation will be given after consultance with Jeeves 19/11/2019 KIPA: Jeeves is goint to deliver solution but delivery date is not given yet. Another approval from CAB need to be given when final estimation of development will be known and will exceed 10h 09/01/2019 KIPA: Jeeves is going to develop necessary changes. Question sent to Product Manager when they plan to release those changes 05/03/2020 KIPA: Jeeves confirm that solution should be delivered witin next two weeks 25/03/2020 KIPA: Jeeves deliverd package. First part conected with instalation will be proces o n a base of feature 7924 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20JPK%20FA.DOCX?d=wea54c4cbf1424ddb8850cf8e8a92fc5a&csf=1&e=TCyYsU
18/11/2019 | Stefan Adersten | Håkan Tjernberg |  |  | HL Display Nordic |  |  | QV | Stock provisioning report joining history from 1810 and 1210 | time saving, c orrect way of caclulation, the same way of caclulation for Group and local purposes | 4 | kipa | 12 | 720 | yes | 19/11/2019 | 01/2020 | REJECTED | 7898 | 12/12/2019 KIPA: to proces specification and developen list of the items sold from 1810 to 1210 need to be deliverd by 1210. 12/12 Kinga send another remindre to Stefan and Bartosz. 09/01/2020 KIPA: 1210 did not deliver list of items yet. reminder to bartosz and Stefan sent 05/03/2020 KIPA: list of the items was deliverd. It was confirm with user thta development is still required. feature created 21/09/2020 KIPA: users decided that report is not longer needed | 05/03/2020 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20stock%20provision%20HL%20rule%20for%201210.docx?d=w1ff487c89da847ba9a7e170820306de9&csf=1&e=fGCSuE
18/11/2019 | Alicja Mamińska | Bożena Paszkowska | Kinga Leśniewska |  | 1800/1810/1190 |  |  | 1J | split paymen functionality - possiblity to retrive in payment files nett, vat and VAT No | legal demand | 5 | KIPA | 8 | 480 | yes | 18/03/2020 | 05/2020 | IN PROGRESS | 7968 | 18/11/2019 KIPA: control files functionality was done by Jeeves as a part of customization for Polish market. IT will ask Jeeves to implement changes in those files Changes need to be impemented till 06/2019 Estimation will be given after consultance with Jeeves 19/11/2019 KIPA: Jeeves is goint to deliver solution but delivery date is not given yet. Another approval from CAB need to be given when final estimation of development will be known and will exceed 10h 09/01/2019 KIPA: Jeeves is going to develop necessary changes. Question sent to Product Manager when they plan to release those changes 05/03/2020 KIPA: Jeeves confirm that solution should be delivered witin next two weeks 25/03/2020 KIPA: Jeeves deliverd package. First part conected with instalation will be proces o n a base of feature 7924 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20split%20payment.docx?d=w3268fde3033b4a53b264a77dda72ef87&csf=1&e=y0oUmq
27/11/2019 | Jessica Steffen | Kinga Leśniewska |  |  | HL Display AB - Finance |  | R20.02 Feb | 1J | Stop transfer internal MUP from factories within 1J | Stop of a transfer of unnecessary data and possibility to track external MUP on a base of Av MUP field on item level (at the moment in this field internal and external MUP values are mixed) | 5 | KIPA | 20 | 1200 | yes | 13/12/2019 | 02/2020 | IMPLEMENTED | 7792 | 13/12/2019 KIPA approved in urgent CAb proces: mail Jessica, Jenny due to Pre CAb canceling - end year activities 14/01/2020 KIPA: RFC extended also to HUB2HUB flow - during creation of specification it accured thta internal MUP is also a subject in HUB2HUB flow 05/03/2020 KIPA: implemented 20/02. Info sent to users |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20Stop%20transfer%20of%20internal%20MUP%20from%20factory%20to%20HUB.docx?d=w3f3725a814284b9191d5129d0fc717a6&csf=1&e=xjb6z7
27/11/2019 | Dimitrios Wlachojorgos | Kinga Leśniewska | [5 empty] | QV | Extend information shown in QV reprt MO diff | Possiblity to define exact reason of MO differences and adjusting report for factory purposes | 5 | KIPA | 8 | 480 |  |  |  | OPEN |  | 14/01/2020 KIPA - no feedback from 1190 concerning approval of development cost |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC_-_MO_diff._report_update.docx?d=w2a91759415b14249b6a99e711e5509d7&csf=1&e=scqXUi
09/01/2020 | Tony Wang | Tina Zhu | Kinga Leśniewska |  | HL Display Suzhou Co. ltd |  | R20.07 July | CJ | changes in functionality connected with use of the budget currency rate. Budget rate should be used only on order level - on invoice level daily rate should be used. The same cahnge required like in 1140 and 1130 done on a base of features 4149 and 4946 | Budget rate should be used only on order level - on invoice level daily rate should be used. The same cahnge required like in 1140 and 1130 done on a base of features 4149 and 4946. ta the momnet budget rate is set manualy on each order in currency becouse ther is no possiblity to use budget rate functionality and issue invoices with daily rate. automatization will allow to avoid mistakes, save time and adjust way of working to other HL factories | 5 | KIPA | 8 | 480 | yes | 14/01/2020 | 03/2020 | IMPLEMENTED | 7839 | 14/01/2020 KIPA: approved in urgent CAB flow - mail from Jessica Steffen |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20budget%20currency%20rate%20handling%20in%201180%20.docx?d=we54bd409d4f24e5c8b670aafd21d4512&csf=1&e=LHcw6L
25/02/2020 | Patryk Baczek | [6 empty] | HL WEB | Add column in Investment Request |  |  | Marika |  | 0 |  |  |  | INVESTIGATION |  | 05/03/2020 KIPA: Kinga asked Patryk for details. Teams meeting will be sheduled by Patryk |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B31E8FC29-1069-416E-9408-C7D9CD231BFC%7D&file=RFC%20-%20Add%20column%20on%20Investment%20Request.docx&action=default&mobileredirect=true
05/03/2020 | Jessica Steffen | Lars Simonsson |  |  | HL Display AB - Finance |  | R20.0 Sep | QV | Changes in BC follow up tab in sales report: - additional view with 16 dimentions - item status as dimention - easy possiblity to filter only sellable items | To improve analysis of BC in calculations | 4 | KIPA | 8 | 480 | yes | 18/03/2020 | 06/2020 | IMPLEMENTED | 8007 | 05/03/2020 KIPA: cost approved by Lars Simmonson. 18/09/2020 KIPA: implemented |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20Adj%20to%20BC%20follow%20up%20QV%20report.docx?d=w4dfb1973eddc4aed8fea25f0d43e6167&csf=1&e=3pjP8O
06/03/2020 | Kinga Lesniewska | Jessica Steffen |  |  | HL Display AB - Finance |  |  | QV | Change of sales market logic in customer specification AARO report in QV - adjust logic to sales report REMOVE REPORT | consistency of data time saving standard report working corectly | 4 | KIPA | 4 | 240 | yes | 30/03/2020 | 06/2020 | INVESTIGATION |  | 08/04/2020 KIPA: it was decided to use sales report to retrive data instead of this report. It was also decided that report Customer spec AARO should be removed |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20customer%20spec%20AARO%20adjustments.docx?d=w7ac7e07922b44dd68821ba6c5ba2ea3e&csf=1&e=UuF3gp
06/04/2020 | Karin W | Kinga Leśniewska | CFO |  | HL Display AB - Treshury |  | R20.05 May | QV | export of files to new cash forecast system - change in the logic and automatization | change of cash forecast system | 5 | KIPA | 16 | 960 | yes | 03/04/2020 | 20/04/2020 | IMPLEMENTED | 7947
06/05/2020 | Graham Wright | Karin Wennerstal |  |  | HL Display AB - Treshury |  | R20.07 July | QV | cash management report - changes for 1710 - factoring invoices | correctness of data and time saving | 5 | KIPA | 12 | 720 | yes | 20/05/2020 | 19/06/2020 | IMPLEMENTED | 8003 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20cash%20managemant%20chnages%20for%201710.docx?d=w3966d3619e95412c83033c08e09bba98&csf=1&web=1&e=e5Vdtb
06/05/2020 | Graham Wright | Karin Wennerstal |  |  | HL Display AB - Treshury |  |  | QV | cash management report - changes for 1710 - include open orders to AR analises | correctness of data and time saving | 5 | KIPA | 16 | 960 | yes | 20/05/2020 | 19/06/2020 | IN PROGRESS | 8004 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20cash%20managemant%20chnages%20for%201710.docx?d=w3966d3619e95412c83033c08e09bba98&csf=1&web=1&e=e5Vdtb
07/05/2020 | Karin W | Kinga Leśniewska | CFO |  | HL Display AB - Treshury |  | R20.06 June | QV | changes in files sent to new cash forecast system | change of cash forecast system | 5 | KIPA | 6 | 360 | yes | 20/05/2020 | 05/06/2020 | IMPLEMENTED | 7987 | 10/06/2020 KIPA: implemented on prod week 23 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20cash%20management%20general%20changes.docx?d=w122c4e5ac5bb4d7c9f50903b0d1fa449&csf=1&web=1&e=QYBIwv
14/05/2020 | Vivian L/Karin W | Karin Wennerstal |  |  | HL Display AB - Treshury |  | R20.06 June | QV | cash management report - changes for 2950 | correctness of data and time saving | 5 | KIPA | 6 | 360 | yes | 20/05/2020 | 12/06/2020 | IMPLEMENTED | 8002 | 10/06/2020 KIPA: implemented on prod week 23 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20cash%20management%202950%20changes.docx?d=wb2d5fa5a1c7048239d02dcf3c9699039&csf=1&web=1&e=J98lMb
14/05/2020 | Kinga Lesniewska | Margareta Karlsson |  |  | HL Display Suomi Oy |  |  | 1J | archive company 3700 in 1J | system performance | 4 | KIPA | 4 | 240 | yes | 20/05/2020 | 31/07/2020 | SPECIFIED | 8006 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/20.%20Approved/Finance/8006%20-%20RFC%20-%20archive%203700%20docx.docx?d=wcb67cb966f3d41cabd964b123aee40e2&csf=1&web=1&e=qgQaM3
16/06/2020 | Kinga Lesniewska | Jessica Steffen |  |  | HL Display AB - Finance |  |  | 1J | design in xx1 - vat settings | VAT handling - basic data | 4 | KIPA | 4 | 240 | yes | 16/06/2020 |  | SPECIFIED | 8123 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20design%20in%20xx1.docx?d=w45da043278874d42b9dd715ef49ffda3&csf=1&web=1&e=eSLlrR
16/06/2020 | Alicja Mamińska | Bożena Paszkowska |  |  | Costs info in comment |  |  | 1J | changes in payment files - international payments + split payment handling | legal demands, time saving - more effitient way of payment files handling | 5 | KIPA | 16 | 960 | yes | 16/06/2020 |  | IN PROGRESS | 8028 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%201810,%201190,%201800%20Payment%20Files%20in%20xjfbs%20for%20invoices%20in%20PLN%20EUR%20and%20other%20curr.docx?d=w80727e84c4ae4bc288540106fe547794&csf=1&web=1&e=KsLLwX
16/06/2020 | Kinga Lesniewska |  |  |  | Costs info in comment |  |  | 1J | instalation of corection from jeeves - JPK FA 9 polish control files) | legal demand | 5 | KIPA | 4 | 240 | yes | 16/06/2020 |  | OPEN
10/09/2020 | Carin Hoglund | Anna Welin |  |  | HL Display Sundsvall AB |  |  | ERP2 SDL | querry used for stock provisioning - connect to ERP2 and Cj, exclude transaction conected with migration | possiblity to caclulate stock provision | 5 | KIPA | 8 | 480 | NO | 18/09/2020 |  | REJECTED | 8112 | KIPA 21/09/2020: RFC was rejected on CAB. it was decided thta 1140 should be aded to standard QV stock provision report.
18/09/2020 | Anna Welin |  | Jenny Nobrand |  | HL Display Sundsvall AB |  |  | QV | add 1140 to stock provisioning report in QV | possiblity to cacluate stock provision according to Group rules | 5 | KIPA | 24 | 1440 | yes | 18/09/2020 | 31/10/2020 | IN PROGRESS | 8116
24/09/2020 | Kinga Lesniewska |  |  |  | 1800/1810/1190 |  |  | 1J | instalation of Jeeves package - polish legal demands - electronic version of fin statement ( BS, P&L) | possiblity to generate from Jeeves PL fin statement and sent it in electronic form to tax office | 4 | KIPA | 8 | 480 |  |  |  | INVESTIGATION |  | 24/09/2020 KIPA: package is design for newer kernale than the one used by HL. Due to thta instalation require additional developer time. Info about package sent to users - further procesing depends on users decision |  | https://hldisplay.sharepoint.com/:f:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20PL%20fin%20stataement%20from%20Jeeves?csf=1&web=1&e=qrI1eS
24/09/2020 | Alicja Maminska | Bożena Paszkowska | Kinga Leśniewska |  | 1800/1810/1190 |  |  | 1J | additional filed to be able to handel split payment by file | legal demand - different understanding split payment by the bank and by tax office | 5 | KIPA | 6 | 360 | yes | 24/09/2020 | 31/10/2020 | IN PROGRESS | 8122 | 24/09/2020 KIPA: approved on a urgent CAB flow |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20additional%20filed%20for%20split%20payment.docx?d=w6cf533fb0f71465aa44fb7a8d61ce2da&csf=1&web=1&e=i3NFPu
07/10/2020 | Imee Santos | Andrej Isoski | Jenny Nobrand |  | HL Display Middle East FZCO |  |  | QV | change of the way how collective invoices are presented in VAt report in QV | correctnes of data | 5 | KIPA | 6 | 360 | yes | 07/10/2020 | 31/10/2020 | SPECIFIED | 8140 | 07/10/2020 KIPA: approved in urgent CAB process |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Finance/RFC%20-%20VAt%20register%20Dubaj%20QV%20changes.docx?d=w934997f451ec40688f44a762629c5d7b&csf=1&web=1&e=bgIlCx
08/10/2020 | Alicja mamińska | Bożena Paszkowska | Jenny Nobrand |  | 1800/1810/1190 |  |  | 1J | correction in JPK VAT | adjust taxfile to lataestlegal requirements | 5 | KIPA | 8 | 480 | yes | 12/10/2020 | 31/10/2020 | SPECIFIED | 8143 | 12/10/2020 KIPA: approved in urgent CAB process

## Marketing
Process Leader |  | Barbro Johansson
Business Coordinator |  | Marcin Pianka
Date | Requested By | Authorized By | Approved By | Business Consultant | HL Unit | HL Area | Release | Product | Description | Justification | Prio | Added By | Est Dev (hrs) | Est Cost (EUR) | Decision | Decision date | Est Deliv Date | Status | Feature ID | Comment | Cust notified | RFC Link
15-6-2018 | B. Johansson | B. Johansson | B. Johansson |  | HL Display AB - Marketing |  | R19.1 Jan | 1J | 2) We have issue with deleting products. Adjustments to be done to cover this process: -> When product is not connected to any items in Jeeves (user mistake), then it should delete also on Jeeves side | To ensure clear data and full synchronization between PIM and Jeeves | 4 | MP | 16 | 960 | YES |  | 01-2019 | IMPLEMENTED | 7141 | Feature 7141
06-04-2018 | B. Johansson | B. Johansson | B. Johansson |  | HL Display AB - Marketing |  | R19.1 Jan | 1J | Change the product no name in Jeeves: Product no = Product sys_id Product Number = ProductId | Headlines are not corresponding to the same headlines in PIM: Product no = Product sys_id in PIM Product Number = ProductId in PIM | 4 | JH | 4 | 240 | YES |  | 01-2019 | IMPLEMENTED | 7291
06-04-2018 | B. Johansson | B. Johansson | B. Johansson |  | HL Display AB - Marketing |  |  | 1J | Make visible the product structure on Item level and use it as selection hierarchy for assignig the product to item. | To make work with products easier for users | 4 | JH | 20 | 1200 | Investigation |  |  | REJECTED |  | 14-1-2019/ 11-2-2019/ 28-02-2019/ 25.4.2019 Waiting for details about marketing licence 23-5-2019 Rejected. But we could go back to this point if it will be needed
3-7-2018 | A. Czajczyńska | B. Johansson | B. Johansson |  | HL Display AB - Marketing |  |  | 1J | Tool is needed to analyze SQL Lite databases, which contain data from digital screens attached to our products | Currently such data are not avaibalbe for marketing department | 4 | MP | 0 | 0 |  |  |  | IMPLEMENTED |  | No Jeeves feature, new plugin for Excel to upload and analyze files outside system. Already covered ourtside Jeeves | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVXPIhQZunZLkNk05X5W6SUBtlgDo4mI_LDTGVjUntIkAg?e=kqs4rb
22-11-2018 | B. Johansson | B. Johansson | B. Johansson |  | HL Display AB - Marketing |  | R19.4 Apr | Article Search | Add Product Name to Article Search | To make work with products easier for users | 3 | KS | 16 | 1120 | YES | 28/02/2019 | 4/2019 | IMPLEMENTED | 7417 | Erwan or Kamil to ask Xlent for the cost of change and Marcin to check if we have space to add new column 5.3.2019 Mail sent to Xlent - what should we do on our side to cover this request 7.3.2019. OK with Xlent. Asked marketing about details
10-12-2018 | B. Johansson | B. Johansson | B. Johansson |  | HL Display AB - Marketing |  |  |  | Google Maps Licence Key | Google Api Key is needed for the new HL Web | 5 | KS | 1 | 60 | Investigation |  |  | REJECTED |  | 14-1-2019 To check if it is still needed 11-2-2019 rejected. Will back to this point if it will be needed.
20-12-2018 | J. Bonda |  |  |  | HL Display AB - Marketing | Headquarter | R19.2 Feb | 1J | Non valid and empty products should be removed. Items should be reassigned according to attached list | Increased correctness of item/product master data in OneJeeves, and of financial reports. The sales of items linked to non-existing products can’t be mapped properly to any ProductSystem in Aaro. | 4 | MP | 8 | 480 | YES |  | 15-02-2019 | IMPLEMENTED | 7332 | 14-1-2019 Approved, try to release in February (15-2-2019) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EV8V0e1rTqhNohGVE3QGwGMBi1Lui9mdIsJn564fYQcRMw?e=3rl6Gh https://hldisplay.sharepoint.com/:x:/s/itdocumentationrepository/EX4oo_tvuW1FjqmkAP2BuuwBaxAoyApRLrTyfDxQ_44hfg?e=yLZHy4
26/09/2018 | Kinga Leśniewska | [6 empty] | One Jeeves | Change replication rules on item class, Product account | Replication will keep correct/equal data between master and local companies. | 4 | PANO | 24 | 1440 |  |  |  | REJECTED |  | Investigation needed - ask Juliette Bonda To be moved to Pre-CAB Marketing
07/02/2019 | J. Bonda |  |  |  | HL Display AB - Marketing |  | R19.3 Mar | PIM | Rename two fields and and add 1 check box in PIM | The changes are needed to improve product visibility for reporting, decision making by Product Managers and shortening lead times for marketing activities. The Sustainable Choice checkbox is also needed for visualizing our Sustainable Choice products and items in the catalogue and on our website. | 4 | MP | 2 | 120 | YES | 11/02/2019 | 15-03-2019 | IMPLEMENTED | 7380 | 11-3-2019 Specification done |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EZSV9FsR36VBtP58-D_j3x0BdTht59eXd9IiZ-thneIn_Q?e=OY41By
14/1/2019 | J. Bonda |  |  |  | HL Display AB - Sales |  |  | 1J | A checkbox Sustainable Choice in all versions of Jeeves |  | 5 | MP | 20 | 1200 | YES |  |  | IMPLEMENTED | 7410 7421 7422 7423 | Point added here to not forget. Reminder sent (11.2.2019) to Kamil, Erwan and Christer to decide how we should proceed this quote big change 1J, Sundsvall and Suzhou + QV + CDB Erwan to ask Lenart about taking costs of changes. Developement will start automatically after cost approval. 4.3.2019. Erwan: sales will take it. Marcin: feature 7410 - QV part, but first Jeevves part should be created (Paweł Nowak) 15.03.2019 Status = investigation due to doubts from me and Paweł. Jeeves part released in April, QV will be released in May |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EaYMiN7gtyxFtJP21SrV-bUByGwvxubsBT9O7a0To9LpLQ?e=lQXdHN
25/4/2019 | Kamil Saczka | Tomas Osbjer |  |  | HL Display AB - IT |  |  | SHAREPOINT | Add HL Business Project List to HL Intranet | We need to publish a clear and transparent list of ongoing and planned projects to all employees. The list must be updated regulary. | 4 | KS | 0 | 0 | YES | 25/4/2019 |  | IMPLEMENTED |  | 25.4.2019 - J. Bonda will discuss with B. Johansson about place where it should be located (and how manage it) and back to all Pre-CAB participants 23-5-2019 Already in Prod (HL Net)
29.4.2019 | J. Bonda | Barbro Johansson | Barbro Johansson |  | HL Display AB - IT |  | R19.6 Jun | PIM | Inriver PIM contains a feature called Merchandize on Media, which should also be available in the version we have. This would allow us to link products and/or items directly to different areas in pictures. | We’d like to start testing this in the Test environment, to test how exactly this would be most useful for us. | 5 | MP | 14 | 840 | YES | 23/5/2019 |  | IMPLEMENTED | 7514 7528 | 23.5.2019 Kamil will check capacity needed to cover this request. 7514 - feature to analyze. 2hr 7528 - for test instalation |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcLL_0YPTjVOmelTWzE4sBwBCfkyql9kwLxlbeSosBp_-A?e=5xKCoF
05.06.2019 | P. Mattsson |  |  |  | HL Display AB - Partners |  | R20.01 Jan | SHAREPOINT | Partners need a downloadable pricelist in excel so that they can update their own ERP systems with actual pricing. There is currently a function to download price list, but this is only possible for selected items. Need is for the complete pricelist . It should be ready by the end of 2019. | This has now been made manually with risk of error and unnecessary manpower. | 5 | MP | 8 | 480 |  |  |  | IMPLEMENTED | 7699 7768 | Shouldn't this request be under Sales and Quotation? Nothing to do with Marketing. /Barbro 25/06/2019 - Marcin to discuss with Marika if we have it on her application list. To check the status. If it is only in old version, then probably we need to have additional request to move to the new Sharepoint. 26/06/2019 - Mail sent to Marika/Point added to IT CAB 22/08/2019 - Marcin will ask Kamil and Marika about status (there is no decission in IT Pre-CAB) - row 82 -------------------------------------------------------------- Decision: in 2020 functionality will be moved to the new web page. To cover price prices 2020 for partners: feature 7699. To be released during weekend 7/8.12.2019 | Kamil - please check if payment has been done properly. 7699 is assigned to release 19.12, 7768 to 20.01 | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EfXKhYSSoE9NlUt7QpOqm1EBOVeYCswG-2nreKw99e5Q7A?e=G1Ea8Q
25.06.2019 | A. Palm |  |  |  | HL Display AB - Marketing |  |  | HL WEB | Search on the Web for products do not show in general search result. The two searches (content & products) come from different search engines so we can't combine them into one search-result as it is now. DevCore can develop this and display the searchresults on the main search in two tabs showing the number of hits on each tab and allow the visitor to switch between them. |  | 4 | BJ | 10 | 600 | YES | 25/06/2019 |  | ON HOLD |  | 25/06/2019 Developement outside HL IT team - added here to have a history of changes 28/11/2019 Barbro will check the current status 19/12/2019 - Will be checked in January 23.01.2020 - It should be a part of next review of HL WEB
25.06.2019 | J. Bonda |  |  |  | HL Display AB - Marketing |  | R19.9 Sep | PIM | The Merchandize on Media feature has already been implemented in the Test version. This still needs to be moved to production. But when we do that, I’d like one small change: Add a new linking level for Spare Parts on Products: - Under Includes this will be called “Spare parts”. Set-up can be like we already have “Suitable Accessories”. - Under Included in: “Spare parts of” Set up like we already have with “Suitable for”. | Showing the functionality of our products and making them easier to understand. This will give our customers a better product-experience, but will also be helpful to explain our products internally to other departments. | 4 | MP | 4 | 240 | YES | 25/06/2019 |  | IMPLEMENTED | 7619 | 25/06/2019 Marcin will contact with Kamil regarding estimation and discuss with Daniel about possibilities. Developement is planned for August 2019, when Juliette will be back. 26/06/2019 marcin sent email to Daniel to take a look at the request. 02.07.2019 - Estimation received from Daniel. 4hrs 22.08.2019 - Green light for implementation. Marcin will cover it with a proper feature. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUyW6sjCzZRKgOmh2Qa-umIBzG_cvz1hos9fRMYGdGb-2w?e=SbMgKQ
03.07.2019 | J. Bonda | Barbro Johansson | Tomas Osbjer |  | HL Display AB - Marketing | Headquarter | R19.7 Jul | 1J | There are a lot of unused Sellable/ estimated items in Jeeves, that should be discontinued. Analysis from the items in Harlow and Gliwice factory show 29813 items | Discontinuing the unused items will reduce the risk of using items that have outdated pricing or set-up. It will also reduce the time spent searching for items, reporting, and updating of unneeded items. Also, this will be needed as first step towards integrating Jeeves and PIM on item-level. Changing the item status before the Budget rounds start will also reduce the complexity on item level, base cost updates etc. | 4 | MP | 12 | 720 | YES | 04/07/2019 | July/August | IMPLEMENTED | 7569 | Long disucssion with P. Nowak regarding the way and details of this operation. |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeBaVPAxv0BDvbH_468sbdwBGZPkBSklY9IuqBebfmg9ag?e=oU9hZQ
26.09.2019 | J. Bonda |  |  |  | HL Display AB - Marketing | Headquarter | R19.10 Oct | PIM | Adding the possibility of “Specifications” in PIM, which we can use for adding technical specifications to products that have a different structure than most, and require different details. | More relevant product information in PIM, which we now can’t add because the fields are adapted to the majority of the products. Also, centralizing product information in PIM, rather than in separate documents, allows us to use this information in the web catalogue, as well as the Online Sales portal. |  | MP | 10 | 600 | YES | 25/09/2019 |  | IMPLEMENTED | 7657 | 26/09/2019 Marcin will inform about costs (info from Daniel is required) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVBrbghk36RMiwG8AO65OXABIrPYkdqCQzqKmOKSkhr-jA?e=XdXaZO
31.10.2019 | J. Bonda |  |  |  | HL Display AB - Marketing | Headquarter | R19.2 Feb | 1J | Analyze of all fields within program item | Better process insight | 4 | MP | 20 | 1200 | YES | 28/11/2019 | Jan/Feb | IMPLEMENTED | 7779 | 06/11/2019 Only general description: field local/global, funtionality connected, integrations affected (we have more than 400 fields in item program) 28/11/2019 Juliette will send a updated version of RFC with a list of most important points to be checked. 04/12/2019 New RFCs. List updated 19/12/2019 RFC approved. 20 hours will be spend as a first part of the process. IT department will back with results of investigation and Markieting will take a decission abouth the next steps. | OLD RFC: https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXEgr0RPJVlNjzIu5kqd-dsB0bPBHl_qGQhXpXhz9GADiA?e=sOuJ4P | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EfpLKJp6-d9Ln-X7kfeinp0B-l9euW-DZeTpWQxdYKghlQ?e=1tpv76 https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EQA0sb6oMSpJhm__1srRyQoBmxUYmKC4uih756o74RrRrg?e=k7e1r0
2019.12.06 | K. Jobe |  |  |  |  | Headquarter |  | SHAREPOINT | Implementation of corporate calendar | [8 empty] | IMPLEMENTED |  | We need doc with RFC and more details. 27-04-2020 Sonia sent email do Karin and ask for more information
10.12.2019 | A. Palm |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | After completing the contact form the LinkedIn link is invisible as the text is white on blue and the URL is blue. | The complete text needs to be visible. | 4 | MP |  | 0 | YES |  |  | IMPLEMENTED | 7829 | 19/12/2019 Juliette will check with Barbro and Kamil who and how should maintain HL web site. 23.1.2020 Kamil sent mail with information about development process. We could continue with the request. Marcin will inform about delivery time and other details. 27.02.2020 Bartosz is responsible 21.04.2020 Feature is on Business Tests 22.04.2020 Feature is still in tests 27-04-2020 Feature is ready for deploy into prod |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ea878sB5Lx1EgoDuVjBgxQABBYRVw_Q4DWN1ZCMczHojYA?e=cC3Z5a
09.12.2019 | A. Palm |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | Spam emails reCAPTCHA - from "do not reply" address We receive 100s of emails daily from the HL website that is spam. Therefore, can you please provide suggestions on how we can fix this on our website? - So the spam bot doesn't fill out the form - So the spam person (or bot) doesn't copy and paste the email address There are some suggestions here that I like, such as the 'human verfication' option: https://www.industrialmarketer.com/how-to-handle-web-form-spam/ There’s also reCAPTCHA that is from Google. | Reduce the amount of spam email, will allow better filtering of real enquiries from legitimate customers / potential customers |  |  | 13 | 780 |  |  |  | IMPLEMENTED | 7830 | 27.02.2020 Daniel is responsible 23.03.2020 Completed.
28.11.2019 | A. Palm |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | Download csv file Please publish to the production server the latest change made by Devcore – they have implemented a download csv function into Episerver from the dashboard view. | This allows us to capture data from the website for lead generation. |  |  |  | 0 |  |  |  | IMPLEMENTED |  | 23.03.2020 Mariusz will check the status 26.03.2020 We have no info from Mariusz and will try to contact with him to get a proper status
28.11.2020 | A. Palm |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | Emails from any HL address are blocked / go to spam folder Ticket #INC-10919 Have contacted Hugo and Marika and this has not been resolved | We are losing customer enquiries and sales leads, therefore we are losing potential business |  |  |  | 0 |  |  |  | IMPLEMENTED |  | Service desk is responsible 23.03.2020 Sonia will check the status with GDM 26.03.2020 No info from Hugo (mails have been sent) 14.04.2020 Hugo confimed that it is resolved already
17.01.2020 | A. Palm |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | URL open in new window DevCore did some testing so the URL to HL Partner sites, e.g. www.grupo-om.com open in a new window. It looks like this change hasn’t been deployed and the link is not working properly (see screen shot below). Can you please prioritise getting this fixed, as the website is a very large source of business for our partners. FYI, all the HL Partner links are doing this. | HL Partners are losing business when being redirected from our website | [7 empty] | IMPLEMENTED |  | Marcin and Mariusz will check it with Devcore 27-04-2020 Issue is solved
17.01.2020 | A. Palm |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | Google Analytics tracking Devcore have been making preparations for tracking of our website through Google Analytics, but we are awaiting a response regarding deployment. Can you let us know where you’re at with this so we can go ahead and deploy? What page they visited when completing the contact form Self-explanatory, but this is so we can see what product page they were looking at and are perhaps interested in finding more information about. Completed contact form We are going to have the contact form on all product pages (as per above) and the contact pages. We need to measure the number of contact form completed in GA (note: we’ll also have a csv file available for download to import into our CRM system). - Downloaded paper (we have 2 x papers) Start / Our take on retail / Category insights / Bulk merchandising - Start / Our take on retail - Watched corporate video / Start - Watched Sustainable Choice video / Start / Our offer / Sustainable choice - Downloaded catalogue / Start / Our offer / Catalogue | Need to track for sales and marketing lead generation purposes | [7 empty] | IN PROGRESS |  | Marcin and Mariusz will check it with Daniel 22.04.2020 Some part is already deployed, but contact form is still in the development process. Daniel and Barbro are in contact. 28.05.2020 More tests are needed after Daniel's implementation with the new gadget
30.01.2020 | A.Palm |  |  |  | HL Display AB - Marketing | Headquarter | R20.02 Feb | HL WEB | Set up URL redirects in Episerver for 14 x countries | For recent web updates |  |  | 8 | 480 |  |  |  | IMPLEMENTED | 7827
26.02.2020 | B. Johansson |  | Barbro Johansson |  | HL Display AB - Marketing | Headquarter |  | SHAREPOINT | In the top menu under Sales & Marketing on HLNet, it's not possible to click on the small dots to extent the top menu. NotFoundError message appears. Several users have reported this and Malte at IT support Need support from DevCore. Reported with INC-14107 |  |  |  |  | 0 |  |  |  | IMPLEMENTED |  | marcin to ask for defect - mail sent 27.02.2020. 18.03.2020 - Info from Bartek - GDM is responsible for this action. 23.03.2020 Sonia will check the status with GDM 26.03.2020 Malte promised to get more details from Devcore regarding such point. 21.04.2020 Sonia had a meeting with Malte, they tried to recreate the issue, but it appears random. Sonia will contact Euvic and ask for the investigation 27-04-2020 DevCore Team answered that the issue should be resolved, users might still displaying the old version of the page. Malte will check with them 28.05.2020 Sonia wil lcheck Malte again
08.04.2020 | B.Johansson |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | Image Vault pictures are cut in the wrong way on the web. Especially visible on contact page. Even if the sizes of the pictures are the same they appear differently. Beg 2019 we got the message that this was due to a bug in Image Vault. Has this been solved now? | Improved design / appearance on the web | [7 empty] | INVESTIGATION |  | 22.04.2020 Sonia will contact Euvic to investigate the bug 27-04-2020 Email sent to Euvic 28.05.2020 Sonia will contact Daniel 30-06-2020 Sonia will check the issue with Bartek 29-09-2020 Euvic: issue from the backend, the picture of Stefan Sundin is 1333x2000 and it is scaled to 295x295 on the website, the best way to avoid it would be to have a picture in a scale 1:1
08.04.2020 | B.Johansson |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | Top menu functionality: When clicking on our offer, the page doesn't open, only the drop down menu. We would like the page to open instead. When hoovering over our offer in the top menu, then the drop down menu should be shown. | Improved visitor experience | [7 empty] | INVESTIGATION |  | 22.04.2020 Sonia will contact Euvic to investigate the bug 27-04-2020 Email sent to Euvic 28.05.2020 Sonia will contact Daniel 30-06-2020 Sonia will ask about the options of the dropdownlist
09.04.2020 | J. Bonda |  |  |  | HL Display AB - Marketing | Headquarter |  | 1J | New item attributes: item characteristics, change in design in Jeeves item program, changes in Jeeves templates - demo/configuration |  | 5 | sonkur | 8 |  | YES | 09/04/2020 |  | IMPLEMENTED | 7954
22.04.2020 | B. Johansson |  |  |  | HL Display AB - Marketing | Headquarter |  | 1J | Integration PIM and labels |  |  | sonkur | [5 empty] | INVESTIGATION |  | 22.04.2020 Sonia will inform Barbro and Juliette about the progress in the Printing Solution project 30-06-2020 Sonia will contact Christer
05.05.2020 | B. Johansson |  |  |  | Costs info in comment | Headquarter |  | HL WEB | Integration between Episerver and CRM | All communication from contact forms published on the HL web should be sent to the CRM system so sales persons can follow-up on the webactivities |  | sonkur | 24 | 4000 € |  |  |  | SPECIFIED |  | Offer received from Danil R at Euvic.. Additional offer received from Sirocco for 25hours for creating the integration with MS flow io CRM. 13-10-2020 Cost splitted into all Sales Areas
14.05.2020 | B. Johansson |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | New editing colors to be added to EpiServer | Improved visitor experience |  | BJ | 16 |  |  |  |  | SPECIFIED |  | Offer received from Danil R at Euvic
15.05.2020 | B. Johansson |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | Several users have reported access problems to our website. Different days, different error messages. It's both "This site cant be reached or it's this blue green sccreen with IIS7 message. Have also raised a ticket for quick resolvment #INC-17338 - but maybe we need to look into this recurrency issue we have. | Improved visitor experience. Important business system. |  | BJ | [5 empty] | INVESTIGATION |  | 28.05.2020 Sonia will contact Euvic about the issue 30-06-2020 Sonia will contact again both Euvic and GDM 29-09-2020 Ticket is in the 2rd line of GDM support, issue conected to the DNS problem
19.05.2020 | B. Johansson |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | We need new block or pagetype that can present inspiration pictures. One should be "moving" pictures with arrow: https://ww8.ikea.com/se/sv/ext/ikea-family/events/heminredarna/sa-fixar-du-en-bra-arbetsplats-hemma/1_dgq1a8cf/ so the visitor can click on - next picture. It would be great if we could add either videos or pictures like this. I assume Daniel from Euvic will work on this. I wil send him a request for estimate. | Improved visitor experience. Important business system. |  | BJ | [5 empty] | INVESTIGATION |  | 28.05.2020 We are in contact with Daniel 30-06-2020 Sonia will ask Daniel about the status of investigation 29-09-2020 Barbro contacted Daniel; one part of the Daniel's suggestion will be done
01.06.2020 | B.Johansson |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | Some products do not show item attributes on the webcatalogue. For example 788218. Are not all fields transfered to Epi? It's difficult for customers to understand the specifications of an item if this is not visible. |  |  | BJ | [5 empty] | INVESTIGATION |  | 30-06-2020 Sonia is in contact with Tomasz from Euvic 29-09-2020 Need adding new attributes, initial estimation from Euvic 20h
29.07.2020 |  |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | Lead generationa and Sharepoint CRM reflection |  |  | KS |  | 840 | Yes |  |  | IMPLEMENTED
10.08.2020 | B Johansson |  |  |  | HL Display AB - Marketing | Headquarter |  | HL WEB | Update of Contact form / Get in Touch: We would like to add one field that is not mandatory. Headline for this field is Region, city or postal code. Please give an estimate. Update 201006 - also add two check boxes with Retail and Brand headines so the customer can click only one of them. This information should also be sent with the request via API to Dynamics. | Faster tracking in CRM who is the contact person |  | BJ | 6 | 360 |  |  |  | INVESTIGATION |  | 08-09-2020 Sonia will reach out to Daniel for the estimation, high prio 29-09-2020 Estimation from Euvic 4-6h 201006 - specifiction updated with two check boxes.
21.09.2020 | Mathilde Murzeau |  |  |  | HL Display France SAS (+ SASU DESIGN) | West |  | HL WEB | Purpose is to develop some functionality in order the latest posts from Linkeding published by HL France are displayed on a connected screen in the reception of the office (with auto execution of video, animated picture without any manual action) |  | 5 | EL | 40 | 2400 |  |  |  | OPEN |  | 2020-09-25 if request will be approved please inform also Dawid Wybierek 29-09-2020 Sonia will schedule a meeting with Erwa and Dawid |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B988729EE-7320-485B-8B93-C0E1EA06E6EB%7D&file=Request%20for%20Change%20-%20Connected%20Screens%20Linkedin.docx&action=default&mobileredirect=true
15-10-2020 | Barbro Johansson |  |  |  | HL Display AB - Marketing | Headquarter |  | HL Web | cannot reach website menu from laptop reduced view but with mobile phone. Worth looking into |  | 3 | BJ
16-10-2020 | Emma Sporrenhjelm |  | Barbro Johansson |  | HL Display AB - Marketing | Headquarter |  | HL WEB | Bug on downloading report page. When choosing Kantar report it´s not possible to push download due to a bug with ID on the forms. |  |  | ES
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN
[14 empty] | 0 |  |  |  | OPEN

## Data
HL Unit | HL Area | Status | Requested By | Autorized By | Approved By | Release | Product | Decision
HL Display AB - Finance | Headquarter | OPEN |  | Małgorzata Stasierska | Emilia Hermiö | R5.14 Dec | 1J | Yes
HL Display AB - Marketing | North East | INVESTIGATION |  | Magda Oczko | Andreas Astgård | R19.1 Jan | CJ | No
HL Display AB - IT | UK/Aus | SPECIFIED |  | Lars Ämtenmyr | Kinga Leśniewska | R19.2 Feb | QV | On Hold
HL Display AB - HR | West | IN PROGRESS |  | Rafał Lewandowski | Kamil Saczka | R19.3 Mar | PIM
HL Display AB - Sales | Central | IMPLEMENTED |  | Johan Nordqvist | Tomas Osbjer | R19.4 Apr | EDI
HL Display AB - Production | Asia | ON HOLD |  | Olivier Pedroncini | Anna Carlsson | R19.5 May | ARIBA
HL Display AB - Partners | Factories | REJECTED |  | Barbro Johansson | Andreas Ekman Lindqvist | R19.6 Jun | EPI
HL Display Nordic |  | MOVED/DUPLICATED |  | Håkan Tjernberg | Lennart Johansson | R19.7 Jul | HL WEB
HL Display Suomi Oy |  | SENT TO PROJECT OFFICE |  | Margareta Karlsson | Barbro Johansson | R19.8 Aug | SHAREPOINT
HL Display Sverige AB |  |  |  | Barys Rasinski | Tomasz Sarniak | R19.9 Sep | INFRA
HL Display Norge A/S |  |  |  | Emilia Hermiö | Benno Eliasson | R19.10 Oct | TALENTSOFT
|  |  |  | Stephane Jacob | Jenny Nobrand | R19.11 Nov | LOCAL APP
HL Display OOO (Russia) |  |  |  | Julia Homik | Eva Wennborg | R19.12 Dec | WMS
HL Display (UK) Ltd |  |  |  | Lennart Johansson | Annika Haaker | R20.01 Jan | Inquiry Form
HL Display Australia Pty Ltd |  |  |  | Stefan Pechmann | Christer Sahlén | R20.02 Feb | DW
HL Display France SAS (+ SASU DESIGN) |  |  |  | Howard Williams | Torbjorn Magnusson | R20.03 Mar | CRM
HL Display Belgium N.V |  |  |  | Duncan Hill | CFO | R20.04 Apr | NICELABEL
HL Display Nederland BV |  |  |  | Stephane Carrivain |  | R20.05 May | E-Store (online sales)
HL Display Middle East FZCO |  |  |  | George Xu |  | R20.06 June | Sales Portal
HL Display Polska SP.zo.o |  |  |  | Kamil Saczka |  | R20.07 July | ERP2 SDL
HL Display Distribution Center Europe sp zoo |  |  |  | Bożena Paszkowska |  | R20.08 Aug
HL Display Österreich GmbH |  |  |  | Jessica Steffen |  | R20.0 Sep
HL Display Ceská republika s.r.o |  |  |  | Kinga Leśniewska |  | R20.10 Oct
HL Display Slovakia |  |  |  | Philippe D'autume |  | R20.11 Nov
HL Display Slovenija d.o.o |  |  |  | Reinhard Rollett
HL Display Schweiz |  |  |  | Lars Simonsson
HL Display Romania |  |  |  | Vojtech Motl
HL Display Deutschland GmbH |  |  |  | Rasmus Michelsson
1800/1810/1190 |  |  |  | Anders Lautmann
HL Display HongKong Ltd |  |  |  | Stephen Mepsted
HL Display Indonesia PT |  |  |  | Fredrik Ström
HL Display Korea Co Ltd |  |  |  | Marika Westrin
HL Display Shanghai Co Ltd |  |  |  | Håkan Tjernberg
HL Display Thailand Ltd |  |  |  | Annika Haaker
HL Display Suzhou Co. ltd |  |  |  | Joanna Rosół
HL Display Gliwice Sp z.o.o |  |  |  | Stephen Mepsted
HL Display Harlow Ltd |  |  |  | Peter Moser
HL Display Sundsvall AB |  |  |  | Graham Wright
HFS |  |  |  | Frank Liebrand
Suzhou Foreign Service Center |  |  |  | Markus Reiterer
Costs info in comment |  |  |  | Tina Zhu
HL Display AB - Treashury |  |  |  | Andreas Astgard
Karin Wennerstal
Anna Welin
Andrej Isoski

## IT
Process Leader |  | Tomas Osbjer
Business Coordinator |  | Kamil Saczka
Date | Requested By | Authorized By | Approved By | Business Consultant | HL Unit | HL Area | Release | Product | Description | Justification | Prio | Added By | Est Dev (hrs) | Est Cost (EUR) | Decision | Decision date | Est Deliv Date | Status | Feature ID | Comment | Cust notified | RFC Link
20/06/2018 | Julia H | [5 empty] | R19.3 Mar | 1J | Increase the number of signs for PersSing in Jeeves | We changed the login standard from 4 to 6 signs. We should extend preparation engineer according to the same number of signs as it is in AD (20) | 5 | JH | 12 | 720 | yes |  | 22/10/2018 | IMPLEMENTED | 7078 | Review old Jeeves (Sundsvall, Suzhou, Russia, Asia) 24/1 To be released in February
01/08/2018 | Pianka | [5 empty] | R19.1 Jan | 1J | Remove all functionality connected with Gmail, mark parameters as non active, remove "use outlook" | To clean up system. Possible place of incident/defects | 4 | MP | 32 | 1920 | yes |  | 30/12/2018 | IMPLEMENTED |  | 7094
06/08/2018 | Julia H | [6 empty] | 1J | CustomerDropDown Languages | There is a problem with inconsistent data. We have different desrcription in the database and on the reports. Not all languages are updated when the update of the field in Jeeves is performed. Only the user language is updated in CustomerDropDown. This caused problems in production as well – we produceed incorrect item becase the descritpion was wrong on the report. | 3 | PANO | 8 | 480 | yes |  | 2019-12-31 | ON HOLD | 7341 | 18/01 assigned to sprint 178 24/01 To be released 15th of February 28/03/2019 To be realed in May (24th of May) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EfWZXe1AZJJOv0he4LfwMeoBN0ZMwlr51AYu1X-kgHzZMg?e=MQCob1
13/08/2918 | Julia H | Julia Homik | Kamil Saczka |  | HL Display AB - IT |  | R19.5 May | 1J | Correct desing settings in Jeeves | 20 APPs with incorrect setting to be fixed - this is a root cause of couple of the incidents and new incidents after releases to ERP system. | 4 | JH | 32 | 1920 | yes | 10/10/2018 | 30/12/2018 | IMPLEMENTED | 7149, 7407 | 24/01 To be released in March (I part) 28/3 Second part to be release in April 24/4 Moved to May (kernel upgrade issues)
31-8-2018 | T. Waterlund | [7 empty] | E-Shop (bestellijst.hl-display.com) is running on an old Windows Server (version 2003, sdl-web-101) that is not supported and exposed on internet. If this web application is still needed to be published on internet it should be moved to a more modern version of Windows Server that is supported and gets security updates. | Risk of external attacks would be lowered if this web application either is removed from internet or moved to a more modern platform. If nothing is done we risk another infection like the one we had in August 2018. | 5 | MP |  | 0 | yes |  |  | IMPLEMENTED |  |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EUrZi0nl-INLqNsoPDC8MN4BxWP7qaUb9nO5pMSWnU67WA?e=SAM6IW
31-8-2018 | T. Wetterlund | [7 empty] | Transportnet is running on an old Windows Server (version 2003, sdl-web-101) that is not supported and exposed on internet. If this web application is still needed to be published on internet it should be moved to a more modern version of Windows Server that is supported and gets security updates. Parts of this application is also dependent on an even older server (sdl-crp-101, running Windows Server 2000). | Risk of external attacks would be lowered if this web application either is removed from internet or moved to a more modern platform. If nothing is done we risk another infection like the one we had in August 2018. | 5 | JH |  | 0 | yes |  |  | IMPLEMENTED
26/09/2018 | Kinga Leśniewska | [6 empty] | One Jeeves | Change replication rules on item class, Product account | Replication will keep correct/equal data between master and local companies. | 4 | PANO | 24 | 1440 |  |  |  | REJECTED |  | Investigation needed - ask Juliette Bonda To be moved to Pre-CAB Marketing
05/11/2018 | Erwan Lardic | [5 empty] | R19.1 Jan | One Jeeves | Refactoring of Crystal Report connected to Proforma invoice and Consolidated invoice for Norway | This report is either - crashing - taking very long time to be executed (up to 10 minutes) justifying the refactoring need | 5 | ERLA | 16 | 960 | yes |  | 14/12/2018 | IMPLEMENTED | 7226 | F7226 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EVgN1qrCSKFKuQncW7r1V5QBy0uPdN01XlVJ0gcSjWGNng?e=6pqGHV https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/ESQ-kStwD3hAvn63uXVi_X8BAj8X4Td0ZwTO54UwO0togg?e=g0zWgs
09/11/2018 | Kinga Lesniewska |  |  |  | HL Display AB - IT |  | R5.14 Dec | 1J | Delayed payments to suppliers - XBR report - to be moved | report was biiuld to fullfil PL legal requirements - law was cahnge report is not used by PL and any other enity | 3 | KIPA | 4 | 240 | yes |  |  | IMPLEMENTED |  | 09/11/2018 KIPA: part of 1J clean up project ??? (FIN or IT CAB) ( question sent to Kamil) 16/11/2018 KIPA: 7257 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B22110C49-D182-482D-9794-00423AB5DB43%7D&file=Request%20for%20Change%20-%20Template%20-%20HL%20Display.docx&action=default&mobileredirect=true
15/11/2018 | Kinga Lesniewska |  |  |  | HL Display AB - Finance |  | R5.14 Dec | 1J | Upload of budget rates fro 2019 | standard maitenance conected with createing of new year in the system | 5 | KIPA | 4 | 240 | yes |  | 31/12/2018 | IMPLEMENTED | 7253
15/11/2018 | Kinga Lesniewska |  |  |  | HL Display AB - Finance |  |  | QV | Upload of budget rates fro 2019 | standard maitenance conected with createing of new year in the system | 5 | KIPA | 2 | 120 | yes |  | 31/12/2018 | REJECTED | 7254 | 24/1 To be released in Ferbuary and to be moved to Finance
15/11/2018 | Kinga Lesniewska |  |  |  | HL Display AB - Finance |  | R19.3 Mar | CDB | Upload of budget rates fro 2019 | standard maitenance conected with createing of new year in the system | 5 | KIPA | 2 | 120 | yes |  | 31/12/2018 | IMPLEMENTED | 7255 | 24/1 To be released in Ferbuary and to be moved to Finance
16/11/2018 | Marika Westrin | [6 empty] | INFRA | Remove H-drive (where possible) for all users and start using OneDrive instead. |  | 4 | KASC |  | 0 |  |  |  | IMPLEMENTED | CRQ000000448740 | Solution ready, when HL want to implement ! | Kasper checks with Lukas, regarding info to current win10 users | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BBAF629F3-493A-421D-BB0D-A69691DEAE11%7D&file=INC000000795940-RFC%20OneDrive%20to%20replace%20H-drive.docx&action=default&mobileredirect=true
| Marika Westrin | [6 empty] | INFRA | Make H-drive visible again for win10 users | [5 empty] | yes | 28/3/2019 |  | IMPLEMENTED | CRQ000000450821 | Implemented !
16/11/2018 | Marika Westrin | [6 empty] | INFRA | Store Large files |  | 4 | KASC |  | 0 |  |  |  | ON HOLD | WO0000000080287 (This is the old order where the POC was created) | 24/1 Ask Erwan to investigate 28/2 Marika and Erwan to discuss with Lennart J 26/5 2020 : GDM will look into this again. | GDM har satt upp en POC, används den ? | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BB8FD3C7F-2420-4772-B3AF-2225C2E5C7EC%7D&file=INC000000801783%20-%20RFC%20-%20Store%20large%20files.docx&action=default&mobileredirect=true
[7 empty] | R19.11 Nov | INFRA | Replace server in France | Server is old, backup solution is no good. Replace current server with current capacity. Price is 8000 Euro... Reason server gets expensive is much data. If data can be moved to "Store Large Files" solution...server will be cheaper.. | 4 |  |  |  | yes | 2019-05-28 | 30-08-2019 | IMPLEMENTED |  | 2019-10-31 : Planned to be migrated 6 or 7 nov 2019.
16/11/2018 | Marika Westrin | [6 empty] | INFRA | Local Admin, LAPS |  | 3 | KASC |  | 0 | YES | 2019-01-24 |  | IMPLEMENTED |  | 24/1 Marika to take a lead on it. 4/4 Implemented, but with some errors. Investigation |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B602BDB9A-C149-40FA-A544-3DB7BA0519F2%7D&file=INC000000803621-RFC%20Local%20admin.docx&action=default&mobileredirect=true
16/11/2018 | Marika Westrin | [6 empty] | TALENTSOFT | Talentsoft - Sync end-date for users to AD |  |  | KASC |  | 0 |  |  |  | IMPLEMENTED |  | Kamil to talk to Anna. 2019/01/24 Mail Sent to Anna C, to be moved to HR pre-CAB |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B845DEF06-4628-499A-91F6-93ABF3940495%7D&file=INC000000795958-RFC-%20Talentsoft%20-%20Sync%20end-date%20for%20users%20to%20AD.DOCX&action=default&mobileredirect=true
29/11/2018 | GDM | [6 empty] | INFRA | Upgrade of all Fortinet firewalls to version 5.6.6 except Datacenter Sundsvall | Earlier versions of firmware has stability issues. Recommended upgrade from vendor. | 4 | TOWE |  | 0 | YES | 2019-01-24 | 13/12/2018 | IMPLEMENTED |  | CRQ000000448465. Maintenance work from GDM. Will not be charged.
3/12/2018 | Tomas Wetterlund | [6 empty] | INFRA | Removal of backup on 7 servers | Servers have been removed a while ago and we no longer need the backup data. Will lower capacity cost. | 3 | TOWE |  | 0 | YES | 2019-01-24 | 2019-01-01 | IMPLEMENTED |  | CRQ000000448937. DCS-ARO-102, DCS-BIZ-111, DCS-BIZ-711, DCS-CRM-102, DCS-WEB-103, DCS-WEB-114, SDL-WTS-005
03/12/2018 | Dawid Wybierek | [6 empty] | SHAREPOINT | HL Sharepoint Calendar or Jorani | As an HL Employee I want to quickly add vacation/sick leave dates to some webapp and see how many days i can use to spend more time productively and relieve the HR department from repetitive manual activities As a manager I want to see calendar with marked vacations/sick leave from all my subordinates all in 1 clear view To better plan projects in our organizationAs a tester/developer/BC | 3 | KASC |  | 0 |  |  |  | REJECTED |  | 24/1 To be discussed with HR. DevCore has a solution for it. |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/New/calendar%20RFC.docx?d=w752655f9ed224dd7a813a66b75fecbf1&csf=1&e=BonaVk
2018-12-01 | Marika Westrin | [6 empty] | INFRA | Connect ePartner to our SCCM-server. | ePartner will install all new computers from ther office in Copenhagen. WO0000000095275 | 3 | MAWE |  | 3500 | yes |  | 2019-02-01 | IMPLEMENTED
05/12/2018 | Kinga Leśniewska |  |  |  | HL Display AB - Finance |  | R19.10 Oct | 1J | remove unused cristal report F11 from xrb and all conected procedures | removal of unused procedures, better performance | 3 | KIPA | 4 | 240 | yes | 2019-02-28 | 21-06-2019 | IMPLEMENTED | 7527 | 24/1 Kamil to Ask Kinga |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20F11%20report%20cleaning.docx?d=wf2a5416cc34c446eb02838298e48fe87&csf=1&e=F8JxIZ
05/12/2018 | Erwan Lardic | [6 empty] | INFRA | Change Fortinet Equipment in French office | Be able to get benefit of the Optical fiber link upgrade done 13/12/2018 from 100 Mbits/s to 200 Mbits/s (which is not supported by the current FORTINET equipment) | 3 | ErLa |  | 0 |  |  | 2019-01-19 | REJECTED | INC000000829643 | 24/1 Stefan from GDM involved in the setup 28/2 Estimate needed from GDM, INC000000829643 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B56C49B09-5F8C-4FD7-BACF-F26E94A8732C%7D&file=Request%20for%20change%20-%20Change%20Fortinet%20equipment%20French%20Office.docx&action=default&mobileredirect=true
13-12-2018 | Tomi Yrjonen |  |  |  | HL Display Suomi Oy |  |  | EDI | Field “Customer reference” in Jeeves is visible in normal printed invoices. That field is not visible in e-invoices. Because it is visible in printed invoices, it needs to be visible in e-invoices as well. | Better customer communication. Customer-required information on invoices can be handled much better. | 4 | MP |  | 0 |  |  |  | REJECTED |  | It will be handled within sales CAB |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EWlj60-6VcxPjOj5L9OlSkoB-teBWtuvZXOnNrTjpwLZAA?e=IM0McL
14-12-2018 | Tomi Yrjonen |  |  |  | HL Display Suomi Oy |  | R19.1 Jan | EDI | Tieto BIX AS2 Certificate and URL Update needs to be done. | If not implemented, e-invoicing might not work. | 5 | MP |  | 0 | YES | 2019-01-24 | 2019-01-01 | IMPLEMENTED |  |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EXyoYDjwAJpHoSUEmFBFwX0B-zDjQe_3Lpv2cqNY2EpbNg?e=C5TUoq
17-12-2018 | Pawel Nowak | Kamil Saczka |  |  | HL Display AB - IT |  | R5.14 Dec | 1J | Remove button Booking job in olhucorl |  |  |  | 2 | 120 |  |  |  | IMPLEMENTED | 7184
| Mariusz Lekstutis | Kamil Saczka |  |  | HL Display AB - IT |  | R5.14 Dec | 1J | Release process improvement - Remove FileTable (archive) and adjust scripts to use code repository for scripts deployment |  |  |  | 11 | 660 |  |  |  | IMPLEMENTED | 7218
19-10-2017 | Tomas Wetterlund |  |  |  |  | Asia |  | INFRA | AS1-RDS-101 extended because of increased load | Needed for a higher number of users on terminal server | 3 | MAWE |  | 0 | yes |  |  | IMPLEMENTED | INC000000708802 | Will be reset to t2.large when VPN issues with China are solved.
22-05-2018 | Marika Westrin | [6 empty] | INFRA | Follow me printer solution, Nacka | Install new solution to get follow me print working. | 2 | TOWE |  | 0 | yes |  |  | REJECTED | CRQ000000445464 | 2019-08-13: Asked Karin Jobe if we should have this and answer is Yes. Marika will pick up the thread again, waiting on info from karin on who to work with.
29-06-2018 | Marika Westrin |  |  |  | HL Display Sundsvall AB |  |  | INFRA | Wlan for new Hub in Sundsvall |  | 3 | TOWE |  | 0 |  |  |  | ON HOLD | WO0000000092579
27-08-2018 | Tomas Wetterlund |  |  |  | HL Display AB - IT |  |  | INFRA | Discontination of SDL-ROU-006 | Backup system for client VPN in Sundsvall. No longer needed and infected files were found on it. | 2 | TOWE |  | 0 | yes |  | 30-04-2019 | IMPLEMENTED | WO0000000095680 | 7/3. Server shut down, but not removed.
26-09-2018 | Marika Westrin |  |  |  | HL Display France SAS (+ SASU DESIGN) |  |  | INFRA | Upgrade of internet connections in France | Higher capacity and lower cost | 2 | ErLa |  | 0 | yes |  | 10-01-2019 | IMPLEMENTED | CRQ451043 | 24/1 2 failures, new release date 25th of January 28/02 : Main office has been upgraded to 200Mbits 25/01/2019 and Warehouse was upgraded to 100Mbits end of november 2018. Remaining : Automatic 4G backup for main office (planned to be configured by the ISP week 11)
12-11-2018 | Tomas Wetterlund |  |  |  | HL Display AB - IT |  |  | INFRA | Discontination of 10 servers at GDM | Servers are no longer in use | 2 | TOWE |  | 0 | yes |  | 21-02-2019 | IMPLEMENTED | CRQ000000448530
21/12/2018 | Norbert Cieślik | Julia Homik |  |  | HL Display AB - IT |  | R19.3 Mar | 1J | New text field in program q_user | exclud excel file, maitain all user info in Jeeves, | 3 | KIPA | 1 | 60 | yes | 2019-01-24 | 15-02-2019 | IMPLEMENTED | 7404 |  | 26/02/2019 | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/RFC%20-%20text%20field%20in%20q_user.docx?d=w767e3090e876490d9198755213a41cc1&csf=1&e=lcsfbZ
10-1-2018 | Marcin Pianka | [6 empty] | QV | Excluding rules of mapping from data warehouse. Move rules to one common Excel file. | Currently rules are placed directly in the code, even in different places. It is very hard to maintain such code (we ahev to remember about background all the times). We still have number of such requests, so we should make clear current rules and provide fast and clear solution for the future | 4 | MP | 32 | 1920 | yes | 2019-03-05 | 19-04-2019 | IMPLEMENTED | 7415 | 24/1 Juliette Bonda to be involved?
15-01-2019 | Dawid Wybierek | Kamil Saczka |  |  | HL Display AB - IT |  |  | INFRA | I want to extend automated test for application used in HL. To complete that task, I need new server only for that purpose. Optimal configuration: OS: Windows RAM: 8 GB CPU: 4 cores 2.3 GHz HDD: 500 GB | If we will have those tests implemented in HL we can improve quality on our application and be more preventive. We will cover other products than Jeeves with automated test framework. | 4 | KS | 4 | 0 |  |  |  | IMPLEMENTED |  | From standard PrimeQ PriceList: 2300 SEK/month 24/1 to ask GDM for the price as well |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/IT/Request%20for%20change%20-%20New%20server%20for%20tests.docx?d=wea29e50a30524f0d98c93e0dc37ecc4d&csf=1&e=oRAjjh
15-01-2019 | Mariusz Lekstutis | Kamil Saczka |  |  | HL Display AB - IT |  | R19.1 Jan | INFRA | Release process improvement - Add release source database and adopt to process - ErpDevRelease | Reduce the number of the defects after release - related to wrong installation | 4 | KS | 20 | 1200 | YES |  | 01-2019 | IMPLEMENTED
15-01-2019 | Julia Homik | Kamil Saczka |  |  | HL Display AB - IT |  | R19.1 Jan | 1J | Remove design from APPs with business logic part1 |  | 4 | KS | 24 | 1440 | YES |  | 01-2019 | IMPLEMENTED
23-01-2019 | Julia Homik |  |  |  | HL Display AB - IT |  | R19.4 Apr | 1J | Kernel upgrade to version 5.1 R2 | Most important issues that were fixed: - Issues with wrong signature, language and company in some routines due to the SQL server process linked to current user (problem was pointed out by auditors in France) - Security issues when logged-in as a normal user (not system administrator | 5 | JH | 20 | 1200 | yes | 2019-01-24 | 15-03-2019 | IMPLEMENTED | INC000000834974, 7445 | 28/2 To be release in April 28/3 Need feedback from GDM regarding client files |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/IT/Request%20for%20change%20-%20Jeeves%20ERP%20Kernel%20upgrade%20to%20version%205.1%20R2.docx?d=w31eeb3bd2f1a457fa1badc0e03c1644f&csf=1&e=0nc76C
23-01-2019 | Julia Homik |  |  |  | HL Display AB - IT |  | R19.4 Apr | QV | QV upgrade to version 12 | There are common problems with performance and ongoing processes deadlocks in QV in the version that we use right now. It is fixed in version 12 | 4 | JH | 40 | 2400 | yes | 2019-01-24 | 19-04-2019 | IMPLEMENTED | 7363 7364 | 24/1 Suggestion from Tomas: to setup a new server for v12 |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/IT/Request%20for%20change%20-%20QV%20upgrade%20to%20version%2012.docx?d=w7ab19f5c65b24c9c80522c08b119f1d6&csf=1&e=8FJydS
23-01-2019 | Julia Homik |  |  |  | HL Display AB - IT |  | R19.6 Jun | QV | Investigation - solution for DW and Replication DB integration | Request to find a integration platform to get one common solution for data synchornization between Replica and DW. | 4 | JH | 20 | 1200 | yes | 2019-01-24 | 15-03-2019 | IMPLEMENTED | 7483 | 28/3/2019 To be ready 15th of April |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/Open/IT/Request%20for%20change%20-Investigation%20-%20solution%20for%20DW%20and%20Replication%20DB%20integration.docx?d=we782a55737e342cda1c9d7f07dba157e&csf=1&e=wGykJb
10-12-2018 | Reto |  |  |  | HL Display Schweiz |  |  | LOCAL APP | Local software for salary | [5 empty] | no |  |  | REJECTED |  |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/New/INC000000804415%20-%20RFC%20-%20Localy%20software%20for%20salery.docx?d=wd642ccc480034417a8bbf1929c47fe98&csf=1&e=dIsjch
27-02-2019 | Marcin Pianka | Kamil Saczka |  |  | HL Display AB - IT |  |  | 1J | Sales support report should be rewriten from the scratch. Current version is unable to maintain and develop. | This report is crucial for sales offices. We need to adjust it to prebooked orders, but it is impossible in current version. | 5 | MP | 32 | 1920 | yes | 2019-02-28 | 19-04-2019 | IMPLEMENTED | 7409 | Development Accepted, to be release 19th of April |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EYIAYEYobEJCg5i68vAF1KUB6B1aCBLnj9FkbCmGw27dcg?e=tRwqfm
07-03-2019 | Marika Westrin | [6 empty] | INFRA | New WSUS | Current one really old. SDL-SUS-001 | 1 | MW | 12 | 720 | yes | 2019-03-28 | 2019-04-30 | IMPLEMENTED | CRQ000000450831 | 25/4 Server up and running. Need to take descison about logon/logoff policy. Max will contact Marika. Discontinuation of old server is not done yet.
21-03-2019 | Kasper Berg | [6 empty] | INFRA | Upgrade Unifi Controller and APs | Fix bugfixes and improve preformance |  | KB | 4 | 350 | yes | 2019-03-28 | 2019-04-14 | IMPLEMENTED | CRQ000000450993 | Done !
21-03-2019 | Kasper Berg | [6 empty] | INFRA | Move InquiryFormPB to newer webserver | It is currnely running on DCS-WEB-111 and DSC-WEB-112. This function is rairly used and should be moved to DCS-WEB-115 where there are some other websites. We will be able to remove 2 W2008R2 servers because of it. |  | KB | 2 |  | yes | 2019-03-28 | 2019-04-01 | IMPLEMENTED | CRQ000000451062 | 4/4. All is done, seems to be working good. Servers are shutdown
21-03-2019 | Kasper Berg | [6 empty] | INFRA | Move W2000 Server Backup to Veeam | Will be able to terminate the Physical W2000 sever SDL-BAK-001 once it is done |  | KB | 3 |  | yes | 2019-03-28 | 2019-05-01 | IMPLEMENTED | CRQ000000451067 | 25/4. Been up and running for a month.Kasper will write mail of what servers we can shut down. 6 may, waiting on answer from Tomas o. Kasper sent list.
28-03-2019 | Kamil Saczka |  |  |  | HL Display AB - IT |  |  | INFRA | Move E-Approval to new app server | E-approval is now running on DMZ server with public IP dedicated for other applicaions | 4 | KS | 4 | 240 | yes | 2019-03-28 | 2019-06-14 | IMPLEMENTED | 7480 | Waiting on Kamil to decide server
04-04-2019 | Marika Westrin | [6 empty] | INFRA | Remove connection with Remedy | HL is changing to another ticket system called Freshservice on the 1:st April, servicedesk@hl-display.com is currently the address used, this connection needs to be closd as the adress will be needed to route emails to Freshservice |  |  | 1 |  | yes | 2019-04-01 | 2019-04-01 | IMPLEMENTED | CRQ000000451077 | 1/4. Done !
04-04-2019 | Kasper Berg | [6 empty] | INFRA | Agda update 2019.3 | Agda is releasing a new version (Agda 2019.3) The new relase has a minimim requirements of: Application: - Windows Server 2016 or higher. - Windows 10 SQL: - MSQL 2014 or higher. | 4 | Kasper | 4 | 240 | yes | 25/4/2019 | 2019-09-30 | IMPLEMENTED | CRQ000000451113 | 24/4 New server installed. Marek installed SQL.Next step is to move AGDA to the new server. Must be done before 1 october 2019. 6 may, Britt-Marie wants this done during evening/weekend. Need to check if Marek are available. Britt-Marie needs to be availalbe to check upgrade is OK. 2019-08-13. Marika sent question to Marek and Kasper if upgrade can be done 26-29 aug. Suggestion from Britt-Marie.
04-04-2019 | Marika Westrin |  |  |  | HL Display AB - IT | Central |  | INFRA | Update desktop info | Current info on desktop is incorrect. Current solution is via package...no good... We will use Microsoft solution instead | 3 | Marika | 5 | 410 | yes | 25/4/2019 | 2019-06-01 | IMPLEMENTED | CRQ451231
12-04-2019 | Dawid Wybierek | Kamil Saczka |  |  | HL Display AB - IT |  | R19.10 Oct | INFRA | Expand disk on EW1-ADM-112 | For development purpose. | 4 | dawy |  | 0 | yes | 25/4/2019 |  | IMPLEMENTED |  | Kamil to ask PrimeQ 28/08/2019 Kamil to expand the disc |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B02D4CF5B-896E-4B2A-979E-070D808CEEFF%7D&file=EW1_ADM-112%20expand%20disk%20space.docx&action=default&mobileredirect=true
18/04/2019 | Pawel Nowak | Julia Homik | Kamil Saczka |  |  |  | R19.4 Apr | 1J | Jeeves printing viewer not works with new Jeeves Kernel version | Improve effectivity of Design and quality department, save time to prepare file to print screen solution and manual adjustment | 5 | pano | 2.5 | 150 | yes | 2019-04-18 | 2019-04-19 | IMPLEMENTED | 7469 | 18/04pano: based on test result on CFT we discovered issue with new Kernel and Viewer solution |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EbVK-VkuPlNJtlUHfFwVXToB2Yvie9mqw4fG3VF0RpfEAg?e=7bggOd
| Reto Hunziker | Marika Westrin |  |  | HL Display Schweiz |  |  | INFRA | AAR change ISP | Office wants to get rid of ISP from Tele2 (Sweden). They have a new ISP from Schweiz, with better speed and price. |  | Marika | 4 |  | yes | 25/4/2019 |  | IMPLEMENTED | CRQ451405 | Tele2 contract will end 31 may. GDM have set up new ISP. Got feedback from Reto that it works fine now.
25/4/2019 | Matthew Self | Tomas Osbjer | [5 empty] | INFRA | WIFI/Lan upgrade - urgent | To be able to use wireless presentation devices in our conference rooms and have network access. To allow users to move between meeting rooms and offices without dropping network connection. | 5 | Kamil |  | 0 | yes | 25/4/2019 |  | IMPLEMENTED | CRQ451638 | 6 may, need to answer on Kaspers mail (17 april) |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EcdZz0NNay9KgpeEARgGqwsB1NgMSML-7EaAmLp_u0nwjg?email=julia.homik%40hl-display.com&e=B4P9SH
25/4/2019 | Marek Gluklich | Kamil Saczka |  |  | HL Display AB - IT |  |  | INFRA | Upgrade SQL Servers (2016/2017 version) OneJeeves Servers |  | 5 | Kamil | 20 | 1200 | yes | 28/5/2019 | 2020-01-01 | ON HOLD |  | 2019-11-25 Status on this ? Who is taking lead on this ?/ Marika 2020-02-27 : It´s only OneJeeves server. More then ten servers. We need to wait for Kernel upgrade come prob. in march.
30.04.2019 | Marcin Pianka | [5 empty] | R19.8 Aug | PIM | Add PIM into monitoring system | Support has no info about problems with integration Jeeves-PIM and has no possibility to react | 4 | MP | 6 | 360 | yes | 28/5/2019 | 28-06-2019 | IMPLEMENTED | 7525 |  |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EeCVpH3W-6NFu_KgYAO7TbgBE_ZfGJwwcQtZcc_3GRJ23g?e=jy4UHJ
2019-05-28 | Kasper Berg | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  |  | INFRA | WSUS patch routines | Patch routines for servers are old, needs to be checked. | 4 | Kasper | 2 | 120 | yes | 28/5/2019 | 14-06.2019 | IMPLEMENTED | CRQ451822 | 2019-08-13. Kasper will have meeting with Adrian and discuss a suggestion for HL. Will get back with a suggestion to Marika. 2019-09-03. Kasper makes sure to document and send to Marika for approval. |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/IT/RFC%20-%20change%20patchwindow%20on%20servers.docx?d=w4a0c3ab3053145008e3d13d501ab8c05&csf=1&e=8HzzdR
07/05/2019 | Kinga Lesniewska | Graham Wright | Kamil Saczka |  | HL Display AB - IT |  | R19.10 Oct | 1J | Cleaning - remove "reconciliation factoring" report from XRB | Report was modified and moved to QV - the one in XRB is not used any more - cleaning, efficienty | 3 | Kinga | 4 | 240 | yes | 28/5/2019 | 30-08-2019 | IMPLEMENTED | 7527 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/RFC%20-%20factoring%20report%20cleaning.docx?d=wb4dc7d6fdcd24f38ab7b26d51dc5eedc&csf=1&e=6s50SI
2019-05-28 | Kamil Saczka | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.4 Apr | INFRA | Jeeves2Label - investigation of installation on old environment | This is a pre-part of Printing Solution problem, we would like to check if it's possible to install the new adapter for NiceLabel on old version of Jeeves | 4 | KaSc | 20 | 1200 | yes | 2019-03-24 | 19-04-2019 | IMPLEMENTED | 7359
2019-05-28 | Kamil Saczka | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.4 Apr | EDI | Automatic external EDI invoice regression tests | Regression tests (data validation) for key EDI suppliers: Carrefour, Tesco, ASDA, Kesko (TIETO) | 5 | KaSc | 24 | 1440 | yes | 2019-02-21 | 19-04-2019 | IMPLEMENTED | 7370
2019-05-28 | Kamil Saczka | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.4 Apr | EDI | External EDI invoice monitoring - edib early notice and queue order adjustment | Report problem when edib entry is created for invoice and no other monitoring log received since that for longer than 1(?) hour. | 4 | KaSc | 20 | 1200 | yes | 2019-03-04 | 19-04-2019 | IMPLEMENTED | 7391
2019-05-28 | Kamil Saczka | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.4 Apr | EDI | HL EDI monitoring - improve SysEDI FTP monitoring | Add old external EDI to monitoring | 4 | KaSc | 6 | 360 | yes | 2019-03-04 | 19-04-2019 | IMPLEMENTED | 7393
2019-05-28 | Kamil Saczka | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.4 Apr | QV | AP ledger, AR ledger - recalculation to SEK according budget rate | Calculation fix | 4 | KaSc | 8 | 480 | yes | 2019-03-04 | 19-04-2019 | IMPLEMENTED | 7400
2019-05-28 | Kamil Saczka | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.4 Apr | EDI | EDI/API Monitoring - Improvements and optimization | Optimization of the app and layout improvements | 3 | KaSc | 12 | 720 | yes | 2019-01-31 | 19-04-2019 | IMPLEMENTED | 7340
2019-05-28 | Kamil Saczka | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.4 Apr | EDI | Integration monitoring - notification improvement | Add notification service to autostart on reboot - DONE. Create TEST env for Monitoring in Docker. Improve logger for python scripts on fails - DONE | 3 | KaSc | 8 | 480 | yes | 2019-01-21 | 19-04-2019 | IMPLEMENTED | 7347
2019-05-28 | Kamil Saczka | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.4 Apr | 1J | Improvement of Crystal report binding after the release | Jeeves deployment process improvement - bind reports automatically | 4 | KaSc | 8 | 480 | yes | 2019-03-20 | 19-04-2019 | IMPLEMENTED | 7389
2019-05-28 | Kamil Saczka | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.4 Apr | LOCAL APP | Improvement of Jeeves templates handling based on GitLab | Jeeves deployment process improvement - jeeves templates repository | 4 | KaSc | 10 | 600 | yes | 2019-03-20 | 19-04-2019 | IMPLEMENTED | 7390
2019-05-28 | Kamil Saczka | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.4 Apr | INFRA | HL-monitoring DB API | Database for regression tests | 5 | KaSc | 8 | 480 | yes | 2019-03-28 | 19-04-2019 | IMPLEMENTED | 7431
2019-05-28 | Jolanda De Vis | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.4 Apr | EDI | HL Universal Platform - Intergamma setup - part 2 | New EDI flow for Benelux | 5 | KaSc | 12 | 720 | yes | 2019-01-19 | 19-04-2019 | IMPLEMENTED | 7308
2019-05-28 | Kamil Saczka | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  |  | INFRA | Remove the old EPI Servers and Update the server list | Project Web is closed, we need to remove the non used servers. | 4 | KaSc | 2 | 120 | yes | 2019-05-28 | 30-06-2019 | IMPLEMENTED | 7521
2019-05-28 | Kasper Berg | Kamil Saczka | Kamil Saczka |  | HL Display AB - IT |  | R19.6 Jun | INFRA | Upgrade firewall software to version 6 | We are going to do this internally on all GDMs firewalls tomorrow afternoon/night (wednesday 2019-05-29). And on thursday (2019-05-30) between 19-22 we want to do this on HL's enviroment.This is the agreed weekly update window. One or two already has this version 6 but we want it on all the firewalls so we know that it will work |  | Kasper | 4 | 330 | yes | 2019-05-28 | 30-06-2019 | IMPLEMENTED | CRQ000000452065 | Rollback is possible if we run into problems. Low risk since we will notice any problem the day before, when we upgrade GDM´s firewalls.
2019-05-29 | Marika Westrin |  |  |  | HL Display AB - IT |  | R19.10 Oct | INFRA | Change regional timezone for Sharepoint | At the moment Sharepoint timezone is set to UTC -08:00 Pacific Time( USA and Canada). This mean deafult time is -8 hours from CET (Central Europe Time). Deafult should be CET. ServiceDesk have a lot of tickets about timestamp on documents. User are confused. |  | Marika Hugo B | 0.5 | 50 | yes | 27-06-2019 | 30-06-2019 | IMPLEMENTED | 453281 | 2019-08-13. We think this is done, but not confirmed with Hugo. He is on vacation. 2019-09-03 . Implementet when new sites are created. Current sites must be scripted. 2019-09-17 : Script ready, will run on thursday evening.
2019-05-31 | Kamil Saczka |  |  |  | HL Display AB - IT |  | R19.10 Oct | INFRA | Monitoring maintenance improvement - Additional App info on health check site | We would like to see more details on monitoring portal regarding the HL applications. Support and NOC needs to know about the customers impacted, importance and area imediately when failure appears | 4 | KaSc | 8 | 0 | yes | 27-06-2019 | 24-08-2019 | IMPLEMENTED | 7530
2019-05-30 | Kamil Saczka |  |  |  | HL Display AB - IT |  |  | CJ | Pre-Study Jeeves Upgrade for Asian Sales Units - Thaliand, Hong Kong, Korea | Current ERP system is obsolete and most of the modules are not supported. Global HL development is more expensive because of the old architecture, sometimes some installations are not possible to be deployed. | 5 | KS | 40 | 2400 |  |  |  | INVESTIGATION |  | This is not an implementation of the project. This is just a start (pre-study) in order to review the current setup, estimate and recommend different alternatives to management. -Costs should go to IT. //Bjorn Borgman Marcin: Point moved from sales pre-CAB |  | Cost Estimate: https://hldisplay.sharepoint.com/:x:/r/sites/hlabitprojectoffice/_layouts/15/Doc.aspx?sourcedoc={f5a550a4-e6c0-48d2-b2cf-7cc261b8290b}&action=editnew
2019-06-18 | Marika Westrin | [6 empty] | INFRA | Change power settings on all computers | With current settings, computer go to sleep (desktops and laptops) . This change will make computers NOT go to sleep as long as they have power. Better support options and download of media, updates... Details : (user can set own settings if they want) Screen goes to sleep On battery = 10 min Plugged in = 30 min Computer goes to sleep On battery = 20 min Plugged in = Never | 4 | MW | 4 | 240 | yes | 27-06-2019 | 15-07-2019 | IMPLEMENTED | CRQ000000452676 | 2018-08-13. Package tested by Marika. Works fine ! Will test on 10 other users before we sent out to all users.
| Patrik Mattsson | [6 empty] | SHAREPOINT | Partners need a downloadable pricelist in excel so that they can update their own ERP systems with actual pricing. There is currently a function to download price list, but this is only possible for selected items. Need is for the complete pricelist . It should be ready by the end of 2019. -------------------------------------------- Marcin: This functionality is currently connected to the old HL Net. So we have to move it to the new portal. | This has now been made manually with risk of error and unnecessary manpower. |  | MP | 16 | 1600 |  |  |  | INVESTIGATION |  | It has to be ready by the end of 2019 2019-09-27 Ask Christer for support 23/08/2019 Kamil: needs to be checked with DevCore and Pawel Kardas if we can do it internally |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EfXKhYSSoE9NlUt7QpOqm1EBOVeYCswG-2nreKw99e5Q7A?e=G1Ea8Q
2019-07-04 | Marika Westrin | [6 empty] | INFRA | Current password policy = 8 characters, special character needed 90 days intervall New suggestion = 16 characters, special characters needed, keep 90 days. (we have 1 year when MFA is implemented) | 16 characters are impossible to hack... 8 characters are. |  |  | 2 |  |  |  |  | OPEN |  | GDM : Var tredje månad, 15 tecken samt MFA Could be a part of Security Project 2020-05-01 : Implemented for all users with MFA. 16 signs, change once/year. Next step for security reasons is to implement more signs in password, with or without MFA.
2019-01-15 | Kinga Leśniewska |  | Tomas Osbjer |  | HL Display AB - IT |  | R19.6 Jun | QV | Store sales market value - change in QV sales reports |  | 4 | KS | 8 | 480 | Yes | 28-05-2019 | 24/6/2019 | IMPLEMENTED | 4428
2019-01-15 | Kamil Saczka |  | Tomas Osbjer |  | HL Display AB - IT |  | R19.6 Jun | 1J | Synchronize the new version of drawings. |  | 4 | KS | 24 | 1440 | Yes | 28-05-2020 | 24/6/2020 | IMPLEMENTED | 7245
2019-07-04 | Kristian Englund | [6 empty] | INFRA | Upgrade AutoCAD | Since it´s a network license, all user (~20) must upgrade. |  | MW | 25 |  | yes | 28/08/2019 | 2019-12-01 | IMPLEMENTED | CRQ454275 | 2019-11-25, Hugo inventerat, inte fått feedback på att INTE uppgradera. Kör på ! 2020-01-07 : Status ? 2020-02-27 : Hugo tested on several test computers. Package is OK... Someone in HL needs to |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/INC-288%20-%20INC000000836201%20-%20RFC%20-%20Autocad%20Mechanical%202018.docx?d=w624d462ce8a04ff0b9f718d242fd0e74&csf=1&e=ZLYWe3
11.07.2019 | Marcin Pianka |  |  |  | HL Display AB - IT |  |  | EDI | Please change routine of EDI connection between CJ Sundsvall and PR Trading. From HL (Jeeves)<-> SysEDI<-> Evry <-> TrueCommerce <-> Pr-Trading To: HL (Jeeves) <-> TrueCommerce <-> Pr-Trading | It will reduce number of errors and improve quality of connection. Analyzing of errors and fixing them will be also faster. | 4 | MP | 40 | 3000 | yes | 2019-09-27 | 2020-02-01 | SENT TO PROJECT OFFICE |  | 28/08/2019 Kamil: try to move all customers SysEDI |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/Ecjp544dgB1NqgqfMMz3ct4BQ7PFVse1sBnczcNQfn0ddw?e=5D6SRf
17.07.2019 | Marcin Pianka | [5 empty] | R19.10 Oct | SHAREPOINT | Power Apps - license. Do we have plans to give license to all Office 365 users? Right now we have 1 application using this technology (Stock availability) and there is a question if we should go this way. | Point added just to not forget abouth it | 5 | MP |  | 0 | Yes | 28/08/2019 | 2019-09-01 | IMPLEMENTED | 452747
29.07.2019 | Julia H | [6 empty] | 1J | Upgrade of Jeeves to version 5.1 R4 | Upgrade of Jeeves to version 5.1 R4 - the installation package includes all correction to kenrel v5. Especially the problem with Client broker will be solved using that version | 5 | JH | 100 | 6000 | YES | 29/07/2019 | 2020-30-08 | IN PROGRESS | 7593, 7658, 7599 | 14th of August: Marika - problem with ditribution of kernal client files |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EdvbOu4Oea1Gr8wF9QXHg74Bz1ynxtSbfwtRyAdqMEKuhA?email=julia.homik%40hl-display.com&e=qUT3y2
28-08-2019 | Marika Westrin | [6 empty] | INFRA | Windows update behaviour win10 | Users must have option to postpone updates certain ammount of hours. |  | Marika |  | 0 | YES | 28/08/2019 |  | IMPLEMENTED | CRQ000000452935 | 13 aug 2019. Kasper will have meeting with Adrian and then get back to Marika with a suggestion. 2019-09-17 : Börjat med att sätta klient inställningar. Max och Hugo jobbar på detta. Verkar som man missat detta i samband med nya WSUS.Alla uppdateringar som inte kräver omstart går på, krävs det omstart ska man få val att skjuta upp det. Samt att vissa datorer/servrar ska exkluderas och istället uppdateras under "övervakning", så man vet att det passar.
28-08-2019 | Irek |  |  |  | HL Display AB - IT |  |  | INFRA | SQL and server Update for Symfonia (Polish local IT system) |  |  | Irek |  | 0 | YES | 28/08/2019 | September | IMPLEMENTED | 454068 | 2019-11-12 : Irek takes lead from HL. HR dont want us to do anything now, we have OK to make changes after 18 nov 2019-11-25 : Status ? 2020-01-07: Enligt Max kan han inte få fram licensnyckeln. Tomas går på patrick A om detta. 2020-01-17 : upgrade is now done / Marika
[7 empty] | R19.8 Aug | INFRA | remving of 1 network connection |  |  | Marika |  |  | YES | 28/08/2019 | August | IMPLEMENTED
[5 empty] | HL Display AB - IT |  |  | INFRA | Patch windows for server | We need to change this ! |  | Marika | [5 empty] | IMPLEMENTED
30.08.2019 | Marcin Pianka |  | Tomas Osbjer |  | HL Display AB - IT |  |  | 1J | Redesign of program q_product is needed | Currently there is a chaos, which makes problems for users and developers | 4 | MP | 4 | 240 | YES | 20/08/2019 | 2019-01-20 | IN PROGRESS | 7636 | 2019-11-27 : Open, to be released in January 2020 |  | https://hldisplay.sharepoint.com/:w:/s/itdocumentationrepository/EccSWRMgvp1AtFjU3QBERWYBBaMBaNnUknCeaJ87aIQbvQ?e=wbt0Te
2019-08-26 | Marika Westrin | Marika Westrin |  |  | HL Display AB - IT |  | R19.8 Aug | INFRA | Upgrade firewalls | Urgent upgrade, to stop security hole. Will be done 28 aug between 19.00-22.00 |  |  | 3 | 180 | yes | 2019-08-26 | 2019-08-28 | IMPLEMENTED | 453033 | Done ! Without poroblems !
2019-09-03 | Marek G |  | Tomas Osbjer |  | HL Display AB - IT |  | R19.11 Nov | INFRA | Move sql-database to new server. | MBAM server needs to be moved. Otherwise we must buy one extra sql license. Used for bitlocker on win10 computers |  | Marek G |  | 0 | YES | 2019-09-27 |  | IMPLEMENTED | 453357 | 2019-09-17 : Who is doing the investigation ?/ marika 2019-10-31 : Henrik Norenius håller på med detta. 2019-11-12 : I princip klar. SQL-tjänsten är av, så dete borde vara OK att snart gå vidare med att aveckla den gamla servern. 2019-11-25 : Avecklad ? Kasper kollar.
2019-09-03 | Marika Westrin | Marika Westrin | Tomas Osbjer |  | HL Display AB - IT |  | R19.10 Oct | INFRA | Change of GPO | win10 users not able to connect to Microsoft Display adapter. |  | Marika |  | 0 | YES | 2019-09-03 | 2019-09-30 | IMPLEMENTED | 453166 | Tested and verified by marika. 2019-09-17 : Är den utlagd ? Hugo kollar.
2019-09-03 | Marika Westrin |  | Tomas Osbjer |  | HL Display AB - IT |  |  | INFRA | Re occuring problems in RDS | Users have sessions logged on for 12 hours, before they are automatically logged out. They have problem with this. " suggestions. 1. Log out users automatically after 3 hours 2. Log out users when they close the RDS window. Mostly used by Partners, but also HL internal... |  | Kasper | 1 | 60 | YES | 2019-09-27 | 2019-09-30 | IMPLEMENTED | 453026 | 2019-10-31 : Kasper skickar lista på Terminal servers 2019-11-12 : Marika ordered to GDM to implement this
2019-09-03 | Marika Westrin |  | Tomas Osbjer |  | HL Display AB - IT |  | R19.10 Oct | INFRA | Implement Microsoft O365 ATP Standalone | Implement an add on to O365 for security. Especially for e-mails |  | Marika |  | 0 | YES | 2019-09-27 |  | IMPLEMENTED |  | 2019-09-03. Kasper will send UB to Marika
2019-09-05 | Julia Homik |  |  |  | HL Display AB - Finance |  | R19.11 Nov | QV | Budget support | To book the time for suppor the budget reporting |  | Julia | 20 | 1200 | YES | 2019-09-27 | 2019-10-31 | IMPLEMENTED | 7637 | Business Tests
2019-09-06 | Julia Homik |  |  |  | HL Display AB - IT |  |  | 1J | 7-digit item number in Jeeves | Prepare Jeeves to use more digits in the item series. 6-digits serie is getting to the end soon. Otherwise we will not be able to create new products for customers in the system | 5! | Julia | 40 | 2400 | YES | 2019-09-27 |  | IMPLEMENTED | 7688 | 2019-09-27: Christer needs to be involved in order to coordinate 2019-11-27 Feature on business tests |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/IT/Request%20for%20change%20-%207-digits%20Item%20serie%20in%20Jeeves.docx?d=w72ccaaca389042ed9b2076c2848b44ee&csf=1&e=Dnd0gi
2019-09-16 | Kamil Saczka | Kamil Saczka | Tomas Osbjer |  | HL Display AB - IT |  |  | 1J | Jeeves Users accounts - cleanup | clean up is needed because of the licence, maintenance and audit purposes | 4 | KaSc | 2 | 120 | YES | 2019-09-17 | 2020-31-08 | IN PROGRESS | 7646 | 2020-02-27 : Still in progress
2019-09-17 | Magnus Rönn |  | Tomas Osbjer |  |  |  | R19.10 Oct |  |  | GUNG online sales portal needs a new domain. sales-se.hl-display.com |  |  |  | 0 | YES |  |  | IMPLEMENTED |  | 2019-09-17 : Who makes purchase for domains ? Hugo investigate and document in Freshservice
2019-09-27 |  |  | Tomas Osbjer |  |  |  |  | INFRA |  | Nederlands office is moving, 1 jan to be setup and ready. |  |  |  | 0 | YES |  |  | IMPLEMENTED | SR-1972 | 2020-01-07 : Status, har dom flyttat ?
2019-09-27 | [6 empty] | R19.10 Oct |  |  | Maileva dont work on win10 |  |  |  | 0 |  |  |  | IMPLEMENTED
2019-09-27 |  |  | Tomas Osbjer | [6 empty] | IT CAB Calender, suggestion from Marika |  |  |  | 0 | YES |  |  | REJECTED |  | 2020-01-23 : Will look what Freshservice can offer...
2019-10-09 | Karin Jobe | Marika Westrin |  |  | HL Display AB - IT | Headquarter |  | SHAREPOINT | Karin Jobe wants to have a calender for Management group. Only managemant can edit in their outlook, but published and visible for all somewere on Sharepoint (intranet). Malte talked to Lukas on GDM, this is possible, not a huge work. They can do it. | I (marika) like this idea. We can have big use of this for more instance/departments... |  | Marika | 6 | 360 | yes |  |  | IMPLEMENTED | INC-7397 | 2019-11-12 : Troligen har Karin vänt sig till DevCore om detta. Redan klart ? Marika kollar
2019-10-22 | Kinga Lesniewska | Kamil Saczka |  |  | HL Display AB - Finance | Headquarter | R19.11 Nov | 1J | review of functionality from feature 4116 and adding automatic job | fulfiling demands from feature 4116 | 5 | KIPA | 14 | 840 | yes | 22/10/2019 | 11/2019 | IMPLEMENTED | 7684 | 2020-03-31 Kamil: COMPLETED | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B12ECC211-63E7-4B18-993E-C7E4184D257F%7D&file=7684%20RFC%20-%20Automatic%20upload%20of%20budget%20currency%20rates%20%E2%80%93%20job%20to%20move%20date%20.docx&action=default&mobileredirect=true
2019-11-04 | Erwan Lardic |  |  |  | HL Display AB - IT | Headquarter | R19.11 Nov | 1J | With W10 upgrade, SAI-WKS-332 used by DPD Carrier company needs to be replaced. Therefore, some macro need to be updated (as the name of SAI-WKS-332 has been hard coded) | This is a requirement to be able to upgrade to W10 the DPD workstation from SAI HUB | 5 | Erwan | 8 | 480 | yes | 04/11/2019 | Nov | IMPLEMENTED | 7709 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc={9538da8f-3d47-47dd-b2b7-0f9e428c6b93}&action=edit&wdPreviousSession=383368e1%2Da1e4%2D4cb5%2Da139%2D86664c92c465
2019-11-12 | Kasper Berg |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Install AntiVirus on alla PrimeQ-servers. |  |  | Kasper | 8 | 480 |  |  | 2019-11-30 | IMPLEMENTED | 454300 | 2019-11-12 : Measure speed before and after... What is cost ? License ? Kasper will get back with more info. 2019-11-25 : Status ? 2020-01-07 : Aktivera Defendere på dem som det går, strunta i dom andra. Inte lägga så mkt krut på de gamla.Börjar med test-servrar.Mäta prestanda innan och efter. 2020-02-27 : Activate Defender on all test-servers in PrimeQ. Only 2016 and 2019-servers. Havent seen any issues, so want to move on with Production-servers. Desision to go ahead. 2020-03-31: Done |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/IT/CRQ454300%20Antivirus%20on%20PrimeQ%20servers.docx?d=wd493f94def324ca9ae730ca372851545&csf=1&e=aj1xfv
2019-11-12 | Tomas Osbjer |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | AD-loggning | We want to be able to track back in time, if we get hacked, or by requests from HR. |  | Marika |  | 0 | yes |  |  | IN PROGRESS |  | 2019-11-12 : GDM will investigate on this and get back with more info 2019-11-25 : Påslagit, logsize 2GB. Vart ska vi spara den. 2020-01-07 : GDM kollar hur denna ser ut. 2020-02-27 : It´s activated, but we are not sure for how long we can go back. Quite complex to search, maybe a tool is needed. Tomas Å go back to server team and discuss this. 2020-03-31: Logging is currently enabled on individual domain controllers and the logs are stored locally. This makes it difficult to search for deviation etc because you have to log on to each server. Our suggestion is to forward the logs to a central server. That will also makesit easier to adjust the amount of logs to be stored.
2019-11-12 | Hugo Berggren |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Object Access Audit | Allow you to track attempts to access specific objects or types of objects on a network or computer. |  | Marika |  | 0 |  |  |  | INVESTIGATION |  | 2019-11-12 : GDM will investigate on this and get back with more info 2020-02-27 : No more info.. 2020-03-31:; This can be quite extensive. An audit policy is needed for all the things you want to keep track of. The logs need to be taken care of immediately, otherwise they will be overwritten quite quickly, usually the same day. We need to know exactly what is to be monitored, exactly what events and how it should be logged and for how long. | https://docs.microsoft.com/en-us/previous-versions/windows/it-pro/windows-server-2008-R2-and-2008/dd772646%28v%3dws.10%29
2019-11-12 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | TeamViewer package | Make sure TeamViwer licens is installed on HL computers and integrated to Freshservice |  | Marika |  | 0 | yes | 2020-01-23 |  | IMPLEMENTED | CRQ454346 | 2019-11-12 : Rickard sent all info to Tomas Å. Tomas will get back with suggestion on hos to install this in the best way 2020-01-07 : Har gjort ett förslag på ett bättre rutin för att skjuta ut detta. Testat, ser bra ut med grupp 1, fortsätter med grupp 2... GDM planerar att detta ska vara klart den 16:e jan
2019-11-12 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Netclean package | We need to install a new version of Netclean. HL wants this to be installed via SCCM from now on. Marika wants GDM and Netclean support to get togheter and make sure it´s setuped by best practise |  | Marika |  | 0 | yes | 2020-01-23 |  | IMPLEMENTED |  | 2019-11-12 : Sent request for upgrading this to GDM. Waiting for reply 2020-01-07 : Första paketet funkade inte..inte heller andra... Så Tomas kollar upp status på denna. | https://hldisplay.sharepoint.com/:u:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/IT/Konfigurera%20NetClean.msg?csf=1&e=ZcU3ic
2019-11-12 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Backup policy | Review backup policy. Retention time, when do backup jobs go ? Clean up accounts from GDM side, next is to clean up HL side Backup schema |  | Marika |  | 0 | yes | 2020-01-23 |  | IN PROGRESS |  | 2019-11-12 : Backup policy with comments is sent to GDM. We need to be ready with Backup policy within 2,5 weeks (Management meeting) 2020-01-07 : Inget mer från GDM som vi väntar på.
2019-11-12 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | G:\ Access | For some reason , a lot of people had access on G-drive. SDL G-drive is fixed. Gliwice seems to be just as bad. Hugo have ticket |  | Marika |  | 0 | yes | 2020-01-23 |  | IN PROGRESS | INC-10002 | 2019-11-12 : Created ticket for GDM 2:nd line 2020-01-07 : Kollar status. 2020-02-27 : Hugo and Malte is looking into this in France as well. Ongoing and time consuming. Why not Gliwice ? |  | https://hldisplayab.freshservice.com/helpdesk/tickets/10002
2019-11-13 | Lennart Björk |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Upgrade SolidWorks | Recomendation from PLM Group is to upgrade now. All users must upgrade at the same time. I want price and time estimation |  | Marika |  | 0 | yes |  | September | ON HOLD |  | 2019-11-13 : Sent questions to GDM and asked for price and hours. 2020-01-07 : Tomas kollar upp med Bredin om denna. 2020-02-27 : Been in contact with Lennart and PLM. Will prob. happen in May. They are waiting for a new version/fix. |  | https://hldisplay.sharepoint.com/:u:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/IT/Upgrade%20SolidWorks.msg?csf=1&e=EzqxDY
2019-11-22 | Kamil Saczka |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Investigate the SMS service for HL IT Tools |  |  | Kamil | [5 empty] | IMPLEMENTED | 7665
2019-12-05 | Kamil Saczka |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | New EPI project handover from Devcore | To ensure proper knowledge handover by Daniel from Devcore | 5 | Mariusz | 32 | 960 | yes | 2019-12-05 |  | IMPLEMENTED | 7757
2019-12-09 | Mariusz Lekstutis |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | New SFTP server for E-approval on PrimeQ (GDM) | Long term goal is to move current FTP sites to the new SFTP and new file storage location. | 4 | Mariusz | 4 | 120 | yes | 2019-12-10 | april | IMPLEMENTED |  | 2020-01-07 : Kom in precis innan jul, har ingen status på denna än, Kasper kollar. 2020-02-27 :Tomas Å. Technican in server team will get in contact with Mariusz very sson.. Kamil says the server is already up ? 2020-03-31: The new server is installed and sftp is being configured |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B20CB6185-AB37-4A05-B216-9D160E63E5A9%7D&file=9612%20New%20SFTP%20Server.docx&action=default&mobileredirect=true
22/05/2019 | Andreas Astgard | Lennart Johansson | Andreas Astgård |  | Costs info in comment |  |  | SHAREPOINT | DevCore contract system | Setup correct account and rights for DEVCore team | 4 | pano |  | 0 | yes | 2019-12-06 |  | IMPLEMENTED | INC-9894 - FW: avtalshantering | The invoice should be sent to HL AB (ref Lennart Johansson) 10/12/2019 added in IT CAB to have control track |  | https://hldisplay.sharepoint.com/:p:/s/itdocumentationrepository/ETZBF4yHCMBGmOd_UhpBRzEBs0Bs84geJkLC5qaL8igQKg?e=y9Zrzs
2019-12-16 | Mariusz Lekstutis |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | DB Structure Monitoring - extend collected informatio | We need to collect more detailed information from database monitoring solution | 4 | Mariusz | 1 | 30 | yes |  |  | IMPLEMENTED | 7695
2019-12-17 | Mariusz Lekstutis |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Object oriented SQL repository. Part 1 - analysis | To evaluate possibility to switch fully to object oriented GitLab repository in order to improve development process | 4 | Mariusz | 4 | 120 | yes | 2020-01-23 |  | IMPLEMENTED | 7597
2019-12-18 | Mariusz Lekstutis |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Auto archive solution for output files - investigation | In order to take care better for storage amount on network drives it is necessary to itroduce auto archive solution for output files | 4 | Mariusz | 8 | 240 | yes | 2020-01-23 |  | IMPLEMENTED | 7715 | 2020-02-27 : Investigation finished. Huge list. Now it´s time to implement some archive solution.
2020-02-18 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Get control over what we isntall manually and being able to get rid of local admin access. | See details in RFC |  | Marika |  | 8000 | yes | 2020-03-31 |  | IMPLEMENTED |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/Request%20for%20Change%20-%20AdminByRequest.docx?d=w3ea1909c528b4b95984c2d55029a8118&csf=1&e=KquZOT
2020-02-18 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Implement MFA for O365 | To secure accounts |  | Marika |  |  | yes | 2020-02-27 |  | IMPLEMENTED |  | 2020-02-18 : Asked GDM to investigate and come with proposal on how to implement
2020-02-18 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Remove external being able to send e-mail to internal HL groups | To secure and lower risk of SPAM |  | Marika |  |  | yes | 2020-03-31 |  | IMPLEMENTED |  | 2020-02-18 : Implement on groups that have more then 30 members ? Or lower or higher ?
2020-02-26 | HR Local | [6 empty] | INFRA | UPS service and tests (regular control) | To secure the INFRA locally - GDPR requests | 4 | Kamil | [5 empty] | INVESTIGATION |  | GDPR request
2020-02-27 | HR Local | [6 empty] | INFRA | USB ports policy / security | To secure the INFRA locally - GDPR requests | 4 | Kamil | [5 empty] | INVESTIGATION |  | 2020-02-27: Tomas A to discuss it internally with GDM specialists 20200331: t is possible to block write access to all portable disk drives, it is done using a gpo. However, we do not recommend this as it is not a flexible way of dealing with the problem. GPO is also set client level, not users. Instead, we recommend that you work with classification of documents and files. Then you can give read or write access per document, permission to print, download etc.
2020-03-02 | Erwan Lardic |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Extension/improvement of q_mail_log functionality in Jeeves Business Mail Application needed | Improve the maillog functionality existing in 1Jeeves in order to have the business informed if they have entered a wrong mail address for their invoice recipient See details in RFC We have significantly increased the number of the invoices send by mail automatically. Current solution is based on standard SQL Mail engine which is not good enough for sending high volume of mails with attachments. Professional mail service is required. | 5 | Erwan |  | 3000 |  |  |  | INVESTIGATION |  | 2020-05-28 Product Evaluation started. 3 options to be evaluated. One option with offer (Azure + SendGrid) - cost ~60 EUR/month |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B12B388FA-A859-485D-BE77-ED755CC8F9D0%7D&file=RFC%20-%20improvement%20of%20q_maillog%20functionality.docx&action=default&mobileredirect=true
2020-03-04 | Kamil Saczka |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Business Mail Application needed Merged with previous row | We have significantly increased the number of the invoices send by mail automatically. Current solution is based on standard SQL Mail engine which is not good enough for sending high volume of mails with attachments. Prodessional mail service is required. | 5 | Kamil | [5 empty] | REJECTED
2020-03-05 | Kinga Leśniewska | Kamil Saczka |  |  | HL Display AB - IT | Headquarter |  | 1J | Remove company 2985 from 1J | There are no plans to join 2985 to Jeeves. Plan is to leave them with local system and integrate. Due to above there is no need to keep additional empty company which will use system resources | 4 | KIPA | 6 | 180 | Yes | 2020-03-31 |  | OPEN | 7899 |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/IT/RFC%20-%20Remove%202985%20from%201J.docx?d=w457d32943e204519bb8f73200534db40&csf=1&e=djmbIi
2020-03-18 | Kinga Lesniewska | Kamil Saczka |  |  | HL Display AB - IT | Headquarter |  | 1J | create tool to monttor files sent to Intrum on intrum's SFTP | possiblity to controll files which we sent to Intrum and react on issues in shorter period of time | 4 | KIPA | 4 | 120 | Yes | 2020-03-31 |  | OPEN | 7910
2020-03-31 | Kamil Saczka |  |  |  | HL Display AB - IT | Headquarter |  |  | CAB Process automations |  | 4 | KASC |  | 0 | Yes |  |  | IN PROGRESS
2020-05-06 | Mariusz Lekstutis | Kamil Saczka |  |  | HL Display AB - IT | Headquarter |  | 1J | Auto archive solution for output files - implementation (start with WSO2) | In order to introduce common auto archive solution for output files from different solutions. Based on previous investigation now we want to implement a solution starting with WSO2 | 4 | MaLk | 8 | 0 | yes | 2020-05-28 |  | OPEN | 7978
2020-05-06 | Mariusz Lekstutis | Kamil Saczka |  |  | HL Display AB - IT | Headquarter |  | 1J | Evaluation of solution for safe password handling in HL applications (start with WSO2) | Evaluation and implementation of solution for safe password handling in HL applications | 5 | MaLk | 8 | 0 | yes | 2020-05-28 |  |  | 7976
2020-05-26 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Implement Microsoft Defender ATP | Antivirus on computers in not good enough. We need more security. Defender ATP is antivirus on steroids :-) We have license for it already. Just need cost for implementation (package distribution) |  | Marika | 8 | 600 | yes | 2020-05-28 |  | IN PROGRESS
2020-05-26 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Remove creation of rule in outlook to forward email to external e-mail | Security risk. Best practise setup. |  | Marika | 2 | 160 | yes | 2020-05-28 |  | IMPLEMENTED
2020-05-26 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Implement new Firewall in Nacka | Upgrade old/inadequate equipment |  | Marika |  | 4500 | yes | 2020-04-01 |  | IMPLEMENTED |  | firewall replaced in June
2020-05-26 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Implement new Firewall in Gliwice Factory | Upgrade old/inadequate equipment |  | Marika |  | 4500 | yes | 2020-05-01 |  | IMPLEMENTED |  | firewall replaced in July
2020-05-26 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Implement new Firewall in Sundsvall Factory | Upgrade old/inadequate equipment |  | Marika |  | 4500 | yes | 2020-05-26 |  | IMPLEMENTED |  | CRQ000000458198 implemented i july
2020-05-26 | Marika Westrin |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Implement new switches in Sundsvall Factory | Upgrade old/inadequate equipment |  | Marika |  | 9500 | yes | 2020-05-26 |  | IMPLEMENTED |  | CRQ000000458198 implemented i july
2020-05-28 | Tomas Åberg |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Activate FSSO i France | Link between firewall and Activ directory. Allows only HL computers to connect to the office network. Have been in monitoring mode for a couple of weeks. GDM wants to activate it next week. Will be carried out during office hours so that we can immediately detect the impact and possible problems. Step 1 - Internet traffic: |  | Tomas |  |  | yes | 2020-05-28 |  | ON HOLD |  | 2020-06-25: Internet traffic is blocked (non HL computers) and monitored. other traffic is monitored in the firewall. 2020-08-14: the change is reversed due to problems with RDS connections
2020-05-28 | Tomas Åberg |  |  |  | HL Display AB - IT | Headquarter |  | INFRA | Disable IPv6 | Disable IPv6 on all servers, can cause problems in communications when ativated. can be done with a group policy before patch window. |  | Tomas |  |  | yes | 2020-05-28 |  | OPEN |  | 2020-06-25: Due to the troubleshooting of communication problems, we have waited to proceed with this right now. 2020-08-14: Microsoft's best practice is not to disable ipv6 completely. What they suggest is that you should instead set so that the servers prefer ipv4 over ipv6. Proposals for implementation are sent to Marika.
25/05/2020 | Patryk Baczek | Magda Oczko |  |  | HL Display Gliwice Sp z.o.o |  |  | SHAREPOINT | Moving the website https://test.sprzedajsuknie.pl/engel/ to our internal network | The owner of this website is our employee Kamil.Mackiewicz@hl-display.com. Have website which is key for update items (weight, time etc.) in our network like it should be from the beginning. |  | sonkur/pano |  |  | yes | 2020-09-24 |  | INVESTIGATION |  | RFC to be moved to Production |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7B1B2831CB-29F5-4A01-BBE1-6418945BD9DF%7D&file=Request%20for%20change%20-%20Sprzedaj%20suknie.docx&action=default&mobileredirect=true
25/06/2020 | Marika Westrin | Kamil Saczka |  |  | HL Display AB - IT |  |  | EDI | EDI Configuration - AWS Asia move to Azure | to install the old EDI application on the new server in Azure is needed |  | kasc | 8 |  | yes | 2020-06-25 | 2020-06-29 | IMPLEMENTED
2020-08-27 | Marika Westrin | Marika Westrin |  |  | HL Display AB - IT | Central |  | INFRA | Azure AD Password Protection | We will not be able to use simple passwords, known bad pad password or leaked password on darknet.. Highly recomended by Microsoft to apply this. This function is included in our Enterprise Agreement |  | Marika |  | 80 | yes | 2020-09-24 |  | OPEN |  | Cost is for the setup and documentation by technichian
27/08/2020 | Mariusz Lekstutis |  |  |  | HL Display AB - IT | Central |  | EDI | Improve PO unblock link security (and other links) | The purpose is to try to find (investigation) another solution for functionalities as unblocking PO which is now conflicting with Outlook security policy causing errors | 4 | MaLk | 4 | 240 | yes | 2020-09-24 |  | OPEN
08/09/2020 | Erwan Lardic | Olivier Pedroncini |  |  | HL Display France SAS (+ SASU DESIGN) | West | R20.10 Oct | LOCAL APP | In the frame of the CORONA virus pandemy , we need to have deployed in the software center the application "AVAYA Communicator" | This will allow the sales support team to be able to take phone calls from home while connected to the VPN exactly like if they were physically in the office | 5 | ErLa | 4 |  | yes | 2020-09-24 |  | IMPLEMENTED |  |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/_layouts/15/Doc.aspx?sourcedoc=%7BBFC2847B-3F27-4A9B-96C2-4291D5FCB171%7D&file=Request%20for%20Change%20-%20AVAYA%20Communicator%20in%20Software%20Center.docx&action=default&mobileredirect=true
16/09/2020 | Dawid Wybierek | Kamil Saczka |  |  | HL Display AB - IT |  |  | INFRA | Add HL IT Group in the HL Domain and assign IT Employees. | Security cleanup users <-> IT Specialists | 4 | KaSc | [5 empty] | INVESTIGATION |  | More specifiction needed: what is a purpose? Which applications? etc
24/09/2020 | Tomas Aberg |  |  |  | HL Display AB - IT |  |  | INFRA | New firewall for UK | More capacity, better secuirity options | 5 | Tomas |  |  | yes | 2020-09-24 |  | IN PROGRESS
24/09/2020 | Kinga Lesniewska | Kamil Saczka |  |  | HL Display AB - IT |  |  | 1J | replication rules for AK tabel in 1J | setting up stabel and comman replication on ths tabel will allow to avoid many incidebnts and amnual handling of changes in all programs conected with AK tabel | 4 | KIPA | 16 | 960 |  |  |  | OPEN |  |  |  | https://hldisplay.sharepoint.com/:w:/r/sites/itdocumentationrepository/Delade%20dokument/CAB/RFC/10.%20Open%20and%20New/IT/RFC%20-%20replication%20in%20Jeeves%20tabel%20AK.docx?d=w193ab3af9af74430bc87c7650231afa6&csf=1&web=1&e=eOlYpG
05/10/2020 | Dawid Wybierek | Kamil Saczka |  |  | HL Display AB - IT |  |  | 1J | Printing jeeves reports from sql - invastigation | Check possibility to generate pdf from sql. We want to have solution that is independent from Jeeves because of "out of space" problem. | 5 | dawy | 8 | 480 | yes | 2020-10-05 |  | OPEN |  | Urgent Pre-CAB (Dawid, Kamil)
06/10/2020 | Marika Westrin | Marika Westrin |  |  | HL Display AB - IT |  |  | INFRA | Get rid of Skype and use Teams as first chat appl. | Microsoft will drop Skype, they extended ut to june 2021. My suggestion is to drop it arround Christmas. S4B will stop working when we do this, we cannot have both anymore... S4B is today the preffered chat in HL. |  | maws | 2 | 160